## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Bardhaman, Murshidabad, Malda, Dakshin & Uttar Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19000 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Uttar Dinajpur District. | Assistant Engineer | Junior Engineer | ORD/000101/2023-2024 | 2700/RS | 30/08/2023 | 28/02/2024 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 105.62 | 105.62 | 100 | 99
2 | MALDAH |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Bardhaman, Murshidabad, Malda, Dakshin & Uttar Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19000 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Uttar Dinajpur District. | Assistant Engineer | Junior Engineer | ORD/000101/2023-2024 | 2700/RS | 30/08/2023 | 28/02/2024 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 105.62 | 105.62 | 100 | 99
3 | MURSHIDABAD |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Bardhaman, Murshidabad, Malda, Dakshin & Uttar Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19000 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Uttar Dinajpur District. | Assistant Engineer | Junior Engineer | ORD/000101/2023-2024 | 2700/RS | 30/08/2023 | 28/02/2024 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 105.62 | 105.62 | 100 | 99
4 | PURBA BARDHAMAN |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Bardhaman, Murshidabad, Malda, Dakshin & Uttar Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19000 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Uttar Dinajpur District. | Assistant Engineer | Junior Engineer | ORD/000101/2023-2024 | 2700/RS | 30/08/2023 | 28/02/2024 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 105.62 | 105.62 | 100 | 99
5 | UTTAR DINAJPUR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Bardhaman, Murshidabad, Malda, Dakshin & Uttar Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19000 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Uttar Dinajpur District. | Assistant Engineer | Junior Engineer | ORD/000101/2023-2024 | 2700/RS | 30/08/2023 | 28/02/2024 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 105.62 | 105.62 | 100 | 99
6 | DAKSHIN DINAJPUR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Bardhaman, Murshidabad, Malda, Dakshin & Uttar Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19000 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Malda District. | Assistant Engineer | Junior Engineer | ORD/000115/2023-2024 | 2748/RS | 05/09/2023 | 05/03/2024 | CHAKVIGU VIDYASAGAR SOCIAL WELFARE SOCIETY | 172.98 | 172.98 | 100 | 50
7 | MALDAH |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Bardhaman, Murshidabad, Malda, Dakshin & Uttar Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19000 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Malda District. | Assistant Engineer | Junior Engineer | ORD/000115/2023-2024 | 2748/RS | 05/09/2023 | 05/03/2024 | CHAKVIGU VIDYASAGAR SOCIAL WELFARE SOCIETY | 172.98 | 172.98 | 100 | 50
8 | MURSHIDABAD |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Bardhaman, Murshidabad, Malda, Dakshin & Uttar Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19000 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Malda District. | Assistant Engineer | Junior Engineer | ORD/000115/2023-2024 | 2748/RS | 05/09/2023 | 05/03/2024 | CHAKVIGU VIDYASAGAR SOCIAL WELFARE SOCIETY | 172.98 | 172.98 | 100 | 50
9 | PURBA BARDHAMAN |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Bardhaman, Murshidabad, Malda, Dakshin & Uttar Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19000 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Malda District. | Assistant Engineer | Junior Engineer | ORD/000115/2023-2024 | 2748/RS | 05/09/2023 | 05/03/2024 | CHAKVIGU VIDYASAGAR SOCIAL WELFARE SOCIETY | 172.98 | 172.98 | 100 | 50
10 | UTTAR DINAJPUR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Bardhaman, Murshidabad, Malda, Dakshin & Uttar Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19000 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Malda District. | Assistant Engineer | Junior Engineer | ORD/000115/2023-2024 | 2748/RS | 05/09/2023 | 05/03/2024 | CHAKVIGU VIDYASAGAR SOCIAL WELFARE SOCIETY | 172.98 | 172.98 | 100 | 50
11 | DAKSHIN DINAJPUR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Bardhaman, Murshidabad, Malda, Dakshin & Uttar Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19000 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Murshidabad. | Assistant Engineer | Junior Engineer | ORD/000190/2023-2024 | 3371/RS | 08/11/2023 | 08/05/2024 | IMAGIN | 306.66 | 306.66 | 100 | 50
12 | MALDAH |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Bardhaman, Murshidabad, Malda, Dakshin & Uttar Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19000 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Murshidabad. | Assistant Engineer | Junior Engineer | ORD/000190/2023-2024 | 3371/RS | 08/11/2023 | 08/05/2024 | IMAGIN | 306.66 | 306.66 | 100 | 50
13 | MURSHIDABAD |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Bardhaman, Murshidabad, Malda, Dakshin & Uttar Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19000 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Murshidabad. | Assistant Engineer | Junior Engineer | ORD/000190/2023-2024 | 3371/RS | 08/11/2023 | 08/05/2024 | IMAGIN | 306.66 | 306.66 | 100 | 50
14 | PURBA BARDHAMAN |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Bardhaman, Murshidabad, Malda, Dakshin & Uttar Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19000 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Murshidabad. | Assistant Engineer | Junior Engineer | ORD/000190/2023-2024 | 3371/RS | 08/11/2023 | 08/05/2024 | IMAGIN | 306.66 | 306.66 | 100 | 50
15 | UTTAR DINAJPUR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Bardhaman, Murshidabad, Malda, Dakshin & Uttar Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19000 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Murshidabad. | Assistant Engineer | Junior Engineer | ORD/000190/2023-2024 | 3371/RS | 08/11/2023 | 08/05/2024 | IMAGIN | 306.66 | 306.66 | 100 | 50
16 | DAKSHIN DINAJPUR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Bardhaman, Murshidabad, Malda, Dakshin & Uttar Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19000 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Daskhin Dinajpur District. | Assistant Engineer | Junior Engineer | ORD/000114/2023-2024 | 2747/RS | 05/09/2023 | 05/03/2024 | CHAKVIGU VIDYASAGAR SOCIAL WELFARE SOCIETY | 90.4 | 90.4 | 100 | 50
17 | MALDAH |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Bardhaman, Murshidabad, Malda, Dakshin & Uttar Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19000 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Daskhin Dinajpur District. | Assistant Engineer | Junior Engineer | ORD/000114/2023-2024 | 2747/RS | 05/09/2023 | 05/03/2024 | CHAKVIGU VIDYASAGAR SOCIAL WELFARE SOCIETY | 90.4 | 90.4 | 100 | 50
18 | MURSHIDABAD |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Bardhaman, Murshidabad, Malda, Dakshin & Uttar Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19000 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Daskhin Dinajpur District. | Assistant Engineer | Junior Engineer | ORD/000114/2023-2024 | 2747/RS | 05/09/2023 | 05/03/2024 | CHAKVIGU VIDYASAGAR SOCIAL WELFARE SOCIETY | 90.4 | 90.4 | 100 | 50
19 | PURBA BARDHAMAN |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Bardhaman, Murshidabad, Malda, Dakshin & Uttar Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19000 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Daskhin Dinajpur District. | Assistant Engineer | Junior Engineer | ORD/000114/2023-2024 | 2747/RS | 05/09/2023 | 05/03/2024 | CHAKVIGU VIDYASAGAR SOCIAL WELFARE SOCIETY | 90.4 | 90.4 | 100 | 50
20 | UTTAR DINAJPUR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Bardhaman, Murshidabad, Malda, Dakshin & Uttar Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19000 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Daskhin Dinajpur District. | Assistant Engineer | Junior Engineer | ORD/000114/2023-2024 | 2747/RS | 05/09/2023 | 05/03/2024 | CHAKVIGU VIDYASAGAR SOCIAL WELFARE SOCIETY | 90.4 | 90.4 | 100 | 50
21 | DAKSHIN DINAJPUR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Bardhaman, Murshidabad, Malda, Dakshin & Uttar Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19000 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Purba Bardhaman District. | Assistant Engineer | Junior Engineer | ORD/000098/2023-2024 | 2683/RS | 29/08/2023 | 27/02/2024 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 262.36 | 262.36 | 100 | 99
22 | MALDAH |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Bardhaman, Murshidabad, Malda, Dakshin & Uttar Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19000 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Purba Bardhaman District. | Assistant Engineer | Junior Engineer | ORD/000098/2023-2024 | 2683/RS | 29/08/2023 | 27/02/2024 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 262.36 | 262.36 | 100 | 99
23 | MURSHIDABAD |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Bardhaman, Murshidabad, Malda, Dakshin & Uttar Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19000 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Purba Bardhaman District. | Assistant Engineer | Junior Engineer | ORD/000098/2023-2024 | 2683/RS | 29/08/2023 | 27/02/2024 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 262.36 | 262.36 | 100 | 99
24 | PURBA BARDHAMAN |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Bardhaman, Murshidabad, Malda, Dakshin & Uttar Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19000 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Purba Bardhaman District. | Assistant Engineer | Junior Engineer | ORD/000098/2023-2024 | 2683/RS | 29/08/2023 | 27/02/2024 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 262.36 | 262.36 | 100 | 99
25 | UTTAR DINAJPUR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Bardhaman, Murshidabad, Malda, Dakshin & Uttar Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19000 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Purba Bardhaman District. | Assistant Engineer | Junior Engineer | ORD/000098/2023-2024 | 2683/RS | 29/08/2023 | 27/02/2024 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 262.36 | 262.36 | 100 | 99
26 | DAKSHIN DINAJPUR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Bardhaman, Murshidabad, Malda, Dakshin & Uttar Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19000 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Uttar Dinajpur District. | Assistant Engineer | Junior Engineer | ORD/000320/2023-2024 | 715/RS | 01/03/2024 | 01/01/2025 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 162.33 | 41.2 | 25.38 | 35
27 | MALDAH |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Bardhaman, Murshidabad, Malda, Dakshin & Uttar Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19000 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Uttar Dinajpur District. | Assistant Engineer | Junior Engineer | ORD/000320/2023-2024 | 715/RS | 01/03/2024 | 01/01/2025 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 162.33 | 41.2 | 25.38 | 35
28 | MURSHIDABAD |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Bardhaman, Murshidabad, Malda, Dakshin & Uttar Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19000 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Uttar Dinajpur District. | Assistant Engineer | Junior Engineer | ORD/000320/2023-2024 | 715/RS | 01/03/2024 | 01/01/2025 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 162.33 | 41.2 | 25.38 | 35
29 | PURBA BARDHAMAN |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Bardhaman, Murshidabad, Malda, Dakshin & Uttar Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19000 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Uttar Dinajpur District. | Assistant Engineer | Junior Engineer | ORD/000320/2023-2024 | 715/RS | 01/03/2024 | 01/01/2025 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 162.33 | 41.2 | 25.38 | 35
30 | UTTAR DINAJPUR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Bardhaman, Murshidabad, Malda, Dakshin & Uttar Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19000 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Uttar Dinajpur District. | Assistant Engineer | Junior Engineer | ORD/000320/2023-2024 | 715/RS | 01/03/2024 | 01/01/2025 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 162.33 | 41.2 | 25.38 | 35
Total | [13 empty] | 5501.76 | 4896.09 | 88.99