## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Malda, Uttar Dinajpur and Dakshin Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19234 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Malda District. | Assistant Engineer | Junior Engineer | ORD/000211/2024-2025 | 3184/RS | 30/12/2024 | 30/03/2025 | CHAKVIGU VIDYASAGAR SOCIAL WELFARE SOCIETY | 86.4 | 0 | 0 | 99
2 | MALDAH |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Malda, Uttar Dinajpur and Dakshin Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19234 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Malda District. | Assistant Engineer | Junior Engineer | ORD/000211/2024-2025 | 3184/RS | 30/12/2024 | 30/03/2025 | CHAKVIGU VIDYASAGAR SOCIAL WELFARE SOCIETY | 86.4 | 0 | 0 | 99
3 | UTTAR DINAJPUR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Malda, Uttar Dinajpur and Dakshin Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19234 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Malda District. | Assistant Engineer | Junior Engineer | ORD/000211/2024-2025 | 3184/RS | 30/12/2024 | 30/03/2025 | CHAKVIGU VIDYASAGAR SOCIAL WELFARE SOCIETY | 86.4 | 0 | 0 | 99
4 | DAKSHIN DINAJPUR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Malda, Uttar Dinajpur and Dakshin Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19234 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Daskhin Dinajpur District. | Assistant Engineer | Junior Engineer | ORD/000212/2024-2025 | 3185/RS | 30/12/2024 | 30/03/2025 | CHAKVIGU VIDYASAGAR SOCIAL WELFARE SOCIETY | 44.14 | 0 | 0 | 99
5 | MALDAH |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Malda, Uttar Dinajpur and Dakshin Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19234 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Daskhin Dinajpur District. | Assistant Engineer | Junior Engineer | ORD/000212/2024-2025 | 3185/RS | 30/12/2024 | 30/03/2025 | CHAKVIGU VIDYASAGAR SOCIAL WELFARE SOCIETY | 44.14 | 0 | 0 | 99
6 | UTTAR DINAJPUR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Malda, Uttar Dinajpur and Dakshin Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19234 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Daskhin Dinajpur District. | Assistant Engineer | Junior Engineer | ORD/000212/2024-2025 | 3185/RS | 30/12/2024 | 30/03/2025 | CHAKVIGU VIDYASAGAR SOCIAL WELFARE SOCIETY | 44.14 | 0 | 0 | 99
7 | DAKSHIN DINAJPUR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Malda, Uttar Dinajpur and Dakshin Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19234 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Malda District. | Assistant Engineer | Junior Engineer | ORD/000317/2023-2024 | 736/RS | 04/03/2024 | 04/01/2025 | CHAKVIGU VIDYASAGAR SOCIAL WELFARE SOCIETY | 267.68 | 223.88 | 83.64 | 50
8 | MALDAH |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Malda, Uttar Dinajpur and Dakshin Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19234 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Malda District. | Assistant Engineer | Junior Engineer | ORD/000317/2023-2024 | 736/RS | 04/03/2024 | 04/01/2025 | CHAKVIGU VIDYASAGAR SOCIAL WELFARE SOCIETY | 267.68 | 223.88 | 83.64 | 50
9 | UTTAR DINAJPUR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Malda, Uttar Dinajpur and Dakshin Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19234 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Malda District. | Assistant Engineer | Junior Engineer | ORD/000317/2023-2024 | 736/RS | 04/03/2024 | 04/01/2025 | CHAKVIGU VIDYASAGAR SOCIAL WELFARE SOCIETY | 267.68 | 223.88 | 83.64 | 50
10 | DAKSHIN DINAJPUR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Malda, Uttar Dinajpur and Dakshin Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19234 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Daskhin Dinajpur District. | Assistant Engineer | Junior Engineer | ORD/000316/2023-2024 | 735/RS | 04/03/2024 | 04/01/2025 | CHAKVIGU VIDYASAGAR SOCIAL WELFARE SOCIETY | 141.49 | 99.42 | 70.27 | 99
11 | MALDAH |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Malda, Uttar Dinajpur and Dakshin Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19234 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Daskhin Dinajpur District. | Assistant Engineer | Junior Engineer | ORD/000316/2023-2024 | 735/RS | 04/03/2024 | 04/01/2025 | CHAKVIGU VIDYASAGAR SOCIAL WELFARE SOCIETY | 141.49 | 99.42 | 70.27 | 99
12 | UTTAR DINAJPUR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Malda, Uttar Dinajpur and Dakshin Dinajpur districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19234 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Daskhin Dinajpur District. | Assistant Engineer | Junior Engineer | ORD/000316/2023-2024 | 735/RS | 04/03/2024 | 04/01/2025 | CHAKVIGU VIDYASAGAR SOCIAL WELFARE SOCIETY | 141.49 | 99.42 | 70.27 | 99
Total | [13 empty] | 1619.15 | 969.9 | 59.9