## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Malda, Uttar Dinajpur, Dakshin Dinajpur districts under Jal Jeevan Mission (JJM) Support Activities | SM/19355 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Uttar Dinajpur District. | Assistant Engineer | Junior Engineer | ORD/000222/2024-2025 | 3197/RS | 31/12/2024 | 31/03/2025 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 53.46 | 0 | 0 | 99
2 | MALDAH |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Malda, Uttar Dinajpur, Dakshin Dinajpur districts under Jal Jeevan Mission (JJM) Support Activities | SM/19355 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Uttar Dinajpur District. | Assistant Engineer | Junior Engineer | ORD/000222/2024-2025 | 3197/RS | 31/12/2024 | 31/03/2025 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 53.46 | 0 | 0 | 99
3 | UTTAR DINAJPUR |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Malda, Uttar Dinajpur, Dakshin Dinajpur districts under Jal Jeevan Mission (JJM) Support Activities | SM/19355 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Uttar Dinajpur District. | Assistant Engineer | Junior Engineer | ORD/000222/2024-2025 | 3197/RS | 31/12/2024 | 31/03/2025 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 53.46 | 0 | 0 | 99
4 | DAKSHIN DINAJPUR |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Malda, Uttar Dinajpur, Dakshin Dinajpur districts under Jal Jeevan Mission (JJM) Support Activities | SM/19355 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Malda District. | Assistant Engineer | Junior Engineer | ORD/000334/2024-2025 | 719/RS | 26/03/2025 | 25/04/2025 | CHAKVIGU VIDYASAGAR SOCIAL WELFARE SOCIETY | 20.06 | 0 | 0 | 99
5 | MALDAH |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Malda, Uttar Dinajpur, Dakshin Dinajpur districts under Jal Jeevan Mission (JJM) Support Activities | SM/19355 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Malda District. | Assistant Engineer | Junior Engineer | ORD/000334/2024-2025 | 719/RS | 26/03/2025 | 25/04/2025 | CHAKVIGU VIDYASAGAR SOCIAL WELFARE SOCIETY | 20.06 | 0 | 0 | 99
6 | UTTAR DINAJPUR |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Malda, Uttar Dinajpur, Dakshin Dinajpur districts under Jal Jeevan Mission (JJM) Support Activities | SM/19355 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Malda District. | Assistant Engineer | Junior Engineer | ORD/000334/2024-2025 | 719/RS | 26/03/2025 | 25/04/2025 | CHAKVIGU VIDYASAGAR SOCIAL WELFARE SOCIETY | 20.06 | 0 | 0 | 99
7 | DAKSHIN DINAJPUR |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Malda, Uttar Dinajpur, Dakshin Dinajpur districts under Jal Jeevan Mission (JJM) Support Activities | SM/19355 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Daskhin Dinajpur District. | Assistant Engineer | Junior Engineer | ORD/000291/2024-2025 | 609/RS | 17/03/2025 | 17/03/2026 | CHAKVIGU VIDYASAGAR SOCIAL WELFARE SOCIETY | 141.56 | 0 | 0 | 25
8 | MALDAH |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Malda, Uttar Dinajpur, Dakshin Dinajpur districts under Jal Jeevan Mission (JJM) Support Activities | SM/19355 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Daskhin Dinajpur District. | Assistant Engineer | Junior Engineer | ORD/000291/2024-2025 | 609/RS | 17/03/2025 | 17/03/2026 | CHAKVIGU VIDYASAGAR SOCIAL WELFARE SOCIETY | 141.56 | 0 | 0 | 25
9 | UTTAR DINAJPUR |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Malda, Uttar Dinajpur, Dakshin Dinajpur districts under Jal Jeevan Mission (JJM) Support Activities | SM/19355 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Daskhin Dinajpur District. | Assistant Engineer | Junior Engineer | ORD/000291/2024-2025 | 609/RS | 17/03/2025 | 17/03/2026 | CHAKVIGU VIDYASAGAR SOCIAL WELFARE SOCIETY | 141.56 | 0 | 0 | 25
10 | DAKSHIN DINAJPUR |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Malda, Uttar Dinajpur, Dakshin Dinajpur districts under Jal Jeevan Mission (JJM) Support Activities | SM/19355 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Malda District. | Assistant Engineer | Junior Engineer | ORD/000010/2025-2026 | 970/RS | 05/05/2025 | 05/05/2026 | IMAGIN | 275.32 | 0 | 0 | 25
11 | MALDAH |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Malda, Uttar Dinajpur, Dakshin Dinajpur districts under Jal Jeevan Mission (JJM) Support Activities | SM/19355 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Malda District. | Assistant Engineer | Junior Engineer | ORD/000010/2025-2026 | 970/RS | 05/05/2025 | 05/05/2026 | IMAGIN | 275.32 | 0 | 0 | 25
12 | UTTAR DINAJPUR |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Malda, Uttar Dinajpur, Dakshin Dinajpur districts under Jal Jeevan Mission (JJM) Support Activities | SM/19355 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Malda District. | Assistant Engineer | Junior Engineer | ORD/000010/2025-2026 | 970/RS | 05/05/2025 | 05/05/2026 | IMAGIN | 275.32 | 0 | 0 | 25
13 | DAKSHIN DINAJPUR |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Malda, Uttar Dinajpur, Dakshin Dinajpur districts under Jal Jeevan Mission (JJM) Support Activities | SM/19355 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Uttar Dinajpur District. | Assistant Engineer | Junior Engineer | ORD/000292/2024-2025 | 611/RS | 17/03/2025 | 17/03/2026 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 161.6 | 0 | 0 | 25
14 | MALDAH |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Malda, Uttar Dinajpur, Dakshin Dinajpur districts under Jal Jeevan Mission (JJM) Support Activities | SM/19355 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Uttar Dinajpur District. | Assistant Engineer | Junior Engineer | ORD/000292/2024-2025 | 611/RS | 17/03/2025 | 17/03/2026 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 161.6 | 0 | 0 | 25
15 | UTTAR DINAJPUR |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Malda, Uttar Dinajpur, Dakshin Dinajpur districts under Jal Jeevan Mission (JJM) Support Activities | SM/19355 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Uttar Dinajpur District. | Assistant Engineer | Junior Engineer | ORD/000292/2024-2025 | 611/RS | 17/03/2025 | 17/03/2026 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 161.6 | 0 | 0 | 25
Total | [13 empty] | 1956 | 0 | 0