## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ANANDIPUR Water Supply Scheme | SM/06853 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ANANDIPUR Water Supply Scheme at Englishbazar Block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000166/2020-2021 | 2719/MD | 10/11/2020 | 10/12/2020 | MANAS KUMAR SAHA | 50.07 | 8.75 | 17.47 | 1
2 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ANANDIPUR Water Supply Scheme | SM/06853 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Anandipur Water Supply Scheme under Englishbazar Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000825/2024-2025 | 702/MD | 21/02/2025 | 07/04/2025 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 28.05 | 0 | 0 | 0
3 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ANANDIPUR Water Supply Scheme | SM/06853 | Retrofitting | Augmentation work of Boundary wall, Pump House, Blower Room,Over Head Reservoir and Construction Pathway & Approach Road at Head Work Site of ANANDIPUR Water Supply Scheme of Englishbazar Block under Malda Division, P.H.E.Dte. in the District of Malda | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000111/2025-2026 | 2414/MD | 27/05/2025 | 10/08/2025 | M/S GHOSH CONSTRUCTION | 20.21 | 0 | 0 | 0
Total | [13 empty] | 98.33 | 8.75 | 8.9