## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ARJUNA Water Supply Scheme | SM/06854 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ARJUNA Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer |  | ORD/000164/2020-2021 | 2717/MD | 10/11/2020 | 25/12/2020 | UNIVERSAL ENTERPRIESES | 70.14 | 124.54 | 177.55 | 1
2 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ARJUNA Water Supply Scheme | SM/06854 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000002/2024-2025 | 3915/MD | 06/08/2024 | 06/08/2024 | Resource Division | 1.42 | 0 | 0 | 0
3 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ARJUNA Water Supply Scheme | SM/06854 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000041/2025-2026 | 2818/MD | 11/06/2025 | 11/06/2025 | Resource Division | 8.32 | 0 | 0 | 0
Total | [13 empty] | 79.87 | 124.54 | 155.92