## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BAKHRA Water Supply Scheme | SM/06855 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BAKHRA Water Supply Scheme at Ratua-I Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Tapan Haldar, Junior Engineer | ORD/000568/2020-2021 | 2464/MD | 12/10/2020 | 11/11/2020 | UTTAM KUMAR GHOSH | 57.92 | 7.52 | 12.99 | 0
2 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BAKHRA Water Supply Scheme | SM/06855 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000007/2024-2025 | 3919/MD | 06/08/2024 | 06/08/2024 | Resource Division | 4 | 0 | 0 | 0
3 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BAKHRA Water Supply Scheme | SM/06855 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Bakhra Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Prosanta Mandal, Assistant Engineer | Tapan Haldar, Junior Engineer | ORD/000739/2024-2025 | 58 | 08/01/2025 | 22/02/2025 | M/S N. N. ENTERPRISE | 28.26 | 0 | 0 | 0
4 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BAKHRA Water Supply Scheme | SM/06855 | Retrofitting | Laying of Parallel/ Dedicated Pipeline, Providing Common Manifold & providing Balance FHTC for better Functionality at Bakhra Piped Water Supply Scheme at Ratua-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer | Tapan Haldar, Junior Engineer | ORD/000231/2025-2026 | 4235/MD | 29/08/2025 | 28/10/2025 | M/S N. N. ENTERPRISE | 32.31 | 0 | 0 | 0
Total | [13 empty] | 122.5 | 7.52 | 6.14