## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BARKOL Water Supply Scheme | SM/06856 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BARKOL Water Supply Scheme at Old Malda Block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000167/2020-2021 | 2720/MD | 10/11/2020 | 25/12/2020 | M/S JHA CONSTRUCTION | 71.77 | 51.42 | 71.65 | 1
2 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BARKOL Water Supply Scheme | SM/06856 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ANANDIPUR Water Supply Scheme at Englishbazar Block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000166/2020-2021 | 2719/MD | 10/11/2020 | 10/12/2020 | MANAS KUMAR SAHA | 50.07 | 5.7 | 11.38 | 1
3 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BARKOL Water Supply Scheme | SM/06856 | Retrofitting | Sinking of 200 mm (all through) Big Dia. Tube-Well NO-02 (130 ) M Deep by D.R Rig. Method using P.V.C pipe & Filter including supply of materials at BORKOL Water Supply Scheme of Old Malda Block under Malda Division, PHE Dte, Govt. of West Bengal | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000454/2024-2025 | 4813/MD | 13/09/2024 | 13/10/2024 | M/S DAS CONSTRUCTION | 9.07 | 0 | 0 | 100
4 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BARKOL Water Supply Scheme | SM/06856 | Retrofitting | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Barkol Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000128/2025-2026 | 2485/MD | 28/05/2025 | 27/07/2025 | SURAJIT MONDAL | 9.44 | 0 | 0 | 0
Total | [13 empty] | 140.34 | 57.12 | 40.7