## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAKSHIN BRINDABANBATI Water Supply Scheme | SM/06857 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of DAKSHIN BRINDABANBATI Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ramen Karmakar, Junior Engineer | ORD/000134/2021-2022 | 1525/MD | 05/05/2021 | 04/06/2021 | M/S DAS CONSTRUCTION | 57.24 | 71 | 124.04 | 1
2 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAKSHIN BRINDABANBATI Water Supply Scheme | SM/06857 | Retrofitting | Replacement of 200 mm dia. all through Tube Well at Head Work site (75m Deep) by D.R. Rig. Method using P.V.C. pipe & filter including supply of materials of Dakshin Brindabanbati Piped Water Supply Scheme at Habibpur Dev. Block under Malda Division, PHE Dte. Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000080/2025-2026 | 2274/MD | 21/05/2025 | 20/06/2025 | A. L. ENGINEERING SOLUTION | 6.9 | 0 | 0 | 0
Total | [13 empty] | 64.14 | 71 | 110.69