## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAKSHIN GOURIPUR Water Supply Scheme | SM/06858 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAKSHIN GOURIPUR Water Supply Scheme at Harshchandrapur-II Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000162/2020-2021 | 3046/MD | 11/12/2020 | 10/01/2021 | S DUTTA | 44.04 | 34.78 | 78.98 | 1
2 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAKSHIN GOURIPUR Water Supply Scheme | SM/06858 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DHANJANA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Rajashree Banarjee, Junior Engineer | ORD/000165/2020-2021 | 2718/MD | 10/11/2020 | 10/12/2020 | NIRENDRA NATH KUNDU | 58.72 | 0 | 0 | 1
3 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAKSHIN GOURIPUR Water Supply Scheme | SM/06858 | Retrofitting | Acceptance cum formal work order for Additional laying work of DI & UPVC pipe line of SADLICHAK W/S Scheme at HARISHCHANDRAPUR-II Dev. Block under Malda division.P.H.E.Dte. In the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000655/2021-2022 | 47/CSD | 14/01/2022 | 13/02/2022 | BEE GEE CONSTRUCTION | 4.19 | 0 | 0 | 1
4 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAKSHIN GOURIPUR Water Supply Scheme | SM/06858 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Mouza- Dakshin Gouripur, Village-Baghuya, JL No. 167 GP-Malior-II of DAKSHIN GOURIPUR Piped Water Supply Scheme at Harishchandrapur-II Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000382/2022-2023 | 2736/MD | 18/11/2022 | 18/12/2022 | M/S SABANA CONSTRUCTION | 3.28 | 0 | 0 | 100
Total | [13 empty] | 110.24 | 34.78 | 31.55