## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DHANJANA Water Supply Scheme | SM/06859 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DHANJANA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Rajashree Banarjee, Junior Engineer | ORD/000165/2020-2021 | 2718/MD | 10/11/2020 | 10/12/2020 | NIRENDRA NATH KUNDU | 58.72 | 82.4 | 140.33 | 1
2 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DHANJANA Water Supply Scheme | SM/06859 | Retrofitting | Extension of UPVC pipe line for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Dhanjana Madhaypara command area of Dhanjana Water Supply Scheme at Chanchal-I Block under Malda Division. PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Yusuf Sk, Junior Engineer | ORD/000611/2023-2024 | 4139/MD | 11/10/2023 | 10/11/2023 | M/S BANERJEE CONSTRUCTION | 3.7 | 3.67 | 99.31 | 100
3 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DHANJANA Water Supply Scheme | SM/06859 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of DHANJANA Water Supply Scheme at Chanchal-I Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Yusuf Sk, Junior Engineer | ORD/000726/2023-2024 | 4775/MD | 05/12/2023 | 19/01/2024 | ANUKUL CHANDRA DAS | 7.04 | 6.63 | 94.16 | 100
4 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DHANJANA Water Supply Scheme | SM/06859 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000109/2023-2024 | 39/MD | 04/01/2024 | 04/01/2024 | Resource Division | 1.08 | 0 | 0 | 0
5 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DHANJANA Water Supply Scheme | SM/06859 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000056/2025-2026 | 5597/MD | 30/10/2025 | 30/10/2025 | Resource Division | 7.06 | 0 | 0 | 0
Total | [13 empty] | 77.59 | 92.7 | 119.47