## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of GOURHANDA Water Supply Scheme | SM/06861 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of GOUR HANDA Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Junior Engineer | ORD/000168/2020-2021 | 2721/MD | 10/11/2020 | 25/12/2020 | SUBHAS CHANDRA KESHARI | 74.49 | 22.71 | 30.48 | 0
2 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of GOURHANDA Water Supply Scheme | SM/06861 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000010/2024-2025 | 3922/MD | 06/08/2024 | 06/08/2024 | Resource Division | 8.62 | 0 | 0 | 0
3 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of GOURHANDA Water Supply Scheme | SM/06861 | Retrofitting | Erection of Property board related to Jal Jeevan Mission works of Gourhanda & Jalalpur GP under Chanchal-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000946/2024-2025 | 635/MD | 19/02/2025 | 26/02/2025 | BIDYUT MAHALDAR | 0.9 | 0 | 0 | 0
4 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of GOURHANDA Water Supply Scheme | SM/06861 | Retrofitting | Augmentation work of OHR, Pump House and Boundary Wall of Gourhanda Water Supply Scheme at Chanchal-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Yusuf Sk, Junior Engineer | ORD/000850/2024-2025 | 1043/MD | 18/03/2025 | 01/06/2025 | MATIUR RAHAMAN | 32.5 | 0 | 0 | 0
5 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of GOURHANDA Water Supply Scheme | SM/06861 | Retrofitting | Providing Functional Household Tap Connection (FHTC) and Laying of Distribution Pipeline in connection with Jal Jeevan Mission (JJM) at Gourhanda Water Supply Scheme under Chanchal-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation,Yusuf Sk, Junior Engineer | ORD/000163/2025-2026 | 2876/MD | 17/06/2025 | 16/08/2025 | M/S KUNDU CONSTRUCTION | 60.09 | 0 | 0 | 0
Total | [13 empty] | 176.6 | 22.71 | 12.86