## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of JAGJIBANPUR Water Supply Scheme | SM/06863 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of JAGJIBANPUR Water Supply Scheme at Habibpu Block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ramen Karmakar, Junior Engineer | ORD/000554/2020-2021 | 2447/MD | 12/10/2020 | 09/02/2021 | MANIK CHOUDHURY | 12 | 12 | 100.01 | 1
2 | MALDAH |  | Central Drilling | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of JAGJIBANPUR Water Supply Scheme | SM/06863 | Retrofitting | SUPPLY & DELIVERY OF CONSUMBLES WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT JAGJIBANPUR, HABIBPUR BLOCK, MALDA DISTRICT UNDER CDD, PHE DTE. |  |  | ORD/000066/2022-2023 | 302/CMSD-I (D) | 08/07/2022 | 23/07/2022 | CHANDA ENTERPRISE | 4.66 | 4.48 | 96.23 | 0
3 | MALDAH |  | Central Drilling | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of JAGJIBANPUR Water Supply Scheme | SM/06863 | Retrofitting | SUPPLY & DELIVERY OF CONSUMBLES WITH OTHER WORKS AT SITEFOR CONSTRUCTION OF TUBE WELL AT JAGJIBANPUR, HABIBPUR BLOCK, MALDA DISTRICT UNDER CDD, PHE DTE. |  |  | ORD/000242/2022-2023 | 346/CMSD-I | 25/07/2022 | 09/08/2022 | CHANDA ENTERPRISE | 4.66 | 3.09 | 66.28 | 0
4 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of JAGJIBANPUR Water Supply Scheme | SM/06863 | Retrofitting | Acceptance cum formal work order for Emergent repairing and laying of uPVC pipeline and Construction of different dia sluice valve chambers with other allied work to proper functioning of FHTC work within the command area of JAGJIBANPUR Water Supply scheme under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ramen Karmakar, Junior Engineer | ORD/000400/2022-2023 | 2960/MD | 07/12/2022 | 06/01/2023 | M/S AYUSH BUILDERS | 3.64 | 3.64 | 100 | 1
5 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of JAGJIBANPUR Water Supply Scheme | SM/06863 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of KADIRPUR Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ramen Karmakar, Junior Engineer | ORD/000029/2020-2021 | 1964/MD | 31/08/2020 | 30/09/2020 | M/S KUNDU CONSTRUCTION | 39.43 | 0 | 0 | 1
6 | MALDAH |  | Central Drilling | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of JAGJIBANPUR Water Supply Scheme | SM/06863 | Retrofitting | PROVIDING TUBE WELL MATERIALS TO IS : 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT JAGJIBANPUR, HABIBPUR BLOCK, MALDA DISTRICT UNDER CDD, PHE DTE. |  |  | ORD/000065/2022-2023 | 301/CMSD-I (D) | 08/07/2022 | 23/07/2022 | CHANDA ENTERPRISE | 4.69 | 4.43 | 94.41 | 50
7 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of JAGJIBANPUR Water Supply Scheme | SM/06863 | Retrofitting | Acceptance cum formal work order for Providing FHTC (Functional House hold Tap Connection) of Ranghat Piped Water Supply Scheme at Chanchal-II Dev. Block, under Malda Division, P.H.E. Dte. in the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer |  | ORD/000056/2023-2024 | 1991/MD | 17/05/2023 | 01/06/2023 | M/S FOUR STAR CONSTRUCTION | 9.06 | 9.06 | 99.92 | 100
Total | [13 empty] | 78.14 | 36.7 | 46.96