## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MAHANANDAPUR Water Supply Scheme | SM/06866 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MAHANANDAPUR Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Yusuf Sk, Junior Engineer | ORD/000161/2020-2021 | 2714/MD | 10/11/2020 | 10/12/2020 | NEOGI ENTERPRISE | 66.16 | 81.97 | 123.9 | 100
2 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MAHANANDAPUR Water Supply Scheme | SM/06866 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Dakshinpaka command area of MAHANANDAPUR Water Supply Scheme at Chanchal-I Block under Malda Division PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Yusuf Sk, Junior Engineer | ORD/000363/2023-2024 | 3052/MD | 09/08/2023 | 08/09/2023 | M/S AYUSH BUILDERS | 7.85 | 7.85 | 99.92 | 100
3 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MAHANANDAPUR Water Supply Scheme | SM/06866 | Retrofitting | Extension of UPVC pipe line for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Dakshinpaka command area of MAHANANDAPUR Water Supply Scheme at Chanchal-I Block under Malda Division PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Yusuf Sk, Junior Engineer | ORD/000365/2023-2024 | 3054MD | 09/08/2023 | 08/09/2023 | M/S SRINJOYEE | 4.65 | 4.63 | 99.67 | 100
4 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MAHANANDAPUR Water Supply Scheme | SM/06866 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000106/2023-2024 | 36/MD | 04/01/2024 | 04/01/2024 | Resource Division | 1.58 | 0 | 0 | 0
5 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MAHANANDAPUR Water Supply Scheme | SM/06866 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000034/2025-2026 | 2814/MD | 11/06/2025 | 11/06/2025 | Resource Division | 7.59 | 0 | 0 | 0
Total | [13 empty] | 87.83 | 94.45 | 107.54