## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MIANAGAR Water Supply Scheme | SM/06867 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MIANAGAR Water Supply Scheme under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Sumit Kumar Ganguly, Junior Engineer | ORD/000551/2020-2021 | 2439/MD | 12/10/2020 | 09/02/2021 | M/S AMIT KUMAR GUPTA | 20 | 0 | 0 | 0
2 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MIANAGAR Water Supply Scheme | SM/06867 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of MAHESHPUR Water Supply Scheme at Ratua-I Block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Sumit Kumar Ganguly, Junior Engineer | ORD/000132/2020-2021 | 2442/MD | 12/10/2020 | 11/11/2020 | M/S PRATIMA CONSTRUCTION | 14.91 | 0 | 0 | 1
3 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MIANAGAR Water Supply Scheme | SM/06867 | Retrofitting | Acceptance cum formal work order for Laying of UPVC pipe line in place of damaged portion due to the construction of PMGSY road at KANDARAN ZONE-I Water Supply Scheme under Malda Division PHE. Dte in The District of Malda. (Part-III) | Mr. Arnab Giri, Assistant Engineer | Sumit Kumar Ganguly, Junior Engineer | ORD/000576/2021-2022 | 36/CSD | 07/01/2022 | 27/01/2022 | M/S FOUR STAR CONSTRUCTION | 4.84 | 0 | 0 | 1
4 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MIANAGAR Water Supply Scheme | SM/06867 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Uttar Chandipur Zone-IV Water Supply Scheme at Manikchak Dev. Block under Malda Division, PHE Dte. in the district of Malda. (Phase-III) | Mr. Arnab Giri, Assistant Engineer,Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000124/2022-2023 | 1642/MD | 19/07/2022 | 18/08/2022 | M/S AMIT KUMAR GUPTA | 16.26 | 0 | 0 | 1
5 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MIANAGAR Water Supply Scheme | SM/06867 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MIANAGAR Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000072/2020-2021 | 2439/MD | 12/10/2020 | 26/11/2020 | M/S AMIT KUMAR GUPTA | 72.29 | 28.64 | 39.61 | 66
6 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MIANAGAR Water Supply Scheme | SM/06867 | Retrofitting | Design , Supplying, Fabrication, Erection, & Commissioning including 3 (three) months Trial Run of 25 m³/hr. capacity Pressure type Iron Elimination Plant with Construction of Blower room & backwash water disposal at Mianagar Water Supply Scheme of Habibpur Dev. Block under Malda Division P.H.E Dte in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000161/2025-2026 | 2760/MD | 09/06/2025 | 01/04/2026 | UTTAM KUMAR GHOSH | 15.57 | 0 | 0 | 0
Total | [13 empty] | 143.87 | 28.64 | 19.91