## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MIHAGHAT Water Supply Scheme | SM/06868 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MIAGHAT Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer |  | ORD/000213/2020-2021 | 3001/MD | 10/12/2020 | 09/01/2021 | A. K. CONSTRUCTION | 49.81 | 44.5 | 89.34 | 1
2 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MIHAGHAT Water Supply Scheme | SM/06868 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000005/2024-2025 | 3917/MD | 06/08/2024 | 06/08/2024 | Resource Division | 3.76 | 0 | 0 | 0
3 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MIHAGHAT Water Supply Scheme | SM/06868 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000071/2025-2026 | 5535/MD | 29/10/2025 | 29/10/2025 | Resource Division | 3.15 | 0 | 0 | 0
Total | [13 empty] | 56.72 | 44.5 | 78.45