## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PAHARPUR Water Supply Scheme | SM/06869 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PAHARPUR Water Supply Scheme at Ratua-II Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer |  | ORD/000077/2020-2021 | 2465/MD | 12/10/2020 | 26/11/2020 | UTTAM KUMAR GHOSH | 70.72 | 96.83 | 136.92 | 1
2 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PAHARPUR Water Supply Scheme | SM/06869 | Retrofitting | Acceptance cum formal work order for Additional laying work of DI & UPVC pipe line of SADLICHAK W/S Scheme at HARISHCHANDRAPUR-II Dev. Block under Malda division.P.H.E.Dte. In the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000655/2021-2022 | 47/CSD | 14/01/2022 | 13/02/2022 | BEE GEE CONSTRUCTION | 4.19 | 0 | 0 | 1
Total | [13 empty] | 74.92 | 96.83 | 129.25