## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PANNAPUR Water Supply Scheme | SM/06870 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PANNAPUR Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000159/2020-2021 | 2712/MD | 10/11/2020 | 25/12/2020 | NIRENDRA NATH KUNDU | 77.09 | 70.11 | 90.95 | 0
2 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PANNAPUR Water Supply Scheme | SM/06870 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Village- Purba Binodpur, JL. No. 44, G.P.-Pandua of PURBA BINODPUR Water Supply Scheme at Gazole Block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000139/2020-2021 | 2449/MD | 12/10/2020 | 11/11/2020 | A. B. CONSTRUCTION | 11.75 | 21.72 | 184.78 | 0
3 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PANNAPUR Water Supply Scheme | SM/06870 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000006/2025-2026 | 2517/MD | 29/05/2025 | 29/05/2025 | Resource Division | 10.69 | 0 | 0 | 0
Total | [13 empty] | 99.53 | 91.83 | 92.26