## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAILPUR Water Supply Scheme | SM/06871 | Retrofitting | Stationary Bill under Malda Division, PHE Dte. n the district of Malda | Mr. Arnab Giri, Assistant Engineer | Bikash Balo, Junior Engineer,Mukaddar Parvage, Junior Engineer | ORD/000259/2022-2023 | 1969/MD | 26/08/2022 | 27/08/2022 | MALDA DISTRICT SERVICE CUM-MARKETING INDS. CO-OP UNION LTD. | 1.26 | 1.26 | 100 | 1
2 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAILPUR Water Supply Scheme | SM/06871 | Retrofitting | Acceptance cum formal work order for Detail route survey and design & drawing of distribution network, for providing FHTC in Uttar Chandipur Zone-I Water Supply scheme of Manikchak Block in the District of Malda under Malda Division, P.H.E.Dte. | Mr. Arnab Giri, Assistant Engineer | Bikash Balo, Junior Engineer,Mukaddar Parvage, Junior Engineer | ORD/000429/2022-2023 | 478/MSD | 09/12/2022 | 24/12/2022 | FUTURE | 0.84 | 0 | 0 | 1
3 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAILPUR Water Supply Scheme | SM/06871 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAILPUR Water Supply Scheme at Englishbazar Block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Bikash Balo, Junior Engineer,Mukaddar Parvage, Junior Engineer | ORD/000136/2020-2021 | 2446/MD | 12/10/2020 | 11/11/2020 | KRISHNENDU DUTTA | 43.4 | 4.78 | 11.02 | 1
4 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAILPUR Water Supply Scheme | SM/06871 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Chatra, JL. No. 29, G.P.-Aktail of SANKAIL Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000143/2020-2021 | 2453/MD | 12/10/2020 | 11/11/2020 | BENGAL ENGINEERING COMPANY | 6.92 | 5.67 | 81.95 | 0
5 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAILPUR Water Supply Scheme | SM/06871 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Village- Bodrail, JL. No. 167, G.P.-Kanturka of SANKAIL Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000102/2020-2021 | 2298/MD | 30/09/2020 | 30/10/2020 | BAKUL CHANDRA HALDAR | 2.82 | 2.51 | 89.17 | 0
6 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAILPUR Water Supply Scheme | SM/06871 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Sailpur Water Supply Scheme at Englishbazar Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Amit Biswas, Assistant Engineer,Mr. Arnab Giri, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000453/2023-2024 | 3370/MD | 29/08/2023 | 13/10/2023 | BENGAL ENGINEERING COMPANY | 11.91 | 9.68 | 81.2 | 95
Total | [13 empty] | 67.16 | 23.91 | 35.6