## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of TALBANGURA Water Supply Scheme | SM/06872 | Retrofitting | Testing of HDPE pipe 20 mm as per IS 4984:2016 reg. |  |  | VCH/000108/2021-2022 | 44 | 07/05/2021 | 07/05/2021 | CIPET EXTN CENTRE | 0.22 | 0 | 0 | 0
2 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of TALBANGURA Water Supply Scheme | SM/06872 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of TALBANGURA Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000558/2020-2021 | 2436/MD | 12/10/2020 | 09/02/2021 | M/S TRILOCHAN CONSTRUCTION CO | 12 | 13.18 | 109.87 | 1
3 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of TALBANGURA Water Supply Scheme | SM/06872 | Retrofitting | Formal work order for Providing house connection under RANGHAT Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer |  | ORD/000015/2020-2021 | 2038/MD | 10/09/2020 | 08/01/2021 | PROJECT INDIA | 94.64 | 8.18 | 8.65 | 100
4 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of TALBANGURA Water Supply Scheme | SM/06872 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of KHANPUR HULASPUR Water Supply Scheme at Chanchal-I Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Yusuf Sk, Junior Engineer | ORD/000722/2021-2022 | 48/1/MD | 13/01/2022 | 12/02/2022 | BIDYUT MAHALDAR | 0.39 | 0.39 | 100 | 100
5 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of TALBANGURA Water Supply Scheme | SM/06872 | Retrofitting | Sinking of 01 (One) Nos. 250mm. Dia. x 200 mm. Big dia. Tube Well 131 Mtr. deep by Direct Rotary method using UPVC pipe & Strainer in connection with 2nd Tube Well Site at Talbangura Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda. |  |  | BILL/00673/2024-2025 | 464/DW | 25/09/2024 | 25/09/2024 | A. L. ENGINEERING SOLUTION | 3.98 | 0 | 0 | 0
6 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of TALBANGURA Water Supply Scheme | SM/06872 | Retrofitting | Laying of Parallel/Dedicated Pipeline improvement of functionality, Providing Balance FHTC and Construction of Boundary Wall of TALBANGURA Water Supply Scheme of Harishchandrapur-II Block under Malda Division P.H.E Dte in the District of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000969/2025-2026 | 696/MD | 13/02/2026 | 29/04/2026 | MANIK CHOUDHURY | 27.19 | 0 | 0 | 0
Total | [13 empty] | 138.42 | 21.76 | 15.72