## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Supply, installation & delivery of water quality testing equipment, chemicals, consumables & glassware etc. for continuing NABL accreditation (Chemical Testing of potable water) including routine water testing of 8 nos Water Testing Laboratories along wit | SM/07971 | Support-WQMSP | Acceptance cum formal work order for Engagement of Resource person to implement water testing laboratory quality management system as per ISO/IEC: 17025 including supply of required equipments, laboratory glassware, reagents, standard reference materials traceable to NIST, measuring instruments & calibration of measuring instruments as per ISO 17025: 2017 protocol for Malda District Water Testing Laboratory under the Executive Engineer, Malda Division, PHE Dte, Government of West Bengal. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000141/2021-2022 | 1610/MD | 19/05/2021 | 03/06/2021 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 16.04 | 9.59 | 59.77 | 100
2 | MALDAH |  | Malda Division | Supply, installation & delivery of water quality testing equipment, chemicals, consumables & glassware etc. for continuing NABL accreditation (Chemical Testing of potable water) including routine water testing of 8 nos Water Testing Laboratories along wit | SM/07971 | Support-WQMSP | Supply of additionally required chemicals for Gazole Sub- District Laboratory |  |  | BILL/00545/2022-2023 |  | 16/03/2023 | 16/03/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.09 | 0 | 0 | 0
3 | MALDAH |  | Malda Division | Supply, installation & delivery of water quality testing equipment, chemicals, consumables & glassware etc. for continuing NABL accreditation (Chemical Testing of potable water) including routine water testing of 8 nos Water Testing Laboratories along wit | SM/07971 | Support-WQMSP | Supply of additionally required chemicals for Gazole Sub- District Laboratory |  |  | BILL/00547/2022-2023 |  | 16/03/2023 | 16/03/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.09 | 0 | 0 | 0
4 | MALDAH |  | Malda Division | Supply, installation & delivery of water quality testing equipment, chemicals, consumables & glassware etc. for continuing NABL accreditation (Chemical Testing of potable water) including routine water testing of 8 nos Water Testing Laboratories along wit | SM/07971 | Support-WQMSP | Supply of additionally required chemicals for Gazole Sub- District Laboratory |  |  | BILL/00546/2022-2023 |  | 16/03/2023 | 16/03/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.09 | 0 | 0 | 0
5 | MALDAH |  | Malda Division | Supply, installation & delivery of water quality testing equipment, chemicals, consumables & glassware etc. for continuing NABL accreditation (Chemical Testing of potable water) including routine water testing of 8 nos Water Testing Laboratories along wit | SM/07971 | Support-WQMSP | Supply of additionally required chemicals for Gazole Sub- District Laboratory |  |  | BILL/00548/2022-2023 |  | 16/03/2023 | 16/03/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.1 | 0 | 0 | 0
6 | MALDAH |  | Malda Division | Supply, installation & delivery of water quality testing equipment, chemicals, consumables & glassware etc. for continuing NABL accreditation (Chemical Testing of potable water) including routine water testing of 8 nos Water Testing Laboratories along wit | SM/07971 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Sahapur Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Government of West Bengal. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000670/2025-2026 | 4229/MD | 28/08/2025 | 27/09/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
7 | MALDAH |  | Malda Division | Supply, installation & delivery of water quality testing equipment, chemicals, consumables & glassware etc. for continuing NABL accreditation (Chemical Testing of potable water) including routine water testing of 8 nos Water Testing Laboratories along wit | SM/07971 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement forSamsi Sub-District Laboratory (erstwhile SANSKRITY -O- SAMAJ UNNAYAN PARISAD SUB-DISTRICT LABORATORY) under Malda Division, Public Health Engineering Directorate, Government of West Bengal | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000669/2025-2026 | 4228/MD | 28/08/2025 | 27/09/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
8 | MALDAH |  | Malda Division | Supply, installation & delivery of water quality testing equipment, chemicals, consumables & glassware etc. for continuing NABL accreditation (Chemical Testing of potable water) including routine water testing of 8 nos Water Testing Laboratories along wit | SM/07971 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Manikchak Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Government of West Bengal. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000668/2025-2026 | 4227/MD | 28/08/2025 | 27/09/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
Total | [13 empty] | 19.11 | 9.59 | 50.18