## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Village-Dubol, JL. No. 93, G.P.- Daulatpur of DAULATPUR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000118/2020-2021 | 2314/MD | 30/09/2020 | 31/10/2020 | PRITAM ENTERPRISE | 3.31 | 3.02 | 91.41 | 0
2 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Birasthali, JL. No. 137, G.P.-Chanchal of DAKSHIN SAHAR Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Yusuf Sk, Junior Engineer | ORD/000148/2020-2021 | 2458/MD | 12/10/2020 | 11/11/2020 | M/S. TEWARI CONSTRUCTION | 28.57 | 5.25 | 18.37 | 66
3 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Village-Sadhail, JL. No. 116, G.P.- Muchia of NEMUA Water Supply Scheme at Old Malda Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000116/2020-2021 | 2312/MD | 30/09/2020 | 31/10/2020 | DEVI ENTERPRISE | 2.07 | 2.07 | 100 | 1
4 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Lalpur Bodra, JL. No. 31, G.P.-Aktail of SANKAIL Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000550/2020-2021 | 3102/MD | 15/12/2020 | 14/01/2021 | M/S SINHA ENTERPRISE | 0 | 5.61 | 28043550 | 1
5 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Sanjib, JL. No. 136, G.P.-Chanchal of DAKSHIN SAHAR Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000147/2020-2021 | 2457/MD | 12/10/2020 | 11/11/2020 | EUREKA UNEMPLOYED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 16.51 | 15.08 | 91.33 | 0
6 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Daksin Sahar, JL. No. 133, G.P.-Chanchal of DAKSHIN SAHAR Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000146/2020-2021 | 2456/MD | 12/10/2020 | 11/11/2020 | M/S BANERJEE CONSTRUCTION | 19.18 | 13.41 | 69.9 | 0
7 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Bagunja, JL. No. 38, G.P.- Bhagabanpur of ARBARA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Yusuf Sk, Junior Engineer | ORD/000150/2020-2021 | 2460/MD | 12/10/2020 | 11/11/2020 | M/S N. N. ENTERPRISE | 5.71 | 9.49 | 166.24 | 0
8 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Khosalpur, JL. No. 56, G.P.- Bhagabanpur of ARBARA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Yusuf Sk, Junior Engineer | ORD/000153/2020-2021 | 2463/MD | 12/10/2020 | 11/11/2020 | IDEAL CONSTRUCTION | 9.01 | 11.83 | 131.31 | 0
9 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Village-Basantapur, JL. No. 82, G.P.- Baidyapur of BHABUK Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000119/2020-2021 | 2315/MD | 30/09/2020 | 31/10/2020 | M/S RADHA KRISHNA ENTERPRISE | 2.64 | 2.52 | 95.19 | 0
10 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Sankail, JL. No. 166, G.P.-Aktail of SANKAIL Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000142/2020-2021 | 2452/MD | 12/10/2020 | 11/11/2020 | M/S BABLU ENTERPRISE | 20.5 | 30.73 | 149.92 | 0
11 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Village- Chandipur, JL. No. 40, G.P.-Bhagabanpur of KENDUA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Yusuf Sk, Junior Engineer | ORD/000105/2020-2021 | 2301/MD | 30/09/2020 | 31/10/2020 | BIDYUT MAHALDAR | 4.45 | 7.63 | 171.51 | 0
12 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Village- Mahupaul, JL. No. 100, G.P.-Pakuahat of BASARA Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000110/2020-2021 | 2306/MD | 30/09/2020 | 31/10/2020 | RABIUL ISLAM | 2.82 | 3.43 | 121.71 | 0
13 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Khadiarpur, JL. No. 21, G.P.- Bhagabanpur of ARBARA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Yusuf Sk, Junior Engineer | ORD/000152/2020-2021 | 2462/MD | 12/10/2020 | 11/11/2020 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 16.85 | 23.43 | 139.06 | 0
14 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Haripur, JL. No. 20, G.P.- Bhagabanpur of ARBARA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Yusuf Sk, Junior Engineer | ORD/000151/2020-2021 | 2461/MD | 12/10/2020 | 11/11/2020 | M/S STAR INDIA CONSTRUTION | 17.3 | 22.14 | 128.02 | 0
15 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Arbara, JL. No. 57, G.P.- Bhagabanpur of ARBARA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Yusuf Sk, Junior Engineer | ORD/000149/2020-2021 | 2459/MD | 12/10/2020 | 11/11/2020 | TARUN KUMAR DEY | 31.69 | 23.11 | 72.92 | 0
16 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Village- Barijpur, JL. No. 43, G.P.-Pandua of PURBA BINODPUR Water Supply Scheme at Gazole Block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000138/2020-2021 | 2448/MD | 12/10/2020 | 11/11/2020 | PARIJAT RAY | 41.39 | 56.13 | 135.61 | 0
17 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Formal work order for Providing Functional Household Tap Connection under MOBARAKPUR Piped Water Supply Scheme at Old Malda Block in the district of Malda under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000358/2020-2021 | 591/MD | 18/02/2021 | 19/04/2021 | NIRENDRA NATH KUNDU | 125 | 30.6 | 24.48 | 0
18 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Basudebpur, JL. No. 150, G.P.- Sadlichak of UTTAR KUMEDPUR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000299/2020-2021 | 273/MD | 28/01/2021 | 27/02/2021 | MD WARESH ALI | 14.72 | 14.66 | 99.61 | 1
19 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Ashrafpur, JL. No. 132, G.P.- Jogdala of PARAMESWARPUR Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000317/2020-2021 | 297/MD | 28/01/2021 | 27/02/2021 | M/S BANERJEE CONSTRUCTION | 13.91 | 0 | 0 | 0
20 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Chhatia, JL. No. 133, G.P.- Jogdala of PARAMESWARPUR Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000318/2020-2021 | 298/MD | 28/01/2021 | 27/02/2021 | M/S BANERJEE CONSTRUCTION | 17.51 | 0 | 0 | 0
21 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Bhabanipur, JL. No. 85, G.P.- Jajail of BHABUK Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000326/2020-2021 | 306/MD | 28/01/2021 | 27/02/2021 | RANJIT ADHIKARY | 8.8 | 0 | 0 | 0
22 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Bhairabpur, JL. No. 86, G.P.- Jajail of BHABUK Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000328/2020-2021 | 308/MD | 28/01/2021 | 27/02/2021 | CHARU CONSTRUCTION | 5.85 | 0 | 0 | 0
23 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Konar, JL. No. 73, G.P.- Bhingole of KONAR Water Supply Scheme at Harishchandrapur-I Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000341/2020-2021 | 450/MD | 08/02/2021 | 10/03/2021 | M/S. TEWARI CONSTRUCTION | 25.97 | 20.69 | 79.66 | 0
24 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Kanua Bhabanipur, JL. No. 78, G.P.- Bhingole of KONAR Water Supply Scheme at Harishchandrapur-I Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000309/2020-2021 | 289/MD | 28/01/2021 | 27/02/2021 | JOYDEB SENGUPTA | 6.64 | 0 | 0 | 0
25 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Bujurkhali, JL. No. 110, G.P.-Pakuahat of BASARA Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer,Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer,Ziaur Rahaman, Junior Engineer | ORD/000314/2020-2021 | 294/MD | 28/01/2021 | 01/01/2026 | GOBINDA ENTERPRISE | 14.53 | 0 | 0 | 0
26 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Teliapara, JL. No. 74, G.P.-Chandpur of PARAMESWARPUR Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000316/2020-2021 | 296/MD | 28/01/2021 | 27/02/2021 | GOALPAR CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 5.53 | 0 | 0 | 0
27 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Malipakar, JL. No. 91, G.P.-Daulatpur of MALIPAKAR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000361/2020-2021 | 568/MD | 15/02/2021 | 01/04/2021 | NEOGI ENTERPRISE | 78.3 | 71 | 90.69 | 46
28 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Uttar Kumedpur, JL. No. 142, G.P.-Sadlichak of UTTAR KUMEDPUR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000431/2021-2022 | 3004/MD | 07/10/2021 | 06/11/2021 | FUTURE | 49.95 | 45.14 | 90.39 | 1
29 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Kankot, JL. No. 50, G.P.-Chandmoni-I of KANKOT Water Supply Scheme at Ratua-I Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000353/2020-2021 | 557/MD | 12/02/2021 | 14/03/2021 | RAY CONSTRUCTION CO. | 57.6 | 29.11 | 50.55 | 1
30 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Arazi Deharul, JL. No. 21, G.P.-Bahirgachhi-II of BAHIRGACHHI Water Supply Scheme at Gazole Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000355/2020-2021 | 555/MD | 12/02/2021 | 14/03/2021 | BEE GEE CONSTRUCTION | 52.81 | 47.96 | 90.82 | 1
31 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Latasi, JL. No. 89, G.P.- Daulatpur of MALIPAKAR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000298/2020-2021 | 272/MD | 28/01/2021 | 27/02/2021 | M/S SABANA CONSTRUCTION | 35.86 | 34.96 | 97.48 | 1
32 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Naikanda, JL. No. 39, G.P.-Kharba of KENDUA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000302/2020-2021 | 282/MD | 28/01/2021 | 27/02/2021 | FAIZUL HAQUE BISWAS | 16.18 | 14.76 | 91.28 | 1
33 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Gorakhpur, JL. No. 76, G.P.-Bhakri of RAMPUR Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000340/2020-2021 | 449/MD | 08/02/2021 | 10/03/2021 | TARUN KUMAR DEY | 27.04 | 23.08 | 85.33 | 1
34 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Khatil, JL. No. 42, G.P.-Bamangola of KHATIL Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000343/2020-2021 | 452/MD | 08/02/2021 | 10/03/2021 | GOBINDA ENTERPRISE | 22.15 | 35.24 | 159.13 | 1
35 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Daulatpur, JL. No. 92, G.P.-Daulatpur of DAULATPUR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000360/2020-2021 | 569/MD | 15/02/2021 | 01/04/2021 | M/S TRILOCHAN CONSTRUCTION CO | 84.94 | 83.13 | 97.87 | 1
36 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Sahabajpur, JL. No. 55, G.P.-Kharba of KENDUA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000301/2020-2021 | 281/MD | 28/01/2021 | 27/02/2021 | M/S. TEWARI CONSTRUCTION | 20.81 | 31.12 | 149.54 | 1
37 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Bibijhuti, JL. No. 58, G.P.-Kharba of KENDUA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000303/2020-2021 | 283/MD | 28/01/2021 | 27/02/2021 | ANUKUL CHANDRA DAS | 9.41 | 15.9 | 168.93 | 1
38 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Uttar Bhabanipur, JL. No. 73, G.P.-Bhakri of RAMPUR Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000305/2020-2021 | 285/MD | 28/01/2021 | 27/02/2021 | M/S BANERJEE CONSTRUCTION | 13.56 | 0.58 | 4.3 | 1
39 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Rampur, JL. No. 74, G.P.-Bhakri of RAMPUR Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000306/2020-2021 | 286/MD | 28/01/2021 | 27/02/2021 | S. N. CONSTRUCTION | 16.86 | 15.79 | 93.67 | 1
40 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Lakshmanpur, JL. No. 74, G.P.- Bhingole of KONAR Water Supply Scheme at Harishchandrapur-I Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000310/2020-2021 | 290/MD | 28/01/2021 | 27/02/2021 | M/S SABANA CONSTRUCTION | 27.25 | 25.76 | 94.56 | 1
41 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Alampur, JL. No. 107, G.P.-Pakuahat of BASARA Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000311/2020-2021 | 291/MD | 28/01/2021 | 27/02/2021 | RANJIT ADHIKARY | 5.68 | 4.84 | 85.23 | 1
42 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Harinandanbati, JL. No. 109, G.P.-Pakuahat of BASARA Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000313/2020-2021 | 293/MD | 28/01/2021 | 27/02/2021 | S. R. CONSTRUCTION | 15.52 | 13.97 | 90.05 | 1
43 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Elam, JL. No. 75, G.P.-Bhakri of RAMPUR Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000307/2020-2021 | 287/MD | 28/01/2021 | 27/02/2021 | ACHARYYA CONSTRUCTION | 12.36 | 0 | 0 | 1
44 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Jagdala, JL. No. 77, G.P.- Jogdala of PARAMESWARPUR Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000320/2020-2021 | 300/MD | 28/01/2021 | 27/02/2021 | PABITRA MONDAL | 9.57 | 17.56 | 183.56 | 1
45 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Parameswarpur, JL. No. 81, G.P.- Jogdala of PARAMESWARPUR Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000321/2020-2021 | 301/MD | 28/01/2021 | 27/02/2021 | A. K. SIKDAR | 7.04 | 5.7 | 80.99 | 1
46 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Bhabanipur, JL. No. 75, G.P.-Chandpur of PARAMESWARPUR Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer,Mr. Sumit Kumar Ghosh, Assistant Engineer | Junior Engineer,Mr. Tilok Roy, Junior Engineer | ORD/000322/2020-2021 | 302/MD | 28/01/2021 | 01/06/2022 | MARSS INTERNATIONAL | 7.25 | 0 | 0 | 100
47 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Bhadreshwar, JL. No. 78, G.P.-Chandpur of PARAMESWARPUR Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000323/2020-2021 | 303/MD | 28/01/2021 | 27/02/2021 | ACHARYYA CONSTRUCTION | 13.25 | 10.79 | 81.39 | 1
48 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Dihatti, JL. No. 79, G.P.-Chandpur of PARAMESWARPUR Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000324/2020-2021 | 304/MD | 28/01/2021 | 27/02/2021 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 5.93 | 2.9 | 48.93 | 0
49 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Jot Haricharan, JL. No. 43, G.P.-Bamangola of KHATIL Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000330/2020-2021 | 310/MD | 28/01/2021 | 27/02/2021 | JOY ENTERPRISE | 6.77 | 5.81 | 85.75 | 1
50 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Dharmma Danga, JL. No. 44, G.P.-Bamangola of KHATIL Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000331/2020-2021 | 311/MD | 28/01/2021 | 27/02/2021 | MANAS KUMAR SAHA | 18.67 | 16.39 | 87.76 | 1
51 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Bansdol, JL. No. 94, G.P.- Daulatpur of DAULATPUR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000292/2020-2021 | 266/MD | 28/01/2021 | 27/02/2021 | M/S. TEWARI CONSTRUCTION | 21.96 | 21.41 | 97.47 | 1
52 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Adampur, JL. No. 121, G.P.- Muchia of NEMUA Water Supply Scheme at Old Malda Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000294/2020-2021 | 268/MD | 28/01/2021 | 27/02/2021 | BEE GEE CONSTRUCTION | 29.13 | 53.15 | 182.46 | 1
53 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Memua, JL. No. 122, G.P.- Muchia of NEMUA Water Supply Scheme at Old Malda Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000295/2020-2021 | 269/MD | 28/01/2021 | 27/02/2021 | GOBINDA ENTERPRISE | 23.19 | 45.81 | 197.53 | 1
54 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Raykhandighi, JL. No. 23, G.P.-Bahirgachhi-I of BAHIRGACHHI Water Supply Scheme at Gazole Block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer,Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer,Ziaur Rahaman, Junior Engineer | ORD/000296/2020-2021 | 270/MD | 28/01/2021 | 09/11/2024 | M/S KUNDU CONSTRUCTION | 25.44 | 0 | 0 | 100
55 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Gaushpur, JL. No. 90, G.P.- Daulatpur of MALIPAKAR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000297/2020-2021 | 271/MD | 28/01/2021 | 27/02/2021 | GOBINDA ENTERPRISE | 14.36 | 25.01 | 174.22 | 1
56 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Manoharpur, JL. No. 117, G.P.-Sultannagar of GANNADIA Water Supply Scheme at Harischandrapur - II Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000338/2020-2021 | 447/MD | 08/02/2021 | 10/03/2021 | MANIK CHOUDHURY | 37.13 | 4.9 | 13.21 | 0
57 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Agra, JL. No. 84, G.P.- Jajail of BHABUK Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000342/2020-2021 | 451/MD | 08/02/2021 | 10/03/2021 | M/S. TEWARI CONSTRUCTION | 25.53 | 15.46 | 60.55 | 1
58 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Muchia, JL. No. 124, G.P.-Muchia of MOBARAKPUR Water Supply Scheme at Old Malda Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000344/2020-2021 | 509/MD | 09/02/2021 | 11/03/2021 | M/S KUNDU CONSTRUCTION | 46.63 | 93.25 | 199.99 | 1
59 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Collection of household tap connection details through baseline household mobile's App (Jal Swapna) under commend area of Rajarampur, Mekpur, Purba Binodpur, Mianagar & Basora Piped Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000551/2021-2022 | 515/MSD | 31/12/2021 | 01/01/2022 | DHRITIPALI | 0.96 | 0.96 | 100 | 1
60 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Laying and extension of uPVC Pipe Line of different diameter at Dihotti & Bhadreswar Mouza of PARAMESHWARPUR Water Supply Scheme at BAMONGOLA Block under Malda Division P.H.E. Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000659/2021-2022 | 3413/MD | 02/12/2021 | 03/12/2021 | ACHARYYA CONSTRUCTION | 1.25 | 2.09 | 167.29 | 1
61 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Bahirgachhi, JL. No. 24, G.P.-Bahirgachhi-I of BAHIRGACHHI Water Supply Scheme at Gazole Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000354/2020-2021 | 556/MD | 12/02/2021 | 29/03/2021 | UTTAM KUMAR GHOSH | 71.29 | 12.54 | 17.6 | 0
62 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Kendua, JL. No. 54, G.P.-Kharba of KENDUA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000339/2020-2021 | 448/MD | 08/02/2021 | 10/03/2021 | FAIZUL HAQUE BISWAS | 25.78 | 24.34 | 94.43 | 1
63 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Bampal Charkhi, JL. No. 51, G.P.- Chandmoni-I of KANKOT Water Supply Scheme at Ratua-I Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000293/2020-2021 | 267/MD | 28/01/2021 | 27/02/2021 | MANIK CHOUDHURY | 35.11 | 16.94 | 48.24 | 0
64 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Surjyapura Tengurpura, JL. No. 151, G.P.- Sadlichak of UTTAR KUMEDPUR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000300/2020-2021 | 274/MD | 28/01/2021 | 27/02/2021 | A. K. CONSTRUCTION | 29.56 | 22.01 | 74.45 | 100
65 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Gopalnagar, JL. No. 80, G.P.- Jogdala of PARAMESWARPUR Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000319/2020-2021 | 299/MD | 28/01/2021 | 27/02/2021 | S. N. CONSTRUCTION | 18.77 | 18.77 | 100 | 1
66 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Harischandrapur, JL. No. 83, G.P.- Baidyapur of BHABUK Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000325/2020-2021 | 305/MD | 28/01/2021 | 27/02/2021 | KRISHNENDU DUTTA | 25.76 | 24.94 | 96.83 | 1
67 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Kasba, JL. No. 45, G.P.-Bamangola of KHATIL Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000332/2020-2021 | 312/MD | 28/01/2021 | 27/02/2021 | EUREKA UNEMPLOYED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 15.48 | 9.46 | 61.16 | 1
68 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Uttar Rasulpur, JL. No. 71, G.P.-Bhakri of RAMPUR Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000304/2020-2021 | 284/MD | 28/01/2021 | 27/02/2021 | A. K. SIKDAR | 8.24 | 7.88 | 95.67 | 1
69 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Barinda, JL. No. 95, G.P.-Pakuahat of BASARA Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000312/2020-2021 | 292/MD | 28/01/2021 | 27/02/2021 | GOALPAR CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 5.85 | 9.98 | 170.72 | 1
70 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Isadpur, JL. No. 77, G.P.- Bhingole of KONAR Water Supply Scheme at Harishchandrapur-I Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000308/2020-2021 | 288/MD | 28/01/2021 | 27/02/2021 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 24.42 | 24.36 | 99.75 | 1
71 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Jalakar Bithan, JL. No. 115, G.P.- Muchia of MOBARAKPUR Water Supply Scheme at Old Malda Block under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer,Mr. Sumit Kumar Ghosh, Assistant Engineer | Bikash Balo, Junior Engineer,Mr. Tilok Roy, Junior Engineer | ORD/000315/2020-2021 | 295/MD | 28/01/2021 | 27/02/2021 | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 7.78 | 7.78 | 99.98 | 100
72 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Bhabuk, JL. No. 89, G.P.- Jajail of BHABUK Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000327/2020-2021 | 307/MD | 28/01/2021 | 27/02/2021 | S. R. CONSTRUCTION | 14.93 | 28.86 | 193.24 | 1
73 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Gangnadia, JL. No. 114, G.P.-Mahendrapur of GANNADIA Water Supply Scheme at Harischandrapur - II Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000291/2020-2021 | 265/MD | 28/01/2021 | 27/02/2021 | MANIK CHOUDHURY | 38.45 | 45.42 | 118.14 | 1
74 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Emergent repairing and laying of uPVC pipeline and Construction of SSP with other allied work to proper functioning of FHTC work within the command area of NEMUA Water Supply scheme under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer,Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer,Mukaddar Parvage, Junior Engineer | ORD/000401/2022-2023 | 2961/MD | 07/12/2022 | 06/01/2023 | SUDEB KARMAKAR | 2.09 | 0 | 0 | 0
75 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Restoration pipe line for Providing FHTC in connection with JJM at Birasthal along NH-81 under command area of Dakshin Sahar Piped Water Supply Scheme under Malda Division, PHE Dte. in the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000352/2022-2023 | 2547/MD | 03/11/2022 | 03/12/2022 | M/S. TEWARI CONSTRUCTION | 1.15 | 0 | 0 | 0
76 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of ARBARA Piped Water Supply Scheme at Chanchal-I Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000303/2022-2023 | 2196/MD | 22/09/2022 | 22/10/2022 | S & G CONSTRUCTION | 7.96 | 7.2 | 90.43 | 1
77 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Acceptance cum formal work order for Laying of additional pipe line and Providing FHTC connection at Uttar Rasulpur village of Rampur water supply scheme, Chanchal-II Dev. Block , Chanchal Sub-Division of PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000351/2022-2023 | 2546/MD | 03/11/2022 | 03/12/2022 | ANUKUL CHANDRA DAS | 6.35 | 6.19 | 97.61 | 100
78 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Nemua Water Supply Scheme at Old Malda Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000450/2023-2024 | 3367/MD | 29/08/2023 | 13/10/2023 | MOMTAJ ALI | 40.32 | 22.66 | 56.21 | 74
79 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Continuation work order for Hiring of 1 no diesel vehicle in good condition (traffic worthily) having licensed contract carriage permit from Regional Transport Authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 23/12/2023 to 19/06/2024=180 Days). Vehicle no. WB 65A/4911. | Mr. Prosanta Mandal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/001161/2023-2024 | 5151/MD | 21/12/2023 | 18/06/2024 | USHA ENTERPRISE | 0.86 | 0.39 | 45.52 | 0
80 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Continuation work order for Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 01/08/2023 to 31/01/2024). | Mr. Arnab Giri, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000987/2023-2024 | 2023/NBC-II | 30/08/2023 | 26/02/2024 | TARUN KUMAR BHATTACHARYA | 0.86 | 0.99 | 115.22 | 76
81 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Providing Functional Household Tap Connection (FHTC) At -Bibijhuti (JL. No. 58), Naikanda (JL. No. 39) & Chandipur (JL. No. 40) G.P.-Kharba In connection of Source Augmentation of Kendua PWSS at Chanchal-I Block under Malda Division. PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Yusuf Sk, Junior Engineer | ORD/000468/2023-2024 | 3458/MD | 07/09/2023 | 31/07/2024 | M/S /FAIZUL HAQUE BISWAS | 33.7 | 29.55 | 87.69 | 100
82 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Continuation of work order for hiring of inspection vehicle (motor cab or Maruti omni category non air condition Bharat stage III purchase on or after 1.05.2008 with deiseal/LPG/CNG Engine ) in perfectly good condition of performing along journey and should cover anywhere without any trouble on monthly heir basis for official use of the office of the Assistant Engineer ,RWS Malda sub division ,PHE Dte.( Period from 06/07/2023 to 31/12/2023 ) | Mr. Amit Biswas, Assistant Engineer |  | ORD/000310/2023-2024 | 199/RWS | 06/06/2023 | 01/12/2023 | SHYAMAL KUMAR MAITRA | 0.85 | 1.65 | 195.47 | 55
83 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Extension of UPVC pipe line laying for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Uttar Arbara under command area of ARBARA Water Supply Scheme at Chanchal-I Block under Malda Division. PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Yusuf Sk, Junior Engineer | ORD/000364/2023-2024 | 3053/MD | 09/08/2023 | 08/09/2023 | SOFIKUL ISLAM | 3.09 | 3.08 | 99.42 | 100
84 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Mabrakpur Water Supply Scheme at Old Malda Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Amit Biswas, Assistant Engineer,Mr. Arnab Giri, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000448/2023-2024 | 3365/MD | 29/08/2023 | 13/10/2023 | GOBINDA ENTERPRISE | 36.28 | 36.26 | 99.93 | 100
85 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Purba Binodpur Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer ,Ziaur Rahaman, Junior Engineer | ORD/000451/2023-2024 | 3368/MD | 29/08/2023 | 13/10/2023 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 10.11 | 9.26 | 91.59 | 100
86 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Kankot Piped Water Supply Scheme at Ratua-I Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Prosanta Mandal, Assistant Engineer | Tapan Haldar, Junior Engineer | ORD/000605/2023-2024 | 3811/MD | 29/09/2023 | 29/10/2023 | PRITAM ENTERPRISE | 7.66 | 7.65 | 99.8 | 100
87 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of BAHIRGACHHI Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Amit Biswas, Assistant Engineer,Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer ,Ziaur Rahaman, Junior Engineer | ORD/000717/2023-2024 | 4766/MD | 05/12/2023 | 21/07/2024 | IDEAL CONSTRUCTION | 12.1 | 9.3 | 76.83 | 80
88 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of UTTAR KUMEDPUR Water Supply Scheme at Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000722/2023-2024 | 4771/MD | 05/12/2023 | 19/01/2024 | MD WARESH ALI | 19.7 | 19.61 | 99.56 | 80
89 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Dakhin Sahar Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Yusuf Sk, Junior Engineer | ORD/000499/2024-2025 | 5403/MD | 21/10/2024 | 26/09/2025 | GOBINDA ENTERPRISE | 65.18 | 0 | 0 | 0
90 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Kankot Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Prosanta Mandal, Assistant Engineer | Tapan Haldar, Junior Engineer | ORD/000664/2024-2025 | 6164/MD | 05/12/2024 | 19/01/2025 | MD WARESH ALI | 30.59 | 0 | 0 | 0
91 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Sankail Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000663/2024-2025 | 6163/MD | 05/12/2024 | 01/10/2025 | M/S N. N. ENTERPRISE | 38.42 | 0 | 0 | 0
92 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Providing Functional Household Tap Connection (FHTC) and Laying of Distribution Pipeline in connection with Jal Jeevan Mission (JJM) at Rampur Water Supply Scheme under Chanchal-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000571/2024-2025 | 5484/MD | 24/10/2024 | 08/12/2024 | M/S JHA CONSTRUCTION | 57.8 | 0 | 0 | 0
93 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Raikhadighi Mouza under BAHIRGACHHI Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000727/2024-2025 | 6418/MD | 19/12/2024 | 02/02/2025 | ANUKUL CHANDRA DAS | 18.48 | 0 | 0 | 0
94 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Providing Functional Household Tap Connection (FHTC) and Laying of Distribution Pipeline in connection with Jal Jeevan Mission (JJM) at Malipakar Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000743/2024-2025 | 6585/MD | 31/12/2024 | 16/10/2025 | M/S BABLU ENTERPRISE | 44.5 | 0 | 0 | 50
95 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Basara Water Supply Scheme under Bamongola Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/001004/2023-2024 | 1512/MD | 16/03/2024 | 31/08/2024 | MANIK CHOUDHURY | 21.17 | 5.55 | 26.21 | 100
96 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at RAIKHADIGHI Mouza under BAHIRGACHI Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000997/2023-2024 | 1176/MD | 14/03/2024 | 01/01/2025 | ABHIJIT ENTERPRISE | 13.25 | 3.09 | 23.33 | 100
97 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Uttar Kumedpur Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000187/2024-2025 | 2966/MD | 10/06/2024 | 01/02/2025 | M/S DYNAMIC CONSTRUCTION | 7.44 | 0 | 0 | 100
98 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000104/2023-2024 | 34/MD | 04/01/2024 | 04/01/2024 | Resource Division | 3.08 | 0 | 0 | 0
99 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000112/2023-2024 | 55/MD | 04/01/2024 | 04/01/2024 | Resource Division | 0.62 | 0 | 0 | 0
100 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000137/2023-2024 | 112/MD | 05/01/2024 | 05/01/2024 | Resource Division | 1.23 | 0 | 0 | 0
101 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000101/2023-2024 | 31/MD | 04/01/2024 | 04/01/2024 | Resource Division | 5.85 | 0 | 0 | 0
102 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000014/2024-2025 | 3993/MD | 08/08/2024 | 08/08/2024 | Resource Division | 6.16 | 0 | 0 | 0
103 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Laying of additional pipeline for retrofitting and Installation of Functional House Connection of Nemua Piped Water Supply Scheme at Old Malda Block under Malda Division PHE. Dte. | Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000787/2024-2025 | 352/MD | 30/01/2025 | 29/07/2025 | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 89.7 | 0 | 0 | 34
104 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Augmentation work of OHR, Pump House and Boundary Wall of Arbara Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Yusuf Sk, Junior Engineer | ORD/000858/2024-2025 | 1051/MD | 18/03/2025 | 01/06/2025 | M/S ANKUSH ENTERPRISE | 32.37 | 0 | 0 | 0
105 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 40m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at head work site of Uttar Kumedpur Water Supply Scheme of Harishchandrapur-II Block under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000151/2025-2026 | 2689/MD | 04/06/2025 | 26/11/2026 | VISCOUS ENGINEERS PVT. LTD. | 18.02 | 0 | 0 | 0
106 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Augmentation work of OHR, Pump House and Boundary Wall of Daulatpur Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000855/2024-2025 | 1048/MD | 18/03/2025 | 15/08/2025 | M/S SABANA CONSTRUCTION | 36.38 | 0 | 0 | 0
107 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 50 m³/hr. capacity Pressure type Iron Elimination Plant with Construction of Blower room & backwash water disposal at Malipakar Water Supply Scheme of Harishchandrapur-II Dev. Block under Malda Division P.H.E Dte in the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000135/2025-2026 | 2510/MD | 29/05/2025 | 11/10/2025 | BANIK BROTHERS | 20.04 | 0 | 0 | 0
108 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Arbara Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Yusuf Sk, Junior Engineer | ORD/000092/2025-2026 | 2334/MD | 22/05/2025 | 21/07/2025 | S & G CONSTRUCTION | 28.65 | 0 | 0 | 0
109 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Additional laying of Pipe line for improvement of FHTC functionality by different dia UPVC pipe & providing FHTC for PURBA BINODPUR piped Water Supply Scheme at Gazole Block in the District of Malda under Malda Division, P.H.E.Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000206/2025-2026 | 3722/MD | 30/07/2025 | 26/01/2026 | ABHIJIT CONSTRUCTION | 17.47 | 0 | 0 | 0
110 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Additional laying of Pipe line for improvement of FHTC functionality by different dia UPVC pipe & FHTC for BASARA piped Water Supply Scheme at Bamongola Block in the District of Malda under Malda Division, P.H.E.Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000205/2025-2026 | 3693/MD | 29/07/2025 | 01/01/2026 | MANIK CHOUDHURY | 60.11 | 0 | 0 | 0
111 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Sinking of 200mm (all through) Big Dia Tube Well of 180m Deep at 3rd Tube Well Site and Construction of Pump House at 3rd Tube Well site Laying of dedicated/Parallel pipe line and Providing balanced FHTC under GANNADIA Piped Water Supply Scheme under at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000208/2025-2026 | 3723/MD | 30/07/2025 | 01/04/2026 | HARUN ALL RASHID & BROTHERS | 39.34 | 0 | 0 | 0
112 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000003/2025-2026 | 2579/MD | 30/05/2025 | 30/05/2025 | Resource Division | 276.41 | 0 | 0 | 0
113 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Laying of Dedicated / Parallel Pipeline for improvement of FHTC functionality by different dia UPVC pipe & Providing FHTC for Bhabuk Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Arnab Giri, Assistant Engineer,Sri Biswadip Sengupta,Sri Biswadip Sengupta, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000955/2025-2026 | 771/MD | 19/02/2026 | 20/04/2026 | RATAN KARMAKAR | 9.66 | 0 | 0 | 0
114 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Dedicated pipe line for Functionality, Road restoration, Rectification of FHTC and Installation of Functional House Connection of Mobarakpur Piped Water Supply Scheme under Malda Division PHE. Dte. | Mr. Debasis Pal, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000423/2026-2027 | 3168/MD | 20/08/2026 | 19/10/2026 | BINA CONSTRUCTION | 38.74 | 0 | 0 | 0
115 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | Retrofitting | Emergency Interconnection between 4th Tube Well and Distribution Pipe Line and Extra 20 mm OD HOPE pipe for Functionality at jalkar Bithan (4th Tube Well site) of Mobarakpur Piped Water Supply Scheme under Malda Division PHE. Dte. | Mr. Debasis Pal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer,Mukaddar Parvage, Junior Engineer | ORD/000410/2026-2027 | 2864/MD | 21/07/2026 | 19/09/2026 | GOBINDA ENTERPRISE | 3.08 | 0 | 0 | 0
Total | [13 empty] | 2788.98 | 1530.06 | 54.86