## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of BHAIRABPUR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000057/2020-2021 | 2142/MD | 16/09/2020 | 15/11/2020 | SUBHAS CHANDRA KESHARI | 92.31 | 48.11 | 52.12 | 1
2 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAKSHIN MAHENDRAPUR Water Supply Scheme at Harishchandrapur-I Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000079/2020-2021 | 2683/MD | 06/11/2020 | 21/12/2020 | MADE & TRADE CO. | 85.01 | 112.26 | 132.06 | 0
3 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of TALSUR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000085/2020-2021 | 2255/MD | 29/09/2020 | 28/12/2020 | TARUN KUMAR BHATTACHARYA | 135.29 | 30 | 22.17 | 0
4 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAHARA Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer |  | ORD/000552/2020-2021 | 2684/MD | 03/12/2020 | 04/12/2020 | MADE & TRADE CO. | 0 | 23.94 | 5439781.82 | 1
5 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Acceptance cum formal work order for Placing of Diesel Driven Car on hire basis for official use of the office of the Assistant Engineer, RWS Malda Sub-Division, PHE Dte. under Malda Division, PHE Dte. in good running condition. (Period from 01/01/2021 to 31/12/2021). | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000573/2020-2021 | 3280/MD | 30/12/2020 | 30/12/2021 | SHYAMAL KUMAR MAITRA | 1.73 | 1.29 | 74.48 | 1
6 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Placing of Diesel Driven Bolero Car on hire basis for official use of the office of the Assistant Engineer, Chanchal Sub-Division, PHE Dte. under Malda Division, PHE Dte. (Period from 01/02/2020 to 31/01/2021) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000778/2019-2020 | 349/MD | 28/01/2020 | 28/01/2020 | RANJIT ADHIKARY | 1.51 | 1.51 | 100 | 1
7 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAMBALPUR Water Supply Scheme at Ratua-II Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000082/2020-2021 | 2437/MD | 12/10/2020 | 11/12/2020 | HANNAN BUILDERS PVT. LTD. | 156.77 | 138.24 | 88.18 | 1
8 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of JAGANNATHPUR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000060/2020-2021 | 2141/MD | 16/09/2020 | 31/10/2020 | DEBAPRIYA SAHA | 77.59 | 32.71 | 42.15 | 0
9 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of KUTUB SAHAR Water Supply Scheme at Gazole Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000070/2020-2021 | 2135/MD | 16/09/2020 | 15/12/2020 | HANNAN BUILDERS PVT. LTD. | 145.2 | 20.4 | 14.05 | 1
10 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MAGURA ZONE-I Water Supply Scheme at Ratua-II Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer |  | ORD/000559/2020-2021 | 2551/MD | 15/10/2020 | 14/11/2020 | MILLENNIUM ENTERPRISR | 1 | 13.37 | 1336.53 | 1
11 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of BEJPURA Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000056/2020-2021 | 2152/MD | 16/09/2020 | 31/10/2020 | NEOGI ENTERPRISE | 68.33 | 36.27 | 53.08 | 1
12 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of SADLICHAK Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000027/2020-2021 | 1962/MD | 31/08/2020 | 30/09/2020 | BEE GEE CONSTRUCTION | 43.35 | 21.01 | 48.48 | 1
13 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAHARA Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000080/2020-2021 | 2684/MD | 06/11/2020 | 05/01/2021 | MADE & TRADE CO. | 132.4 | 29.22 | 22.07 | 100
14 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BHADO Water Supply Scheme at Ratua-I Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000155/2020-2021 | 2704/MD | 10/11/2020 | 09/01/2021 | GHOSH BROTHERS | 148.17 | 148.15 | 99.99 | 100
15 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DALLA Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000560/2020-2021 | 2438/MD | 12/10/2020 | 09/02/2021 | M/S JHA CONSTRUCTION | 10 | 11.19 | 111.87 | 1
16 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of RAJARAMPUR Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000087/2020-2021 | 2263/MD | 29/09/2020 | 13/11/2020 | UTTAM KUMAR DUTTA | 59.93 | 48.18 | 80.4 | 0
17 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ANANDIPUR Water Supply Scheme at Englishbazar Block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000166/2020-2021 | 2719/MD | 10/11/2020 | 10/12/2020 | MANAS KUMAR SAHA | 50.07 | 46.89 | 93.65 | 1
18 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of KHANPUR HULASPUR Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Yusuf Sk, Junior Engineer | ORD/000065/2020-2021 | 2139/MD | 16/09/2020 | 31/10/2020 | M/S TRILOCHAN CONSTRUCTION CO | 65.52 | 16.95 | 25.87 | 0
19 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of GUN SANKRUL Water Supply Scheme at Malda Old Block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000059/2020-2021 | 2261/MD | 29/09/2020 | 13/11/2020 | MILLENNIUM ENTERPRISR | 74.5 | 21.23 | 28.49 | 0
20 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of JALALPUR Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000067/2020-2021 | 2140/MD | 16/09/2020 | 15/11/2020 | FUTURE | 116.65 | 86.06 | 73.77 | 0
21 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Balupur Zone-III Water Supply Scheme at Ratua-I under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000226/2021-2022 | 2379/MD | 13/08/2021 | 12/09/2021 | FUTURE | 13.48 | 0 | 0 | 0
22 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Acceptance cum formal work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, RWS Malda Sub-Division, PHE Dte. under Malda Division, PHE Dte. (Period from 01/01/2022 to 30/06/2022). | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000557/2021-2022 | 520/MSD | 31/12/2021 | 30/06/2022 | SHYAMAL KUMAR MAITRA | 0.86 | 1.2 | 139.78 | 1
23 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, RWS Malda Sub-Division, PHE Dte. under Malda Division, PHE Dte. (Period from 01/01/2022 to 30/06/2022). | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000717/2021-2022 | 520/MSD | 31/12/2021 | 06/01/2022 | SHYAMAL KUMAR MAITRA | 2.16 | 0.67 | 30.82 | 0
24 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Acceptance cum formal work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division, PHE Dte. under Malda Division, PHE Dte. (Period from 01/01/2022 to 30/06/2022). | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000706/2021-2022 | 521/MSD | 31/12/2021 | 31/12/2022 | ARUN KUMAR DAS | 0.86 | 1.76 | 206.19 | 1
25 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of KHANPUR Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000356/2020-2021 | 554/MD | 12/02/2021 | 14/03/2021 | RAY CONSTRUCTION CO. | 57.64 | 80.35 | 139.4 | 1
26 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection under DAULATNAGAR Piped Water Supply Scheme at Harishchandrapur-II Block in the district of Malda under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000357/2020-2021 | 553/MD | 12/02/2021 | 13/04/2021 | NEOGI ENTERPRISE | 120.32 | 119.96 | 99.71 | 1
27 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection under BALUPUR ZONE-II Piped Water Supply Scheme at Ratua-I Block in the district of Malda under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000346/2020-2021 | 512/MD | 09/02/2021 | 10/04/2021 | JAL PRAVAHIKA PVT. LTD. | 104.87 | 5.04 | 4.81 | 0
28 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection under BEHERPUR ZONE-I Pipe Water Supply Scheme at Bamangola Block in the district of Malda under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000481/2020-2021 | 435/MD | 08/02/2021 | 09/04/2021 | PROJECT INDIA | 126.35 | 53.22 | 42.12 | 100
29 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Acceptance cum formal work order for Supplying, fitting and fixing of G.I. pipes of TATA make & Collection of Household Tap Connection details through baseline household Mobile's App( Jal Swapna) for Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Jalalpur Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000515/2021-2022 | 546/CSD | 01/11/2021 | 01/12/2021 | FUTURE | 2.66 | 2.66 | 100 | 1
30 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Acceptance cum formal work order for Collection of Household Tap Connection details through baseline household Mobile's App( Jal Swapna) under commend area of Kutubsahar Water Supply Scheme of Gazole Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000658/2021-2022 | 1899/MD | 30/06/2021 | 28/10/2021 | RABIUL ISLAM | 10 | 0.63 | 6.26 | 0
31 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of UTTAR CHANDIPUR ZONE-II Water Supply Scheme at Manikchak Dev. Block under Malda Division, PHE Dte. (Phase-I) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000529/2021-2022 | 3573/MD | 20/12/2021 | 19/01/2022 | M/S JHA CONSTRUCTION | 39.81 | 36.95 | 92.82 | 1
32 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of UTTAR CHANDIPUR ZONE-IV Water Supply Scheme at Manikchak Dev. Block under Malda Division, PHE Dte. (Phase-I) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000531/2021-2022 | 3575/MD | 20/12/2021 | 19/01/2022 | PABITRA MANDAL | 19.48 | 17.34 | 89.01 | 1
33 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Acceptance cum formal work order for Different dia. Damaged pipe line repair on emergency basis (damage due to widening of road) in connection with annual operation maintenance and providing FHTC to villagers under MEKPUR Piped Water Supply Scheme at Old Malda Dev. block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000549/2021-2022 | 513/MSD | 31/12/2021 | 01/01/2022 | A. K. CONSTRUCTION | 2.06 | 0 | 0 | 0
34 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of UTTAR CHANDIPUR ZONE-III Water Supply Scheme at Manikchak Dev. Block under Malda Division, PHE Dte. (Phase-I) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000530/2021-2022 | 3574/MD | 20/12/2021 | 19/01/2022 | GOBINDA ENTERPRISE | 19.97 | 19.47 | 97.5 | 1
35 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Supply of Forms & Stationary articles for the use of this office. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000707/2021-2022 | 3456/MD | 06/12/2021 | 07/12/2021 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 1.28 | 1.28 | 100 | 1
36 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Acceptance cum formal work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Period from 01/01/2022 to 30/06/2022). | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000705/2021-2022 | 522/MSD | 31/12/2021 | 30/06/2022 | UTTAM KUMAR GHOSH | 0.86 | 2.38 | 278.9 | 1
37 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Continuation work order for Placing of Diesel Driven Car on hire basis for official use of the office of the Assistant Engineer, Chanchal Sub-Division, PHE Dte. under Malda Division, PHE Dte. in good running condition. (Period from 01/02/2021 to 30/09/2021). | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000579/2020-2021 | 276/MD | 28/01/2021 | 28/01/2022 | RANJIT ADHIKARY | 2.66 | 1.26 | 47.4 | 0
38 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Acceptance cum formal work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division, PHE Dte. under Malda Division, PHE Dte. (Period from 01/01/2022 to 30/06/2022). | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000718/2021-2022 | 521/MSD | 31/12/2021 | 30/06/2022 | ARUN KUMAR DAS | 2.16 | 0.9 | 41.61 | 0
39 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Acceptance cum formal work order for Supplying, fitting and fixing of G.I. pipes of TATA make & Collection of Household Tap Connection details through baseline household Mobile's App( Jal Swapna) for Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Bejpura Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000513/2021-2022 | 542/CSD | 27/10/2021 | 26/11/2021 | NEOGI ENTERPRISE | 4.26 | 4.24 | 99.41 | 1
40 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Balupur Zone-I Water Supply Scheme under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000225/2021-2022 | 2378/MD | 13/08/2021 | 12/09/2021 | ACHARYYA CONSTRUCTION | 13.48 | 12.47 | 92.45 | 1
41 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Acceptance cum formal work order for Supplying, fitting and fixing of G.I. pipes of TATA make & Collection of Household Tap Connection details through baseline household Mobile's App( Jal Swapna) for Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Jalalpur Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000514/2021-2022 | 545/CSD | 01/11/2021 | 01/12/2021 | FUTURE | 4.72 | 4.6 | 97.45 | 1
42 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Uttar Bhabanipur, JL. No. 73, G.P.-Bhakri of RAMPUR Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000305/2020-2021 | 285/MD | 28/01/2021 | 27/02/2021 | M/S BANERJEE CONSTRUCTION | 13.56 | 17.95 | 132.36 | 1
43 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Acceptance cum formal work order for Additional laying work of UPVC distribution pipe line for JALALPUR Water Supply Scheme at CHANCHAL- II Dev. Block under Malda Division, PHE Dte. In the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000352/2020-2021 | 552/MD | 12/02/2021 | 14/03/2021 | FUTURE | 3.33 | 5.86 | 175.78 | 0
44 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Manoharpur, JL. No. 117, G.P.-Sultannagar of GANNADIA Water Supply Scheme at Harischandrapur - II Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000338/2020-2021 | 447/MD | 08/02/2021 | 10/03/2021 | MANIK CHOUDHURY | 37.13 | 22.88 | 61.61 | 0
45 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000003/2021-2022 | 3552/MD | 26/11/2021 | 26/11/2021 | Resource Division | 8.78 | 0 | 0 | 0
46 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000004/2021-2022 | 3585/MD | 21/12/2021 | 21/12/2021 | Resource Division | 6.45 | 0 | 0 | 0
47 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Formal work order for the work of Hiring of 1 no. diesel vehicle in good condition (traffic worthily) having licence contract carriage permit from Regional Transport Authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 01/04/2022 to 27/09/2022) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000127/2022-2023 | 797/MD | 01/04/2022 | 28/09/2022 | USHA ENTERPRISE | 0.86 | 0.45 | 52.45 | 1
48 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Continuation work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Period from 01/07/2022 to 31/12/2022). | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000137/2022-2023 | 213/MSD | 30/06/2022 | 31/12/2022 | UTTAM KUMAR GHOSH | 0.86 | 2.07 | 242.04 | 1
49 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Formal work order for the work of Hiring of 1 no. diesel vehicle in good condition (traffic worthily) having licence contract carriage permit from Regional Transport Authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 01/02/2022 to 31/03/2022) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000703/2021-2022 | 232/MD | 27/01/2022 | 27/03/2022 | USHA ENTERPRISE | 0.28 | 0.33 | 118 | 1
50 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Car hiring No. 51C/7999 for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 01/03/2022 to 30/06/2022) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000704/2021-2022 | 473/MD | 25/02/2022 | 25/06/2022 | TARUN KUMAR BHATTACHARYA | 0.58 | 1.04 | 180.33 | 1
51 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Continuation work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, RWS Malda Sub-Division, PHE Dte. (Period from 01/07/2022 to 31/12/2022). | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000141/2022-2023 | 215/MSD | 30/06/2022 | 06/07/2022 | SHYAMAL KUMAR MAITRA | 0.86 | 1.6 | 186.94 | 1
52 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Continuation work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division, PHE Dte. under Malda Division, PHE Dte. (Period from 01/07/2022 to 31/12/2022). | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000334/2022-2023 | 215/1/MSD | 30/06/2022 | 31/12/2022 | ARUN KUMAR DAS | 4.5 | 2.17 | 48.27 | 0
53 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of MOYNA Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. In the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000408/2022-2023 | 2991/MD | 07/12/2022 | 21/01/2023 | S. R. CONSTRUCTION | 25.41 | 21.2 | 83.43 | 0
54 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Acceptance cum formal work order for Laying of distribution pipe line for Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM) under command area of Bhado of BHADO Water Supply Scheme under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000381/2022-2023 | 2735/MD | 18/11/2022 | 18/12/2022 | M/S MANDAL & SONS | 6.77 | 6.11 | 90.3 | 0
55 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing car on daily hirer basis @ Rs. 12.00/km for official use of the office of the Assistant Engineer, Chanchal Sub-Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000503/2022-2023 | 653/CSD | 07/11/2022 | 07/11/2023 | SAUDIPTA KUMAR DAS | 4.56 | 0.33 | 7.21 | 0
56 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Continuation work order for the work of hiring of 1 no diesel vehicle in good condition (traffic authority) having licence contract carage permit from regional transport authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte (Period from 28/09/2022 to 26/03/2023) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000533/2022-2023 | 1108/MD | 20/09/2022 | 19/03/2023 | USHA ENTERPRISE | 4.5 | 1.02 | 22.57 | 0
57 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MOYNA Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000563/2021-2022 | 49/MD | 13/01/2022 | 14/03/2022 | S. R. CONSTRUCTION | 40.3 | 39.7 | 98.5 | 1
58 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Acceptance cum formal work order for Repairing of existing FHTC connection for Talsur Water Supply Scheme under Malda division.P.H.E.Dte. In the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000074/2022-2023 | 330/CSD | 22/06/2022 | 22/07/2022 | GOALPARA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 1.06 | 1.06 | 100 | 1
59 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of KHANPUR HULASPUR Water Supply Scheme at Chanchal-I Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000564/2021-2022 | 48/MD | 13/01/2022 | 03/02/2022 | BIDYUT MAHALDAR | 7.56 | 6.11 | 80.71 | 0
60 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Uttar Chandipur Zone-III Water Supply Scheme at Manikchak Dev. Block under Malda Division, PHE Dte. in the district of Malda. (Phase-II) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000123/2022-2023 | 1641/MD | 19/07/2022 | 18/08/2022 | UTTAM KUMAR GHOSH | 23.82 | 22.75 | 95.5 | 1
61 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Acceptance cum formal work order for Replacement of different dia A.C pipe line (damage due to widening of road) by laying of different dia UPVC pipe in connection with annual operation maintenance and providing FHTC to Villagers under RAJARAMPUR Piped Water Supply Scheme of Habibpur Dev. Block in the District of Malda under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000672/2021-2022 | 142/MSD | 31/03/2022 | 02/04/2022 | SSD CONSTRUCTION | 4.84 | 4.35 | 89.81 | 1
62 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Uttar Chandipur Zone-II Water Supply Scheme at Manikchak Dev. Block under Malda Division, PHE Dte. in the district of Malda. (Phase-II) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000122/2022-2023 | 1640/MD | 19/07/2022 | 18/08/2022 | KRISHNENDU DUTTA | 26.59 | 26.43 | 99.41 | 1
63 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) including upvc laying in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of UTTAR CHANDIPUR ZONE-IV Water Supply Scheme at Manikchak Dev. Block under Malda Division, PHE Dte. in the district of Malda (Phase - II). | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000663/2021-2022 | 742/MD | 28/03/2022 | 27/04/2022 | FUTURE | 22.06 | 21.09 | 95.6 | 1
64 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Supply of Stationary articles for the use of Malda District Laboratory. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000708/2021-2022 | 367/MD | 10/02/2022 | 11/02/2022 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 0.35 | 0.35 | 100 | 1
65 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Car hiring No. WB 65 A/4911 for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000258/2022-2023 | 312/NBC-II | 01/04/2022 | 01/04/2023 | USHA ENTERPRISE | 3.59 | 1.09 | 30.42 | 0
66 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Continuation work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Period from 01/01/2023 to 30/06/2023). | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000510/2022-2023 | 520/MSD | 30/12/2022 | 30/06/2023 | UTTAM KUMAR GHOSH | 0.86 | 2.29 | 268.02 | 15
67 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Acceptance cum formal work order for Additional laying work of DI & UPVC pipe line of SADLICHAK W/S Scheme at HARISHCHANDRAPUR-II Dev. Block under Malda division.P.H.E.Dte. In the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000655/2021-2022 | 47/CSD | 14/01/2022 | 13/02/2022 | BEE GEE CONSTRUCTION | 4.19 | 3.9 | 93.03 | 1
68 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Acceptance cum formal work order for Extension of UPVC pipe line laying for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) under command area of Khanpur-Hulaspur W/S Scheme at Chanchal-I Block under Malda Division. PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Yusuf Sk, Junior Engineer | ORD/000403/2022-2023 | 2963/MD | 07/12/2022 | 06/01/2023 | BIDYUT MAHALDAR | 7.04 | 7.03 | 99.79 | 100
69 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Acceptance cum formal work order for Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Period from 01/11/2022 to 30/04/2023). | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000518/2022-2023 | 2474/MD | 21/10/2022 | 21/10/2023 | SHABNAM ARA | 4.5 | 3.51 | 77.94 | 21
70 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Uttar Chandipur Zone-IV Water Supply Scheme at Manikchak Dev. Block under Malda Division, PHE Dte. in the district of Malda. (Phase-III) | Mr. Arnab Giri, Assistant Engineer,Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000124/2022-2023 | 1642/MD | 19/07/2022 | 18/08/2022 | M/S AMIT KUMAR GUPTA | 16.26 | 15.32 | 94.24 | 1
71 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of KHANPUR HULASHPUR Water Supply Scheme at Chanchal-I Dev. Block under Malda Division, PHE Dte. In the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Yusuf Sk, Junior Engineer | ORD/000395/2022-2023 | 2955/MD | 07/12/2022 | 06/01/2023 | BIDYUT MAHALDAR | 5.17 | 4.98 | 96.37 | 100
72 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Supply of Stationary articles for the use of Malda District Laboratory. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000709/2021-2022 | 368/MD | 10/02/2022 | 11/02/2022 | MALDA DISTRICT SERVICE CUM-MARKETING INDS. CO-OP UNION LTD. | 1.1 | 0.46 | 41.65 | 0
73 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bejpura Piped Water Supply Scheme (Phase-II) at Harischandrapur - II Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000055/2022-2023 | 1487/MD | 23/06/2022 | 23/07/2022 | CHARU CONSTRUCTION | 6.53 | 6.53 | 99.95 | 1
74 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Acceptance cum formal work order for Emergent installation of Sulice Valve & Construction of Sluice Valve & Repairing of FHTC for Khanpur Hulashpur Water Supply Scheme under Malda division, P.H.E. Dte. In the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000631/2021-2022 | 31/CSD | 05/01/2022 | 20/01/2022 | BIDYUT MAHALDAR | 1.27 | 1.27 | 99.9 | 1
75 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000006/2021-2022 | 456/MD | 22/02/2022 | 22/02/2022 | Resource Division | 3.29 | 0 | 0 | 0
76 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000008/2022-2023 | 1258/MD | 27/05/2022 | 27/05/2022 | Resource Division | 8.01 | 0 | 0 | 0
77 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Acceptance cum formal work order for Supply & delivery of Steel Table with Locker and Wooden Top, Office Visitors Chair and High back mesh Executive Chair for the Conference Room of District Laboratory 1st Floor and office of the Superintending Engineer, North Bengal Circle - Il under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000021/2023-2024 | 1712/MD | 20/04/2023 | 05/05/2023 | M/S PARIMAL DAS | 2.42 | 2.42 | 100 | 0
78 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Saiyedpur Water Supply Scheme at Old Malda Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000454/2023-2024 | 3371/MD | 29/08/2023 | 13/10/2023 | S. R. CONSTRUCTION | 20.14 | 13.53 | 67.19 | 100
79 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Hiring of 1 no. diesel vehicle in good condition (traffic worthily) having licence contract carriage permit from Regional Transport Authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 26/06/2023 to 22/12/2023) | Mr. Prosanta Mandal, Assistant Engineer |  | ORD/000562/2023-2024 | 1452/NBC-II | 21/06/2023 | 19/12/2023 | USHA ENTERPRISE | 2.19 | 2.03 | 92.64 | 42
80 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of BALUPUR ZONE-II & III Water Supply Scheme at Ratua-I Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Prosanta Mandal, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/000742/2023-2024 | 5247/MD | 22/12/2023 | 05/02/2024 | M/S. TEWARI CONSTRUCTION | 56.74 | 16.52 | 29.11 | 40
81 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Continuation work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Period from 01/01/2024 to 30/06/2024). | Mr. Prosanta Mandal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000894/2023-2024 | 1010/MSD | 29/12/2023 | 29/06/2024 | UTTAM KUMAR GHOSH | 0.86 | 2.38 | 277.81 | 25
82 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Continuation work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division, PHE Dte. under Malda Division, PHE Dte. (Period from 01/01/2024 to 30/06/2024). | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000922/2023-2024 | 1011/MSD | 29/12/2023 | 29/06/2024 | ARUN KUMAR DAS | 0.86 | 1.93 | 225.91 | 67
83 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Continuation of work order for hiring of inspection vehicle(Motor Cab or Maruti Omni Category(Standard,Non-Air Condition, Bharat Stage-III purchase on or after 01.05.2008 with Diesel/LPG/CNG Engine)in perfectly good condition of performing a very long journey and should cover anywhere without any trouble on monthly hire basis for official use of the office of the Assistant Engineer, R.W.S. Malda Sub-Division, PHE Dte.(Period from 01.01.2024 to 30.06.2024) | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000930/2023-2024 | 431/RWS | 29/12/2023 | 28/06/2024 | SHYAMAL KUMAR MAITRA | 0.86 | 1.84 | 213.08 | 70
84 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Continuation work order for Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Division, PHE Dte. (Period from 20/08/2023 to 15/02/2024). | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000938/2023-2024 | 3225/MD | 18/08/2023 | 14/02/2024 | M/S. TEWARI CONSTRUCTION | 0.86 | 1.96 | 229.36 | 90
85 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Continuation work order for Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Divion, PHE Dte. (Period from 10/08/2023 to 06/02/2024). | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000939/2023-2024 | 3029/MD | 08/08/2023 | 04/02/2024 | M/S FOUR STAR CONSTRUCTION | 0.86 | 2 | 234.47 | 99
86 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Continuation work order for the work of hiring of 1 no diesel vehicle in good condition (traffic authority) having licence contract carage permit from regional transport authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte (Period from 23/12/2023 to 19/06/2024) | Mr. Arnab Giri, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/001010/2023-2024 | 2089/NBC-II | 20/12/2023 | 17/06/2024 | USHA ENTERPRISE | 0.86 | 0.39 | 45.28 | 26
87 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Acceptance cum formal work order for hiring of inspection vehicle (Motor Cab or Maruti Omni Category (Standard), Non-Air Condition, Bharat Stage-III purchased on or after 01.05.2008 with Diesel/LPG/CNG Engine) in perfectly good condition of performing a very long journey and should cover anywhere without any trouble on monthly hire basis for official use of the office of the Assistant Engineer, R.W.S. Malda Sub-Division, P.H.E. Dte. (Period from 06/01/2023 to 05/07/2023) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000437/2022-2023 | 193/RWS | 05/01/2023 | 05/07/2023 | SHYAMAL KUMAR MAITRA | 0.86 | 1.61 | 188.57 | 15
88 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Acceptance cum formal work order for Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Division, PHE Dte. (Period from 20/02/2023 to 19/08/2023). | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000760/2022-2023 | 809/MD | 17/02/2023 | 16/08/2023 | M/S. TEWARI CONSTRUCTION | 0.86 | 2.22 | 259.71 | 100
89 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Acceptance cum formal work order for Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Divion, PHE Dte. (Period from 10/03/2023 to 09/08/2023). | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000761/2022-2023 | 1020/MD | 10/03/2023 | 06/09/2023 | M/S FOUR STAR CONSTRUCTION | 0.86 | 1.83 | 214.43 | 100
90 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Mekpur Water Supply Scheme at Old Malda Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000449/2023-2024 | 3366/MD | 29/08/2023 | 13/10/2023 | MANIK CHOUDHURY | 16.14 | 15.87 | 98.34 | 90
91 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Rajarampur Water Supply Scheme at Habibpur Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000452/2023-2024 | 3369/MD | 29/08/2023 | 13/10/2023 | M/S PRATIMA CONSTRUCTION | 16.13 | 15.46 | 95.8 | 100
92 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Continuation work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Period from 01/07/2023 to 31/12/2023). | Mr. Prosanta Mandal, Assistant Engineer |  | ORD/000230/2023-2024 | 504/MSD | 30/06/2023 | 31/12/2023 | UTTAM KUMAR GHOSH | 0.86 | 1.18 | 138.09 | 26
93 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Sadlichak Piped Water Supply Scheme at Harishchandrapur-II Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000604/2023-2024 | 3810/MD | 16/10/2023 | 15/11/2023 | RABIUL ISLAM | 8.8 | 8.79 | 99.93 | 90
94 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of DALLA Water Supply Scheme at Habibpur Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000718/2023-2024 | 4767/MD | 05/12/2023 | 19/01/2024 | A. B. CONSTRUCTION | 14.09 | 13.2 | 93.69 | 100
95 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of KUTUB SAHAR Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000720/2023-2024 | 4769/MD | 05/12/2023 | 19/01/2024 | ACHARYYA CONSTRUCTION | 12.14 | 12.14 | 99.96 | 100
96 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of KHOPAKATI Water Supply Scheme at Harishchandrapuir-II Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000743/2023-2024 | 5245/MD | 22/12/2023 | 05/02/2024 | M/S FOUR STAR CONSTRUCTION | 38.41 | 37.84 | 98.52 | 98
97 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Bill for car hiring no. WB/51C/7999 for office of the Superintending Enginner, North Bengal Circle-II, PHE Dte. For the period from (01/02/2023 to 15/05/2023). |  |  | BILL/00228/2023-2024 | BP-2023-24-108 | 13/07/2023 | 13/07/2023 | TARUN KUMAR BHATTACHARYA | 1.05 | 0 | 0 | 0
98 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Bill for reimbursement of cost of Diesel and Mobil in respect of hired vehicle Car No. WB65C/6570, For the month of MAY, 2023. |  |  | BILL/00289/2023-2024 | BP-2023-24-143 | 09/08/2023 | 09/08/2023 | UTTAM KUMAR GHOSH | 0.4 | 0 | 0 | 0
99 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Magura Water Supply Scheme under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Prasanta Mandal, Assistant Engineer,Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer,Sudip Kumar Mahata, Junior Engineer | ORD/000276/2024-2025 | 3196/MD | 27/06/2024 | 11/08/2024 | NATIONAL CONSTRUCTION | 26.03 | 0 | 0 | 0
100 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Extension of UPVC pipe line for Providing Functional Household Tap Connection with Jal Jeevan Mission (JJM) command area of Khanpur Hulashpur Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Yusuf Sk, Junior Engineer | ORD/000281/2024-2025 | 3232/MD | 28/06/2024 | 12/08/2024 | BIDYUT MAHALDAR | 9.98 | 0 | 0 | 0
101 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Khopakati Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000625/2024-2025 | 5832/MD | 22/11/2024 | 30/06/2026 | M/S SABANA CONSTRUCTION | 55.74 | 0 | 0 | 0
102 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division Division, PHE Dte. (Period from 01/03/2024 to 31/08/2024). | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000993/2023-2024 | 843/MD | 22/02/2024 | 20/08/2024 | RAJENDRA PRASAD SINGH | 0.86 | 2.39 | 280.09 | 17
103 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gun Sankrul Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/001021/2023-2024 | 1189/MD | 14/03/2024 | 01/04/2025 | TARUN KUMAR DEY | 26.39 | 0 | 0 | 0
104 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Mekpur Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/001011/2023-2024 | 1513/MD | 16/03/2024 | 30/04/2024 | A. B. CONSTRUCTION | 26.41 | 0 | 0 | 0
105 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division Division, PHE Dte. (Period from 01/09/2024 to 28/02/2025). | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000444/2024-2025 | 4590/MD | 30/08/2024 | 26/02/2025 | RAJENDRA PRASAD SINGH | 0.86 | 2.37 | 277.37 | 0
106 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Sadlichak Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000506/2024-2025 | 5409/MD | 21/10/2024 | 30/04/2026 | S. N. CONSTRUCTION | 41.99 | 0 | 0 | 0
107 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Malsa Mouza of KhanpurHulaspur Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Prosanta Mandal, Assistant Engineer,Mr. Sumit Kumar Ghosh, Assistant Engineer | Sudip Kumar Mahata, Junior Engineer,Yusuf Sk, Junior Engineer | ORD/000574/2024-2025 | 5485/MD | 24/10/2024 | 20/10/2025 | M/S /FAIZUL HAQUE BISWAS | 26.08 | 0 | 0 | 40
108 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Kutub Sahar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000721/2024-2025 | 6412/MD | 19/12/2024 | 27/06/2026 | PABITRA MANDAL | 40.29 | 0 | 0 | 65
109 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and Laying with Extension of different diameter (OD) uPVC pipe line under command area at Baherpur Zone-II Water Supply Scheme under Bamangola Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Debasis Pal, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000668/2024-2025 | 6167/MD | 05/12/2024 | 19/01/2025 | S. R. CONSTRUCTION | 63.36 | 0 | 0 | 0
110 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the Assistant Engineer, Malda Division, PHE Dte. (Period from 01/07/2024 to 31/12/2024). | Mr. Prasanta Mandal, Assistant Engineer,Mr. Prosanta Mandal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000324/2024-2025 | 3255/MD | 28/06/2024 | 25/12/2024 | AMIN ENTERPRISE | 0.86 | 2.38 | 278.53 | 60
111 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Division Division, PHE Dte.(Car-1) (Period from 01/07/2024 to 31/12/2024). | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000325/2024-2025 | 3256/MD | 28/06/2024 | 25/12/2024 | M/S FOUR STAR CONSTRUCTION | 0.86 | 2.19 | 256 | 100
112 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, RWS Malda Sub-Division Division, PHE Dte. (Car-2) (Period from 15/06/2024 to 14/12/2024). | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000327/2024-2025 | 3054/MD | 14/06/2024 | 11/12/2024 | RUQAIYA ENTERPRISE | 0.86 | 1.92 | 224.94 | 0
113 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division Division, PHE Dte. (Period from 01/07/2024 to 31/12/2024). | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000321/2024-2025 | 3252/MD | 28/06/2024 | 25/12/2024 | ARUN KUMAR DAS | 0.86 | 1.99 | 233.09 | 0
114 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, RWS Malda Sub-Division Division, PHE Dte. (Car-1) (Period from 01/07/2024 to 31/12/2024). | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000322/2024-2025 | 3253/MD | 28/06/2024 | 25/12/2024 | SHYAMAL KUMAR MAITRA | 0.86 | 2.17 | 254.31 | 0
115 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Division Division, PHE Dte.(Car-1)(Period from 01/07/2024 to 31/12/2024). | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000326/2024-2025 | 3257/MD | 28/06/2024 | 25/12/2024 | M/S TEWARI CONSTRUCTION | 0.86 | 1.81 | 211.78 | 100
116 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) and allied laying work in connection with Jal Jeevan Mission (JJM) at Dahara Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000258/2024-2025 | 3206/MD | 27/06/2024 | 11/08/2024 | M/S AMIT KUMAR GUPTA | 69.58 | 0 | 0 | 0
117 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) and allied laying work in connection with Jal Jeevan Mission (JJM) at Talsur Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000259/2024-2025 | 3207/MD | 27/06/2024 | 28/10/2025 | BEE GEE CONSTRUCTION | 88.37 | 0 | 0 | 65
118 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Nikhrail command area of MAHANADAPUR Water Supply Scheme at Chanchal-I Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Yusuf Sk, Junior Engineer | ORD/000907/2023-2024 | 285/MD | 11/01/2024 | 25/02/2024 | M/S AYUSH BUILDERS | 6.37 | 6.24 | 98.05 | 100
119 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of DAKSHIN MAHENDRAPUR Water Supply Scheme at Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000912/2023-2024 | 385/MD | 17/01/2024 | 01/11/2024 | RAHANUL ALAM | 23.84 | 15.18 | 63.67 | 100
120 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of DAHARA Water Supply Scheme at Harishchandrapur-II Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000913/2023-2024 | 386/MD | 17/01/2024 | 02/03/2024 | PARIJAT RAY | 58.89 | 58.88 | 99.98 | 70
121 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Erection of Jal Jeevan Mission Sign Board at Retrofitting Schemes of Ratua-I & Ratua-II Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/001041/2023-2024 | 894/MD | 28/02/2024 | 06/03/2024 | RABIUL ISLAM | 0.85 | 0.84 | 98.96 | 100
122 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Erection of Jal Jeevan Mission Sign Board at Source Augmentation and Retrofitting Schemes of Habibpur Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/001046/2023-2024 | 899/MD | 28/02/2024 | 06/03/2024 | M/S AYUSH BUILDERS | 0.85 | 0.85 | 99.98 | 100
123 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Erection of Jal Jeevan Mission Sign Board at different Retrofitting Schemes of Gazole Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/001052/2023-2024 | 905/MD | 28/02/2024 | 06/03/2024 | M/S AYUSH BUILDERS | 0.97 | 0.97 | 99.74 | 100
124 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Erection of Jal Jeevan Mission Sign Board at Source Augmentation Schemes and different CWPP sites of Chanchal-I, Ratua-I & Ratua-II Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/001054/2023-2024 | 907/MD | 28/02/2024 | 06/03/2024 | RABIUL ISLAM | 0.6 | 0.59 | 97.92 | 100
125 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Erection of Jal Jeevan Mission Sign Board at Retrofitting Schemes of Englishbazar & Manikchak Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/001055/2023-2024 | 908/MD | 28/02/2024 | 06/03/2024 | PRITAM ENTERPRISE | 0.36 | 0.36 | 99.73 | 100
126 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Erection of Jal Jeevan Mission Sign Board at Retrofitting Schemes of Harishchandrapur-II Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/001040/2023-2024 | 893/MD | 28/02/2024 | 06/03/2024 | RAHANUL ALAM | 0.85 | 0.84 | 99.48 | 100
127 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Erection of Jal Jeevan Mission Sign Board at Retrofitting Schemes of Ratua-I Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/001042/2023-2024 | 895/MD | 28/02/2024 | 06/03/2024 | RABIUL ISLAM | 0.85 | 0.85 | 99.98 | 100
128 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Erection of Jal Jeevan Mission Sign Board at Source Augmentation, Retrofitting Schemes and different CWPP site of Chanchal-II Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/001044/2023-2024 | 897/MD | 28/02/2024 | 06/03/2024 | RABIUL ISLAM | 0.85 | 0.84 | 99.74 | 100
129 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Erection of Jal Jeevan Mission Sign Board at Retrofitting Schemes and different CWPP site of Old Malda Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/001045/2023-2024 | 898/MD | 28/02/2024 | 06/03/2024 | PRITAM ENTERPRISE | 0.85 | 0.84 | 99.74 | 100
130 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Erection of Jal Jeevan Mission Sign Board at Retrofitting Schemes of Harishchandrapur-II Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/001048/2023-2024 | 901/MD | 28/02/2024 | 06/03/2024 | RAHANUL ALAM | 0.97 | 0.96 | 98.96 | 100
131 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Erection of Jal Jeevan Mission Sign Board at Bamongola Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/001049/2023-2024 | 902/MD | 28/02/2024 | 06/03/2024 | M/S AYUSH BUILDERS | 0.97 | 0.97 | 99.73 | 100
132 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Erection of Jal Jeevan Mission Sign Board at different CWPP sites of Chanchal-I, Harishchandrapur-I & Harishchandrapur-II Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/001053/2023-2024 | 906/MD | 28/02/2024 | 06/03/2024 | RAHANUL ALAM | 0.73 | 0.72 | 99.47 | 100
133 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Erection of Jal Jeevan Mission Sign Board at different CWPP site of Gazole & Habibpur Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/001047/2023-2024 | 900/MD | 28/02/2024 | 06/03/2024 | M/S AYUSH BUILDERS | 0.85 | 0.84 | 99.74 | 100
134 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Erection of Jal Jeevan Mission Sign Board at Source Augmentation Schemes of Gazole & Old Malda Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/001050/2023-2024 | 903/MD | 28/02/2024 | 06/03/2024 | M/S AYUSH BUILDERS | 0.97 | 0.96 | 99.48 | 100
135 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Erection of Jal Jeevan Mission Sign Board at different Retrofitting Schemes of Habibpur Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/001051/2023-2024 | 904/MD | 28/02/2024 | 06/03/2024 | M/S AYUSH BUILDERS | 0.97 | 0.97 | 99.74 | 100
136 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Hazzabari Village of Khord Babupur Mouza under KUTUB SAHAR Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000983/2023-2024 | 978/MD | 04/03/2024 | 18/04/2024 | DHRITIPALI | 12.79 | 12.26 | 95.83 | 100
137 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Erection of Jal Jeevan Mission Sign Board at Retrofitting Schemes of Chanchal-I & Harishchandrapur-I Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/001039/2023-2024 | 892/MD | 28/02/2024 | 06/03/2024 | RAHANUL ALAM | 0.85 | 0.85 | 99.99 | 100
138 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Erection of Jal Jeevan Mission Sign Board at Source Augmentation Schemes of Harishchandrapur-I & Harishchandrapur-II Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/001043/2023-2024 | 896/MD | 28/02/2024 | 06/03/2024 | RABIUL ISLAM | 0.85 | 0.84 | 99.48 | 100
139 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for GUN SANKRUL Piped Water Supply Scheme (Gunkrul JL-34) of Old Malda Block in the District of Malda under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000199/2024-2025 | 2931/MD | 10/06/2024 | 25/07/2024 | RABIUL ISLAM | 17.29 | 17.18 | 99.34 | 100
140 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Replacement of 200 mm dia. X 150 mm Dia.) Tubewell No:-2 (130 M Deep) by D.R Rig. Method using P.V.C pipe & Filter including supply of materials at MAHAMMADPUR Water Supply Scheme of Old Malda Block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000451/2024-2025 | 4807/MD | 13/09/2024 | 30/11/2024 | GOBINDA ENTERPRISE | 8.29 | 0 | 0 | 100
141 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Erection of Jal Jeevan Mission Display Board for different schemes and CWPP sites within Chanchal-I, Ratua-I, Ratua-II, Harishchandrapur-I, Harishchandrapur-II, Manikchak, Habibpur, Old Malda and Bamongola block under RWS Malda Sub-Division in the district of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000502/2024-2025 | 5275/MD | 01/10/2024 | 08/10/2024 | S. M. BUILDER | 3.02 | 3.02 | 99.99 | 100
142 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Laying Distribution of DI pipe line along the Bandh and other allied work of KHOPAKATI Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division P.H.E Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000473/2024-2025 | 4987/MD | 27/09/2024 | 11/11/2024 | RABIUL ISLAM | 9.02 | 9.01 | 99.87 | 90
143 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) and Laying of Distribution Pipeline in connection with Jal Jeevan Mission (JJM) at Konar Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000509/2024-2025 | 5384/MD | 04/10/2024 | 07/08/2025 | SOVON KUMAR DAS | 71.34 | 0 | 0 | 100
144 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000100/2023-2024 | 30/MD | 04/01/2024 | 04/01/2024 | Resource Division | 1.23 | 0 | 0 | 0
145 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000113/2023-2024 | 56/MD | 04/01/2024 | 04/01/2024 | Resource Division | 0.31 | 0 | 0 | 0
146 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000110/2023-2024 | 40/MD | 04/01/2024 | 04/01/2024 | Resource Division | 5.85 | 0 | 0 | 0
147 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000102/2023-2024 | 32/MD | 04/01/2024 | 04/01/2024 | Resource Division | 1.42 | 0 | 0 | 0
148 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000111/2023-2024 | 52/MD | 04/01/2024 | 04/01/2024 | Resource Division | 1.93 | 0 | 0 | 0
149 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000176/2023-2024 | 533/MD | 30/01/2024 | 30/01/2024 | Resource Division | 12.94 | 0 | 0 | 0
150 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000011/2024-2025 | 3923/MD | 06/08/2024 | 06/08/2024 | Resource Division | 4.31 | 0 | 0 | 0
151 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000013/2024-2025 | 3926/MD | 06/08/2024 | 06/08/2024 | Resource Division | 5.13 | 0 | 0 | 0
152 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000023/2024-2025 | 5970/MD | 28/11/2024 | 28/11/2024 | Resource Division | 154 | 0 | 0 | 0
153 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000025/2024-2025 | 5973/MD | 28/11/2024 | 28/11/2024 | Resource Division | 154 | 0 | 0 | 0
154 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Diesel driven Vehicle as casual hiring basis for Monitoring of Works as and when called for |  |  | BILL/00763/2024-2025 | BP-2024-25-390 | 05/12/2024 | 05/12/2024 | SUBHANKAR SINGH | 0.26 | 0 | 0 | 0
155 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Augmentation of Head work site Pump House, PUMP House No.-2 ,Earth filling and 2 Nos. Boundary wall at DALLA Water Supply scheme at Habibpur Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000884/2024-2025 | 1123/MD | 21/03/2025 | 05/05/2025 | M/S GHOSH CONSTRUCTION | 9.58 | 0 | 0 | 0
156 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Mihaghat Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000737/2024-2025 | 56 | 08/01/2025 | 15/11/2025 | ASHIS CONSTRUCTION | 26.57 | 0 | 0 | 0
157 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Dahara Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000761/2024-2025 | 80 | 13/01/2025 | 27/02/2025 | M/S AMIT KUMAR GUPTA | 65.21 | 0 | 0 | 1
158 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Extension of Pipe line and replacing of damage A.C/uPVC pipe line by different dia UPVC pipe for DALLA Piped Water Supply Scheme (Dalla JL.-54, Aragachi JL-57) of Habibpur Block in the District of Malda under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000046/2025-2026 | 2252/MD | 21/05/2025 | 19/01/2026 | ACHARYYA CONSTRUCTION | 25.17 | 0 | 0 | 0
159 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Daulatpur Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer ,Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000791/2024-2025 | 356/MD | 30/01/2025 | 28/04/2026 | M/S DYNAMIC CONSTRUCTION | 26.07 | 0 | 0 | 100
160 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing Balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Different Piped Water Supply Scheme under Harishchandrapur-I & II, Chanchal-I & II Block to facilitate Har Ghar Jal under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000098/2025-2026 | 2340/MD | 22/05/2025 | 22/05/2026 | M/S SABANA CONSTRUCTION | 65.08 | 0 | 0 | 0
161 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing Balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Different Locations under Different Piped Water Supply Scheme under Ratua-I & II Block to facilitate Har Ghar Jal under Malda Division, PHE Dte. in the district of Malda. | Mr. Prosanta Mandal, Assistant Engineer | Sudip Kumar Mahata, Junior Engineer,Tapan Haldar, Junior Engineer | ORD/000099/2025-2026 | 2341/MD | 22/05/2025 | 22/05/2026 | M/S TEWARI CONSTRUCTION | 32.63 | 0 | 0 | 0
162 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) and Laying of Distribution Pipeline in connection with Jal Jeevan Mission (JJM) at Khanpur Water Supply Scheme under Chanchal-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation,Yusuf Sk, Junior Engineer | ORD/000165/2025-2026 | 2878/MD | 17/06/2025 | 16/08/2025 | BINA CONSTRUCTION | 61.93 | 0 | 0 | 0
163 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) with additional Laying of Distribution Pipeline at Jalalpur Water Supply Scheme under Chanchal-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer ,Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer,Mr. Susanta Pal, JE_Deputation,Yusuf Sk, Junior Engineer | ORD/000164/2025-2026 | 2877/MD | 17/06/2025 | 14/12/2025 | M/S SABANA CONSTRUCTION | 37.6 | 0 | 0 | 0
164 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Jagannathpur Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000171/2025-2026 | 2888/MD | 17/06/2025 | 26/08/2026 | M/S SABANA CONSTRUCTION | 90.55 | 0 | 0 | 0
165 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Birjabhita Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Prosanta Mandal, Assistant Engineer | Tapan Haldar, Junior Engineer | ORD/000091/2025-2026 | 2333/MD | 22/05/2025 | 21/07/2025 | ACHARYYA CONSTRUCTION | 52.11 | 0 | 0 | 0
166 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Augmentation of work to ensure proper functioning of 250 M³ Capacity 20 Mtr. Staging height RCC Over Head Reservoir of Dalla Water Supply scheme at Habibpur Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000832/2024-2025 | 1060/MD | 19/03/2025 | 18/05/2025 | BENGAL ENGINEERING COMPANY | 8.47 | 0 | 0 | 0
167 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Augmentation work of OHR, Pump House and Boundary Wall of Dakshin Mahendrapur Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000853/2024-2025 | 1046/MD | 18/03/2025 | 15/08/2025 | VISCOUS ENGINEERS PVT. LTD. | 29.12 | 0 | 0 | 0
168 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Augmentation work of OHR, Pump House and Boundary Wall of Daulatnagar Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000854/2024-2025 | 1047/MD | 18/03/2025 | 01/06/2025 | M/S PARIMAL DAS | 30.45 | 0 | 0 | 0
169 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gadai Maharajpur Zone-II Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Prosanta Mandal, Assistant Engineer | Rajashree Banarjee, Junior Engineer | ORD/000086/2025-2026 | 2329/MD | 22/05/2025 | 21/07/2025 | SAHA CONSTRUCTION | 43.45 | 0 | 0 | 0
170 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gadai Maharajpur Zone-III Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Prosanta Mandal, Assistant Engineer,Sri Susanta Saha, Assistant Engineer | Rajashree Banarjee, Junior Engineer,Tapan Haldar, Junior Engineer | ORD/000087/2025-2026 | 2330/MD | 22/05/2025 | 21/07/2025 | BEE GEE CONSTRUCTION | 43.45 | 0 | 0 | 0
171 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gadai Maharajpur Zone-IV Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Prosanta Mandal, Assistant Engineer | Rajashree Banarjee, Junior Engineer,Tapan Haldar, Junior Engineer | ORD/000088/2025-2026 | 2331/MD | 22/05/2025 | 17/01/2026 | M/S SRINJOYEE | 8.7 | 0 | 0 | 0
172 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and Laying with Extension of different diameter (OD) uPVC pipe line under command area at Baherpur Zone-I Water Supply Scheme under Bamangola Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Debasis Pal, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000172/2025-2026 | 2889/MD | 17/06/2025 | 16/08/2025 | M/S SINHA ENTERPRISE | 43.12 | 0 | 0 | 0
173 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Augmentation work of OHR, Pump House and Boundary Wall of Jalalpur Water Supply Scheme at Chanchal-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer ,Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer,Yusuf Sk, Junior Engineer | ORD/000861/2024-2025 | 1054/MD | 18/03/2025 | 29/10/2025 | M/S MOON LIGHT CONSTRUCTION & CO. | 28.53 | 0 | 0 | 0
174 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing Balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Different Locations under Different Piped Water Supply Scheme under Habibpur & Gazole Block to facilitate Har Ghar Jal under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer ,Ziaur Rahaman, Junior Engineer | ORD/000160/2025-2026 | 2880/MD | 17/06/2025 | 17/06/2026 | SAMBHU NATH SARKAR | 52.09 | 0 | 0 | 0
175 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Augmentation work of OHR, Pump House and Boundary Wall of Khanpur-Hulaspur Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer,Yusuf Sk, Junior Engineer | ORD/000182/2025-2026 | 2897/MD | 17/06/2025 | 16/08/2025 | M/S ROY CONSTRUCTION | 31.51 | 0 | 0 | 0
176 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gadai Maharajpur Zone-I Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Prosanta Mandal, Assistant Engineer | Rajashree Banarjee, Junior Engineer | ORD/000085/2025-2026 | 2313/MD | 22/05/2025 | 21/07/2025 | M/S JHA CONSTRUCTION | 52.11 | 0 | 0 | 0
177 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gobarjana Water Supply Scheme under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Prosanta Mandal, Assistant Engineer | Sudip Kumar Mahata, Junior Engineer | ORD/000177/2025-2026 | 2893/MD | 17/06/2025 | 16/08/2025 | J. M. CONSTRUCTION | 26 | 0 | 0 | 0
178 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Bejpura Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000084/2025-2026 | 2282/MD | 21/05/2025 | 05/07/2025 | M I CONSTRUCTION | 30.42 | 0 | 0 | 0
179 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Additional laying of Pipe line for improvement of FHTC functionality by UPVC pipe line and Construction of Boundary wall ,Aproach Raod at HW & 2nd TW site in for PERAPUR Piped Water Supply Scheme at Habibpur Dev. Block in the District of Malda under Malda Division, P.H.E. Dte. | Mr. Sri Biswadip Sengupta, Assistant Engineer ,Mr. Sri Susanta Saha, Assistant Engineer ,Sri Biswadip Sengupta , Assistant Engineer | Sudip Kumar Mahata, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer,Ziaur Rahaman, Junior Engineer | ORD/000237/2025-2026 | 4520/MD | 12/09/2025 | 01/07/2026 | BANIK BROTHERS | 90.01 | 0 | 0 | 0
180 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Erection of 9 nos. display Board on Swajal Gram/Har Ghar Jal Village board at different locations of Chanchal-I and Chanchal-II Block under Malda Division, PHE Dte. in the district of Malda. | Sri Sumit Kumar Ghosh, Assistant Engineer,Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Susanta Pal, JE_Deputation | ORD/000715/2025-2026 | 3688/MD | 28/07/2025 | 24/01/2026 | M D P ENTERPRISE | 0.97 | 0 | 0 | 0
181 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Replacement of damaged UPVC pipe line & repairing of FHTC damaged by Tulsihatta GP For construction of Surface drain at Tulsihatta Zone-I Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Sumit Kumar Ghosh, Assistant Engineer,Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Susanta Pal, JE_Deputation | ORD/000720/2025-2026 | 3711/MD | 29/07/2025 | 25/01/2026 | S K BANIK | 0.78 | 0 | 0 | 100
182 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Erection of 9 nos. display Board on Swajal Gram/Har Ghar Jal Village board at different locations of Bamongola, Old Malda and Englishbazar Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Debasis Pal, Assistant Engineer | Mukaddar Parvage, Junior Engineer,Shreya Das, Junior Engineer | ORD/000713/2025-2026 | 3686/MD | 28/07/2025 | 24/01/2026 | M D P ENTERPRISE | 0.97 | 0 | 0 | 0
183 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Laying of Parallel/ Dedicated Pipeline, Providing Common Manifold & providing Balance FHTC for better Functionality at Magura Zone-I Piped Water Supply Scheme at Ratua-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer | Sudip Kumar Mahata, Junior Engineer | ORD/000228/2025-2026 | 4233/MD | 29/08/2025 | 28/10/2025 | BEE GEE CONSTRUCTION | 51.17 | 0 | 0 | 0
184 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Laying of Parallel/ Dedicated Pipeline, Providing Common Manifold, Land Development & providing Balance FHTC for better Functionality at Mekpur Piped Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Biswadip Sengupta, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000232/2025-2026 | 4236/MD | 29/08/2025 | 28/10/2025 | MANIK CHOUDHURY | 91.14 | 0 | 0 | 0
185 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Erection of 9 nos. display Board on Swajal Gram/Har Ghar Jal Village board at different locations of Gazole, Habibpur and Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | Sri Biswadip Sengupta , Assistant Engineer | Amit Karmakar, Junior Engineer ,Rahul Das Biswas, Junior Engineer | ORD/000712/2025-2026 | 3685/MD | 28/07/2025 | 24/01/2026 | M D P ENTERPRISE | 0.97 | 0 | 0 | 0
186 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Erection of 9 nos. display Board on Swajal Gram/Har Ghar Jal Village board at different locations of Ratua-I and Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Prosanta Mandal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer,Sudip Kumar Mahata, Junior Engineer | ORD/000714/2025-2026 | 3687/MD | 28/07/2025 | 24/01/2026 | M D P ENTERPRISE | 0.97 | 0 | 0 | 0
187 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Erection of 9 nos. display Board on Swajal Gram/Har Ghar Jal Village board at different locations of Harishchandrapur-I and Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Sri Sumit Kumar Ghosh, Assistant Engineer,Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000716/2025-2026 | 3707/MD | 29/07/2025 | 25/01/2026 | M D P ENTERPRISE | 0.97 | 0 | 0 | 0
188 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Augmentation work of OHR, Pump House and Boundary Wall of Bhairabpur Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000851/2024-2025 | 1044/MD | 18/03/2025 | 01/01/2026 | FUTURE | 31.16 | 0 | 0 | 100
189 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Extension of Pipe line and replacing of damage A.C/uPVC pipe line by different dia UPVC pipe for GUNSANKRUL Piped Water Supply Scheme (Jadupur JL.-28, Paschim Banjhapara JL32) of Old Malda Block in the District of Malda under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000047/2025-2026 | 2253/MD | 21/05/2025 | 19/08/2025 | RABIUL ISLAM | 22.84 | 0 | 0 | 100
190 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Detail route survey and design & drawing of distribution network, for providing FHTC in Balupur Zone-I Water Supply Scheme under Malda Division, PHE Dte. in the District of Malda. | Mr. Prosanta Mandal, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/000771/2024-2025 | 271/MD | 28/01/2025 | 12/02/2025 | FUTURE | 0.84 | 0.67 | 79.44 | 100
191 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Detail route survey and design & drawing of distribution network, for providing FHTC in Balupur Zone-II Water Supply Scheme under Malda Division, PHE Dte. in the District of Malda. | Mr. Prosanta Mandal, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/000772/2024-2025 | 272/MD | 28/01/2025 | 12/02/2025 | FUTURE | 0.84 | 0 | 0 | 100
192 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Carrying charges of FTK Materials from Malda District Laboratory to different Blocks Rural Hospitals at English Bazar, Manikchak, Gazole, Habibpur, Bamongola, Old Malda, Ratua-I, Ratua-II, Chanchal-I, Chanchal-II, Harischandrapur-I, Harischandrapur-II, Kaliachak - I, Kaliachak - II, Kaliachak - III Block in the district of Malda under Malda Division, PHE Dte. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000719/2025-2026 | 3710/MD | 29/07/2025 | 25/01/2026 | RAJA CONSTRUCTION | 0.38 | 0 | 0 | 100
193 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Detail route survey and design & drawing of distribution network, for providing FHTC in Balupur Zone-III Water Supply Scheme under Malda Division, PHE Dte. in the District of Malda. | Mr. Prosanta Mandal, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/000773/2024-2025 | 273/MD | 28/01/2025 | 12/02/2025 | FUTURE | 0.84 | 0 | 0 | 100
194 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000004/2025-2026 | 2515/MD | 29/05/2025 | 29/05/2025 | Resource Division | 312.14 | 0 | 0 | 0
195 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Mekpur Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Sri Biswadip Sengupta, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000428/2026-2027 | 3138/MD | 17/08/2026 | 01/10/2026 | MD. TALEB ALI | 52.89 | 0 | 0 | 0
196 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Laying of Parallel/Dedicated Pipeline improvement of functionality and Providing FHTC at Balupur Zone-II under Ratua-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000426/2026-2027 | 3170/MD | 20/08/2026 | 19/10/2026 | SARAJ TRADERS | 46.61 | 0 | 0 | 0
197 | MALDAH |  | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | Retrofitting | Laying of Parallel/Dedicated Pipeline improvement of functionality and Providing FHTC at Balupur Zone-I under Ratua-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000425/2026-2027 | 3169/MD | 20/08/2026 | 19/10/2026 | UTTAM KUMAR GHOSH | 49.63 | 0 | 0 | 0
Total | [13 empty] | 5242.8 | 1813.48 | 34.59