## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Augmentation of Bulbulchandi PWSS. | SM/09422 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000041/2022-2023 | 1586/MD | 28/03/2023 |  | Resource Division | 6.43 | 0 | 0 | 0
2 | MALDAH |  | Malda Mechanical | Augmentation of Bulbulchandi PWSS. | SM/09422 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I and making compound lighting arrangement at T/W no. I of Augmentation of Bulbulchandi Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008161) | Assistant Engineer - II | Junior Engineer-03 | ORD/000256/2023-2024 | 2229/MLMD | 18/07/2023 | 15/11/2023 | SUDIP DEY | 14.67 | 0 | 0 | 0
3 | MALDAH |  | Malda Division | Augmentation of Bulbulchandi PWSS. | SM/09422 | Augmentation | Submission of Bill for Hire Charges & HSD & Mobil charges of Vehicle No. - WB 04-H-8254 for the month of MAY, JUNE, JULY 2023 under Malda Division, PHE Dte. |  |  | BILL/00314/2023-2024 | BP-2023-24-157 | 18/08/2023 |  | SHABNAM ARA | 1.18 | 0 | 0 | 0
4 | MALDAH |  | Malda Division | Augmentation of Bulbulchandi PWSS. | SM/09422 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000003/2022-2023 | 1105/MD | 17/05/2022 |  | Resource Division | 81.12 | 0 | 0 | 0
5 | MALDAH |  | Malda Division | Augmentation of Bulbulchandi PWSS. | SM/09422 | Augmentation | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 110 Mtr. Deep Big dia Tube well (1 Nos.) at BULBULCHANDI Water Supply Scheme under Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000015/2023-2024 | 1672/MD | 18/04/2023 | 18/05/2023 | A. L. ENGINEERING SOLUTION | 8.95 | 8.64 | 96.47 | 100
6 | MALDAH |  | Malda Mechanical | Augmentation of Bulbulchandi PWSS. | SM/09422 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation for T/W no.- II of Bulbulchandi Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008161) | Assistant Engineer - II | Junior Engineer-03 | ORD/000257/2023-2024 | 2230/MLMD | 18/07/2023 | 15/11/2023 | JOY MAA SANTOSHI ENTERPRISE. | 8.02 | 5.09 | 63.46 | 86
7 | MALDAH |  | Malda Mechanical | Augmentation of Bulbulchandi PWSS. | SM/09422 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation for T/W No.- III of Bulbulchandi Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008161) | Assistant Engineer - II | Junior Engineer-03 | ORD/001099/2022-2023 | 596/MLMD | 30/03/2023 | 28/07/2023 | PABITRA MANDAL | 10.76 | 10.73 | 99.68 | 70
8 | MALDAH |  | Malda Division | Augmentation of Bulbulchandi PWSS. | SM/09422 | Augmentation | Repairing of boundary wall and Land Development work corresponding to Tube Well No. 3 at BULBULCHANDI Piped Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000947/2023-2024 | 657/MD | 08/02/2024 | 24/03/2024 | M/S GHOSH CONSTRUCTION | 2.5 | 2.49 | 99.79 | 100
9 | MALDAH |  | Malda Division | Augmentation of Bulbulchandi PWSS. | SM/09422 | Augmentation | Formal work order for the work of Augmentation of Bulbulchandi Piped water supply scheme for the work of Geotechnical Study,construction of 700 Cum RCC OHR,Laying Distribution of pipe line and providing Functional Household Tap connection (FHTC) within Habibpur Block in the District of Malda under Malda Division, PH Engg Dte. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000006/2022-2023 | 1125/MD | 19/05/2022 | 19/05/2023 | ACQUA CONSTRUCTION CONSORTIUM | 551.54 | 446.27 | 80.91 | 85
10 | MALDAH |  | Malda Division | Augmentation of Bulbulchandi PWSS. | SM/09422 | Augmentation | Dismentling of Concrete road and Construction the same at different places of road connecting to LDS of BULBULCHANDI Water Supply Scheme ( Mouza - Bulbulchandi, Soladanga) at Habibpur Dev. Block under Malda Division, P.H.E.Dte. In the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer,Ziaur Rahaman, Junior Engineer | ORD/000302/2024-2025 | 3448/MD | 11/07/2024 | 25/08/2024 | ACQUA CONSTRUCTION CONSORTIUM | 47.09 | 0 | 0 | 0
Total | [13 empty] | 732.26 | 473.22 | 64.63