## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Augmentation of Tilasan Piped water supply scheme | SM/09567 | Augmentation | Acceptance cum formal work order for Design, Preparation & Submission of DPR as per existing route survey data for Augmentation of TILASAN Piped Water Supply Scheme under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Biswajit Gosh, Junior Engineer,Shreya Das, Junior Engineer | ORD/000539/2021-2022 | 2693/MD | 09/09/2021 | 16/09/2021 | RADIANT | 1.25 | 1.25 | 100 | 1
2 | MALDAH |  | Malda Division | Augmentation of Tilasan Piped water supply scheme | SM/09567 | Augmentation | Formal work order for Augmentation of TILASAN Piped water supply scheme for the work of Geotechnical Study,construction of 200 Cum RCC OHR,Laying Distribution of pipe line and providing Functional Household Tap connection (FHTC) within Habibpur Block under Malda Division PH Engg.Dte. In the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Biswajit Gosh, Junior Engineer,Mukaddar Parvage, Junior Engineer,Shreya Das, Junior Engineer | ORD/000004/2022-2023 | 996/MD | 22/04/2022 | 22/04/2023 | UTTAM KUMAR GHOSH | 180.23 | 163.53 | 90.73 | 100
3 | MALDAH |  | Malda Division | Augmentation of Tilasan Piped water supply scheme | SM/09567 | Augmentation | Acceptance cum formal work order for Laying of Rising Main including connection of Pump No-1 & Pump No 2 and by pass arrangement for TILASAN Water Supply Scheme at Habibpur Dev. Block under Malda Division, PHE Dte. in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Biswajit Gosh, Junior Engineer,Shreya Das, Junior Engineer | ORD/000030/2022-2023 | 1307/MD | 01/06/2022 | 01/07/2022 | M/S EHAN ENTERPRISE | 4.44 | 4.43 | 99.69 | 1
4 | MALDAH |  | Central Drilling | Augmentation of Tilasan Piped water supply scheme | SM/09567 | Augmentation | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT TILASAN, HABIBPUR BLOCK, MALDA DISTRICT UNDER CDD, PHE DTE. |  |  | ORD/000241/2022-2023 | 347/CMSD-I | 25/07/2022 | 09/08/2022 | CHANDA ENTERPRISE | 4.69 | 4.43 | 94.41 | 0
5 | MALDAH |  | Central Drilling | Augmentation of Tilasan Piped water supply scheme | SM/09567 | Augmentation | SUPPLY & DELIVERY OF CONSUMBLES WITH OTHER WORKS AT SITEFOR CONSTRUCTION OF TUBE WELL AT JAGJIBANPUR, HABIBPUR BLOCK, MALDA DISTRICT UNDER CDD, PHE DTE. |  |  | ORD/000242/2022-2023 | 346/CMSD-I | 25/07/2022 | 09/08/2022 | CHANDA ENTERPRISE | 4.66 | 1.4 | 29.95 | 0
6 | MALDAH |  | Malda Division | Augmentation of Tilasan Piped water supply scheme | SM/09567 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000005/2022-2023 | 1107/MD | 17/05/2022 | 17/05/2022 | Resource Division | 16.55 | 0 | 0 | 0
7 | MALDAH |  | Malda Division | Augmentation of Tilasan Piped water supply scheme | SM/09567 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000010/2022-2023 | 1461/MD | 22/06/2022 | 22/06/2022 | Resource Division | 6.78 | 0 | 0 | 0
8 | MALDAH |  | Malda Mechanical | Augmentation of Tilasan Piped water supply scheme | SM/09567 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation for T/W no.- I of Tilason Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/009047) | Assistant Engineer - II | Junior Engineer-03,Junior Engineer-06 | ORD/000253/2023-2024 | 2226/MLMD | 18/07/2023 | 03/11/2025 | SUBRATA KUMAR DAS. | 10.08 | 6.06 | 60.08 | 30
9 | MALDAH |  | Malda Mechanical | Augmentation of Tilasan Piped water supply scheme | SM/09567 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation for T/W no.- II of Tilason Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/009047) | Assistant Engineer - II | Junior Engineer-03,Junior Engineer-06 | ORD/000254/2023-2024 | 2227/MLMD | 18/07/2023 | 10/01/2025 | JOY ENTERPRISE. | 7.57 | 0 | 0 | 25
10 | MALDAH |  | Malda Division | Augmentation of Tilasan Piped water supply scheme | SM/09567 | Augmentation | Acceptance cum formal work order for Dismantling of concrete road and Construction the same at different places of road connecting to LDS of TILASAN Piped Water Supply Scheme at Habibpur Dev. Block, under Malda Division, P.H.E. Dte. in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000081/2023-2024 | 2177/MD | 07/06/2023 | 07/07/2023 | UTTAM KUMAR GHOSH | 21.68 | 21.68 | 99.99 | 100
11 | MALDAH |  | Malda Division | Augmentation of Tilasan Piped water supply scheme | SM/09567 | Augmentation | Acceptance cum formal work order for Providing Functional House hold Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under Command area of Augmentation of TILASAN Piped Water Supply Scheme at Habibpur Dev. Block, under Malda Division, P.H.E. Dte. in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000082/2023-2024 | 2178//MD | 07/06/2023 | 07/07/2023 | UTTAM KUMAR GHOSH | 13.35 | 12.19 | 91.32 | 100
12 | MALDAH |  | Malda Division | Augmentation of Tilasan Piped water supply scheme | SM/09567 | Augmentation | Acceptance cum formal work order for Dismentling of Concrete road and Construction the same from Head Work site to 2nd Tube Well Site of TILASAN Water Supply Scheme at Habibpur Dev. Block under Malda Division, P.H.E. Dte. In the district of Malda. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000785/2022-2023 | 1443/MD | 29/03/2023 | 28/04/2023 | M/S EHAN ENTERPRISE | 3.15 | 3.15 | 100 | 100
13 | MALDAH |  | Malda Division | Augmentation of Tilasan Piped water supply scheme | SM/09567 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000043/2022-2023 | 1587/MD | 28/03/2023 | 28/03/2023 | Resource Division | 0.41 | 0 | 0 | 0
14 | MALDAH |  | Central Drilling | Augmentation of Tilasan Piped water supply scheme | SM/09567 | Augmentation | Hiring of Diesel Driven Motor Cab (BS-IV & Above) having contract carriage permit along with driver for the office of the Calcutta Mecha nical Sub Division-I(D), CDD, P.H.Engineering Dte. For Supervision of JJM related works. | Driller In Charge | Junior Engineer | ORD/000220/2023-2024 | 13/CMSD-I(D) | 15/01/2024 | 31/07/2024 | AJAY KUMAR | 0.94 | 1.04 | 110.17 | 15
15 | MALDAH |  | Malda Division | Augmentation of Tilasan Piped water supply scheme | SM/09567 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) and Laying of 90 mm dia (OD) uPVC Pipeline under command area of AUGMENTATION OF TILASAN Water Supply Scheme at Habibpur Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/001036/2023-2024 | 1262/MD | 15/03/2024 | 24/11/2024 | SATTWIK CONSTRUCTION | 7.44 | 6.93 | 93.12 | 100
16 | MALDAH |  | Malda Division | Augmentation of Tilasan Piped water supply scheme | SM/09567 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000055/2025-2026 | 5598/MD | 30/10/2025 | 30/10/2025 | Resource Division | 2.88 | 0 | 0 | 0
Total | [13 empty] | 286.12 | 226.09 | 79.02