## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Augmentation of Deotala Water Supply Scheme | SM/09986 | Augmentation | Acceptance cum formal work order for Route survey for distribution network design for augmentation of Deotala Water Supply Scheme in Gazole block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Biswajit Gosh, Junior Engineer | ORD/000148/2021-2022 | 1746/MD | 15/06/2021 | 29/06/2021 | HORIZEN | 2.86 | 1.78 | 62.16 | 1
2 | MALDAH |  | Malda Mechanical | Augmentation of Deotala Water Supply Scheme | SM/09986 | Augmentation | Supply, installation and commissioning of electro-mechanical components of T/W no. II and making compound lighting arrangement at T/W no. I of Augmentation of Deotala Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/005108) | Assistant Engineer - II |  | ORD/000607/2023-2024 | 2723/MLMD | 14/08/2023 | 10/02/2024 | JIBU SINGHA | 14.75 | 0 | 0 | 0
3 | MALDAH |  | Malda Division | Augmentation of Deotala Water Supply Scheme | SM/09986 | Augmentation | Acceptance cum formal work order for Laying of Rising main with connection between 1st Tube well and 3 rd Tube well and condtructtion of standpost for DEOTALA Water Supply Scheme under Malda Division, PHE Dte. in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Biswajit Gosh, Junior Engineer | ORD/000031/2022-2023 | 1308/MD | 01/06/2022 | 01/07/2022 | JIBON GHOSH | 4.43 | 2.05 | 46.13 | 0
4 | MALDAH |  | Malda Division | Augmentation of Deotala Water Supply Scheme | SM/09986 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000004/2022-2023 | 1106/MD | 17/05/2022 | 17/05/2022 | Resource Division | 37.39 | 0 | 0 | 0
5 | MALDAH |  | Malda Division | Augmentation of Deotala Water Supply Scheme | SM/09986 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000042/2022-2023 | 1585/MD | 28/03/2023 | 28/03/2023 | Resource Division | 2.3 | 0 | 0 | 0
6 | MALDAH |  | Malda Division | Augmentation of Deotala Water Supply Scheme | SM/09986 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000194/2023-2024 | 816/MD | 21/02/2024 | 21/02/2024 | Resource Division | 45.08 | 0 | 0 | 0
7 | MALDAH |  | Malda Division | Augmentation of Deotala Water Supply Scheme | SM/09986 | Augmentation | Formal work order for Augmentation of DEOTALA Piped water supply scheme for the work of Geotechnical Study,construction of 500 Cum RCC OHR,Laying Distribution of pipe line and providing Functional Household Tap connection (FHTC) within Gazole Dev Block under Malda Division PH Engg Dte. In the District of Malda | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000003/2022-2023 | 868/MD | 08/04/2022 | 29/07/2025 | MAHAVIR PUMPS MANUFACTURING PVT. LTD. | 460.03 | 178.96 | 38.9 | 50
8 | MALDAH |  | Malda Division | Augmentation of Deotala Water Supply Scheme | SM/09986 | Augmentation | Laying of Rising Main including Specials and Valves for Deotala Piped Water Supply Scheme at Deotala Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000889/2023-2024 | 163/MD | 08/01/2024 | 01/04/2025 | M I CONSTRUCTION | 14.99 | 0 | 0 | 100
9 | MALDAH |  | Malda Division | Augmentation of Deotala Water Supply Scheme | SM/09986 | Augmentation | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Deotala Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000718/2024-2025 | 6409/MD | 19/12/2024 | 01/10/2025 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 26.07 | 0 | 0 | 0
10 | MALDAH |  | Malda Division | Augmentation of Deotala Water Supply Scheme | SM/09986 | Augmentation | Augmentation of Head Work Site pump House at DEOTALA Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000117/2025-2026 | 2468/MD | 28/05/2025 | 12/07/2025 | S. R. ENTERPRISE | 2.06 | 0 | 0 | 100
11 | MALDAH |  | Malda Division | Augmentation of Deotala Water Supply Scheme | SM/09986 | Augmentation | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division Division, PHE Dte. (Car-2) (Period from 01/03/2025 to 31/08/2025). | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/001038/2024-2025 | 752/MD | 27/02/2025 | 27/08/2025 | SINGH BROTHERS | 0.86 | 0 | 0 | 0
12 | MALDAH |  | Malda Division | Augmentation of Deotala Water Supply Scheme | SM/09986 | Augmentation | Sinking of 200mm (all through) Big dia. Tube Well, Construction of Pump House, Boundary wall and allied works of Deotala PWSS under Gazole Block under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Biswadip Sengupta, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000233/2025-2026 | 4237/MD | 29/08/2025 | 12/11/2025 | HARUN ALL RASHID & BROTHERS | 55.58 | 0 | 0 | 0
13 | MALDAH |  | Malda Division | Augmentation of Deotala Water Supply Scheme | SM/09986 | Augmentation | Dedicated Pipe laying for better Functionality and Providing Balance FHTC for Deotala Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000217/2025-2026 | 3778/MD | 04/08/2025 | 03/10/2025 | MANIK CHOUDHURY | 65.09 | 0 | 0 | 0
Total | [13 empty] | 731.49 | 182.78 | 24.99