## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | AUGMENTATION OF MALATIPUR PWSS | SM/09987 | Augmentation | Soil Investigation and design of substructure for Over Head Reservoirs for MALATIPUR Piped Water Supply Scheme at Chanchal-II Dev. Block under Malda Division, PHE Dte. In the district of Malda. |  |  | BILL/00489/2022-2023 | BP-2022-23-198 | 09/03/2023 |  | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR. | 2.95 | 0 | 0 | 0
2 | MALDAH |  | Malda Division | AUGMENTATION OF MALATIPUR PWSS | SM/09987 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000035/2023-2024 | 1801/MD | 27/04/2023 |  | Resource Division | 0.59 | 0 | 0 | 0
3 | MALDAH |  | Malda Mechanical | AUGMENTATION OF MALATIPUR PWSS | SM/09987 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation for T/W No.- II of Malatipur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008173) | Assistant Engineer - II | Junior Engineer-05 | ORD/001098/2022-2023 | 415/MLMD | 14/03/2023 | 12/07/2023 | PABITRA MANDAL | 10.28 | 10.11 | 98.3 | 1
4 | MALDAH |  | Malda Mechanical | AUGMENTATION OF MALATIPUR PWSS | SM/09987 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation for T/W no.- III of Malatipur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008173) | Assistant Engineer - II | Junior Engineer-05 | ORD/000255/2023-2024 | 2228/MLMD | 18/07/2023 | 15/11/2023 | EMCON. | 12.51 | 0 | 0 | 0
5 | MALDAH |  | Malda Division | AUGMENTATION OF MALATIPUR PWSS | SM/09987 | Augmentation | Submission of Bill for Hire Charges & HSD & Mobil charges of Vehicle No. - WB61A/3084 for the month of April 2023 |  |  | BILL/00234/2023-2024 | BP-2023-24-115 | 20/07/2023 |  | SHYAMAL KUMAR MAITRA | 0.31 | 0 | 0 | 0
6 | MALDAH |  | Malda Division | AUGMENTATION OF MALATIPUR PWSS | SM/09987 | Augmentation | Submission of bill for hire charges & HSD & Mobil charges of vehicle No. WB61A/3084 for the month of May-2023. |  |  | BILL/00294/2023-2024 | BP-2023-24-147 | 10/08/2023 |  | SHYAMAL KUMAR MAITRA | 0.36 | 0 | 0 | 0
7 | MALDAH |  | Malda Division | AUGMENTATION OF MALATIPUR PWSS | SM/09987 | Augmentation | Bill for reimbursement of cost of Diesel and Mobile in respect of hired Vehicle Car No. WB65C/6570 for the month of July2023. |  |  | BILL/00369/2023-2024 | BP-2023-24-195 | 07/09/2023 |  | UTTAM KUMAR GHOSH | 0.4 | 0 | 0 | 0
8 | MALDAH |  | Malda Division | AUGMENTATION OF MALATIPUR PWSS | SM/09987 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2022-2023 | 1207/MD | 24/05/2022 |  | Resource Division | 0.61 | 0 | 0 | 0
9 | MALDAH |  | Malda Division | AUGMENTATION OF MALATIPUR PWSS | SM/09987 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000138/2023-2024 | 113/MD | 05/01/2024 |  | Resource Division | 8.6 | 0 | 0 | 0
10 | MALDAH |  | Malda Division | AUGMENTATION OF MALATIPUR PWSS | SM/09987 | Augmentation | Formal work order for the work of Construction of 400 M3 Capacity OHR with FHTC (Mouza-Harishpara, Kashipara and Gobindapara) of MALATIPUR Piped Water Supply Scheme at Chanchal-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000311/2023-2024 | 2914/MD | 31/07/2023 | 27/01/2024 | DEEP CONSTRUCTION | 183.27 | 52.03 | 28.39 | 61
11 | MALDAH |  | Malda Division | AUGMENTATION OF MALATIPUR PWSS | SM/09987 | Augmentation | Formal work order for the work of Laying of Distribution pipe line in connection with Augmentation of Malatipur Pipe Water Supply Scheme at Chanchal-II Block in the District of Malda under Malda Division P.H.E. Dte. (2ND Call) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000132/2022-2023 | 1788/MD | 01/08/2022 | 30/09/2022 | M/S MAA TARA CONSTRUCTION | 300.02 | 202.1 | 67.36 | 76
12 | MALDAH |  | Malda Mechanical | AUGMENTATION OF MALATIPUR PWSS | SM/09987 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components at T/W no. I of Augmentation of Malatipur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008173) | Assistant Engineer - II | Junior Engineer-05 | ORD/000247/2023-2024 | 2264/MLMD | 18/07/2023 | 16/10/2023 | M/S DYNAMIC ENGINEERS ENTERPRISE.... | 11.11 | 3.77 | 33.99 | 68
13 | MALDAH |  | Malda Division | AUGMENTATION OF MALATIPUR PWSS | SM/09987 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000012/2024-2025 | 3925/MD | 06/08/2024 |  | Resource Division | 8.01 | 0 | 0 | 0
Total | [13 empty] | 539.01 | 268.01 | 49.72