## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | AUGMENTATION OF MALATIPUR PWSS | SM/09987 | Augmentation | Formal work order for the work of Laying of Distribution pipe line in connection with Augmentation of Malatipur Pipe Water Supply Scheme at Chanchal-II Block in the District of Malda under Malda Division P.H.E. Dte. (2ND Call) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000132/2022-2023 | 1788/MD | 01/08/2022 | 01/11/2024 | M/S MAA TARA CONSTRUCTION | 300.02 | 208.69 | 69.56 | 85
2 | MALDAH |  | Malda Division | AUGMENTATION OF MALATIPUR PWSS | SM/09987 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2022-2023 | 1207/MD | 24/05/2022 | 24/05/2022 | Resource Division | 0.61 | 0 | 0 | 0
3 | MALDAH |  | Malda Mechanical | AUGMENTATION OF MALATIPUR PWSS | SM/09987 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation for T/W no.- III of Malatipur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008173) | Assistant Engineer - II | Junior Engineer-05 | ORD/000255/2023-2024 | 2228/MLMD | 18/07/2023 | 15/11/2023 | EMCON. | 12.51 | 0 | 0 | 0
4 | MALDAH |  | Malda Mechanical | AUGMENTATION OF MALATIPUR PWSS | SM/09987 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components at T/W no. I of Augmentation of Malatipur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008173) | Assistant Engineer - II | Junior Engineer-05 | ORD/000247/2023-2024 | 2264/MLMD | 18/07/2023 | 16/10/2023 | M/S DYNAMIC ENGINEERS ENTERPRISE.... | 11.11 | 7.55 | 67.97 | 68
5 | MALDAH |  | Malda Division | AUGMENTATION OF MALATIPUR PWSS | SM/09987 | Augmentation | Formal work order for the work of Construction of 400 M3 Capacity OHR with FHTC (Mouza-Harishpara, Kashipara and Gobindapara) of MALATIPUR Piped Water Supply Scheme at Chanchal-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000311/2023-2024 | 2914/MD | 31/07/2023 | 27/03/2026 | DEEP CONSTRUCTION | 183.27 | 104.05 | 56.78 | 100
6 | MALDAH |  | Malda Mechanical | AUGMENTATION OF MALATIPUR PWSS | SM/09987 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation for T/W No.- II of Malatipur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008173) | Assistant Engineer - II | Junior Engineer-05 | ORD/001098/2022-2023 | 415/MLMD | 14/03/2023 | 12/07/2023 | PABITRA MANDAL | 10.28 | 10.11 | 98.3 | 100
7 | MALDAH |  | Malda Division | AUGMENTATION OF MALATIPUR PWSS | SM/09987 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000035/2023-2024 | 1801/MD | 27/04/2023 | 27/04/2023 | Resource Division | 0.59 | 0 | 0 | 0
8 | MALDAH |  | Malda Division | AUGMENTATION OF MALATIPUR PWSS | SM/09987 | Augmentation | Submission of bill for hire charges & HSD & Mobil charges of vehicle No. WB61A/3084 for the month of May-2023. |  |  | BILL/00294/2023-2024 | BP-2023-24-147 | 10/08/2023 | 10/08/2023 | SHYAMAL KUMAR MAITRA | 0.36 | 0 | 0 | 0
9 | MALDAH |  | Malda Division | AUGMENTATION OF MALATIPUR PWSS | SM/09987 | Augmentation | Bill for reimbursement of cost of Diesel and Mobile in respect of hired Vehicle Car No. WB65C/6570 for the month of July2023. |  |  | BILL/00369/2023-2024 | BP-2023-24-195 | 07/09/2023 | 07/09/2023 | UTTAM KUMAR GHOSH | 0.4 | 0 | 0 | 0
10 | MALDAH |  | Malda Division | AUGMENTATION OF MALATIPUR PWSS | SM/09987 | Augmentation | Submission of Bill for Hire Charges & HSD & Mobil charges of Vehicle No. - WB61A/3084 for the month of April 2023 |  |  | BILL/00234/2023-2024 | BP-2023-24-115 | 20/07/2023 | 20/07/2023 | SHYAMAL KUMAR MAITRA | 0.31 | 0 | 0 | 0
11 | MALDAH |  | Malda Division | AUGMENTATION OF MALATIPUR PWSS | SM/09987 | Augmentation | Soil Investigation and design of substructure for Over Head Reservoirs for MALATIPUR Piped Water Supply Scheme at Chanchal-II Dev. Block under Malda Division, PHE Dte. In the district of Malda. |  |  | BILL/00489/2022-2023 | BP-2022-23-198 | 09/03/2023 | 09/03/2023 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR. | 2.95 | 0 | 0 | 0
12 | MALDAH |  | Malda Division | AUGMENTATION OF MALATIPUR PWSS | SM/09987 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000138/2023-2024 | 113/MD | 05/01/2024 | 05/01/2024 | Resource Division | 8.6 | 0 | 0 | 0
13 | MALDAH |  | Malda Division | AUGMENTATION OF MALATIPUR PWSS | SM/09987 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000012/2024-2025 | 3925/MD | 06/08/2024 | 06/08/2024 | Resource Division | 8.01 | 0 | 0 | 0
14 | MALDAH |  | Malda Division | AUGMENTATION OF MALATIPUR PWSS | SM/09987 | Augmentation | Diesel driven Vehicle as casual hiring basis for Monitoring of Works as and when called for on daily basis |  |  | BILL/00765/2024-2025 | BP-2023-24-392 | 04/12/2024 | 04/12/2024 | PRASENJIT GHOSH | 0.28 | 0 | 0 | 0
15 | MALDAH |  | Malda Division | AUGMENTATION OF MALATIPUR PWSS | SM/09987 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Kharba Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer ,Sri Sumit Kumar Ghosh, Assistant Engineer,Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000169/2025-2026 | 7811/MD | 11/06/2025 | 10/08/2025 | HANNAN BUILDERS PVT. LTD. | 130.04 | 0 | 0 | 0
16 | MALDAH |  | Malda Division | AUGMENTATION OF MALATIPUR PWSS | SM/09987 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Malatipur Water Supply Scheme under Chanchal-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Yusuf Sk, Junior Engineer | ORD/000166/2025-2026 | 2879/MD | 17/06/2025 | 16/08/2025 | SAHA CONSTRUCTION | 56.44 | 0 | 0 | 0
17 | MALDAH |  | Malda Division | AUGMENTATION OF MALATIPUR PWSS | SM/09987 | Augmentation | Erection of Property board related to Jal Jeevan Mission works of Kshempur & Malatipur GP under Chanchal-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000947/2024-2025 | 636/MD | 19/02/2025 | 26/02/2025 | BIDYUT MAHALDAR | 0.82 | 0 | 0 | 0
18 | MALDAH |  | Malda Division | AUGMENTATION OF MALATIPUR PWSS | SM/09987 | Augmentation | Augmentation Pump House and Boundary Wall of Malatipur Water Supply Scheme at Chanchal-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation,Yusuf Sk, Junior Engineer | ORD/000130/2025-2026 | 2492/MD | 28/05/2025 | 11/08/2025 | CHARU CONSTRUCTION | 16.65 | 0 | 0 | 0
Total | [13 empty] | 743.24 | 330.39 | 44.45