## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Augmentation of Bhaluka Fatepur Piped water supply scheme | SM/10137 | Augmentation | Acceptance cum formal work order for Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at 4th Tube Well site of Bhaluka Fatepur Water Supply Scheme under Malda Division, PHE Dte. In the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000025/2022-2023 | 1192/MD | 24/05/2022 | 24/06/2022 | M/S GULFAM CONSTRUCTION. | 4.78 | 0 | 0 | 0
2 | MALDAH |  | Malda Division | Augmentation of Bhaluka Fatepur Piped water supply scheme | SM/10137 | Augmentation | Acceptance cum formal work order for Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at 3rd Tube Well site of Bhaluka Fatepur Water Supply Scheme under Malda Division, PHE Dte. In the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000026/2022-2023 | 1193/MD | 24/05/2022 | 24/06/2022 | M/S SRINJOYEE | 4.78 | 0 | 0 | 0
3 | MALDAH |  | Malda Division | Augmentation of Bhaluka Fatepur Piped water supply scheme | SM/10137 | Augmentation | Acceptance cum formal work order for Sinking of 02 (Two) Nos. 150mm. Dia. x 100mm. Big dia. Tube Well 150 Mtr. deep by Direct Rotary method using UPVC pipe & Strainer in connection with Augmentation of Bhaluka Fatepur Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000046/2022-2023 | 1395/MD | 14/06/2022 | 14/07/2022 | A. L. ENGINEERING SOLUTION | 10 | 0 | 0 | 0
4 | MALDAH |  | Malda Division | Augmentation of Bhaluka Fatepur Piped water supply scheme | SM/10137 | Augmentation | Continuation work order for Route survey for distribution network design for augmentation of Bhaluka Fatepur Water Supply Scheme in Harischandrapur-II block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000695/2021-2022 | 1840/MD | 30/06/2021 | 14/07/2021 | INDRANIL DUTTA & ACCOCIATES | 1.45 | 0 | 0 | 0
5 | MALDAH |  | Malda Mechanical | Augmentation of Bhaluka Fatepur Piped water supply scheme | SM/10137 | Augmentation | Supply, installation & commissioning of electro-mechanical components at T/W no. I & II of Augmentation of Bhaluka Fatepur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. | Assistant Engineer - II | Junior Engineer-05 | ORD/001058/2022-2023 | 267/MLMD | 24/02/2023 | 25/05/2023 | SHREE BISHNU CONSTRUCTION | 7.97 | 5.61 | 70.37 | 70
6 | MALDAH |  | Malda Division | Augmentation of Bhaluka Fatepur Piped water supply scheme | SM/10137 | Augmentation | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Augmentation of BHALUKA FATEPUR Piped Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. In the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000083/2023-2024 | 2173/MD | 07/06/2023 | 07/07/2023 | M/S EHAN ENTERPRISE | 11.04 | 0 | 0 | 0
7 | MALDAH |  | Malda Division | Augmentation of Bhaluka Fatepur Piped water supply scheme | SM/10137 | Augmentation | Formal work order for the work of Laying of Distribution pipe line in connection with Augmentation of Bhaluka Fatepur Pipe Water Supply Scheme at Harishchandrapur-II Block in the District of Malda under Malda Division P.H.E. Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000136/2022-2023 | 1828/MD | 04/08/2022 | 02/11/2022 | GHOSH BROTHERS | 348.1 | 309.95 | 89.04 | 68
8 | MALDAH |  | Malda Division | Augmentation of Bhaluka Fatepur Piped water supply scheme | SM/10137 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000012/2022-2023 | 1871/MD | 16/08/2022 | 16/08/2022 | Resource Division | 65.9 | 0 | 0 | 0
9 | MALDAH |  | Malda Division | Augmentation of Bhaluka Fatepur Piped water supply scheme | SM/10137 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000026/2023-2024 | 1607/MD | 11/04/2023 | 11/04/2023 | Resource Division | 29.16 | 0 | 0 | 0
10 | MALDAH |  | Malda Division | Augmentation of Bhaluka Fatepur Piped water supply scheme | SM/10137 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000037/2023-2024 | 1801 | 27/04/2023 | 27/04/2023 | Resource Division | 59.54 | 0 | 0 | 0
11 | MALDAH |  | Malda Division | Augmentation of Bhaluka Fatepur Piped water supply scheme | SM/10137 | Augmentation | Soil Investigation and design of substructure for Over Head Reservoirs for BHALUKA FATEPUR Piped Water Supply Scheme at Harishchandapur-II Dev. Block under Malda Division, PHE Dte. In the district of Malda. |  |  | BILL/00486/2022-2023 | BP-2022-23-192 | 09/03/2023 | 09/03/2023 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR. | 2.95 | 0 | 0 | 0
12 | MALDAH |  | Malda Mechanical | Augmentation of Bhaluka Fatepur Piped water supply scheme | SM/10137 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation for T/W No.- III & IV of Bhaluka Fatepur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/009046) | Assistant Engineer - II | Junior Engineer-05 | ORD/000259/2023-2024 | 2232/MLMD | 19/07/2023 | 29/10/2025 | A.K. SIKDAR | 21.58 | 16.52 | 76.58 | 77
13 | MALDAH |  | Malda Division | Augmentation of Bhaluka Fatepur Piped water supply scheme | SM/10137 | Augmentation | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No 2 at BHALUKA FATEPUR Piped Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000971/2023-2024 | 830/MD | 21/02/2024 | 06/04/2024 | OLI CONSTRUCTION | 4.17 | 0 | 0 | 0
14 | MALDAH |  | Malda Mechanical | Augmentation of Bhaluka Fatepur Piped water supply scheme | SM/10137 | Augmentation | New service connection at BHALUKA- FAFATEPUR PWSS T/W NO III Under EE/MLMD PHE DTE DIST. Malda.( Bhaluka c.c.c) |  |  | BILL/01170/2024-2025 | BP-2024-25-351 | 24/06/2024 | 24/06/2024 | W.B.S.E.D.C.LTD | 9.85 | 0 | 0 | 0
15 | MALDAH |  | Malda Division | Augmentation of Bhaluka Fatepur Piped water supply scheme | SM/10137 | Augmentation | Formal work order for the work of Construction of 700 M3 Capacity OHR with FHTC (Mouza-Bhaluka) of Bhaluka Fatepur Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000354/2023-2024 | 3020/MD | 08/08/2023 | 19/07/2025 | GHOSH BROTHERS | 283.26 | 0 | 0 | 0
16 | MALDAH |  | Malda Division | Augmentation of Bhaluka Fatepur Piped water supply scheme | SM/10137 | Augmentation | Laying of Rising Main including Specials and Valves for BHALUKA FATEPUR Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000962/2023-2024 | 715/MD | 09/02/2024 | 25/03/2024 | J. M. CONSTRUCTION | 14.06 | 2.02 | 14.39 | 80
17 | MALDAH |  | Malda Division | Augmentation of Bhaluka Fatepur Piped water supply scheme | SM/10137 | Augmentation | Acceptance cum formal work order for Route survey for distribution network design for augmentation of Bhaluka Fatepur Water Supply Scheme in Harischandrapur-II block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000152/2021-2022 | 1750/MD | 15/06/2021 | 29/06/2021 | INDRANIL DUTTA & ACCOCIATES | 2.86 | 2.86 | 100 | 1
18 | MALDAH |  | Malda Division | Augmentation of Bhaluka Fatepur Piped water supply scheme | SM/10137 | Augmentation | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 180 Mtr. Deep Big dia Tube well (1 No) at BHALUKA FATEPUR Water Supply Scheme under Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Tilok Roy, Junior Engineer | ORD/000016/2023-2024 | 1673/MD | 18/04/2023 | 10/07/2024 | MERCURY ENGINEERING COMPANY | 10.71 | 0 | 0 | 95
19 | MALDAH |  | Malda Division | Augmentation of Bhaluka Fatepur Piped water supply scheme | SM/10137 | Augmentation | Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of Bhaluka Fatepur Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000174/2024-2025 | 2949/MD | 10/06/2024 | 25/07/2024 | SK ENTERPRISE | 6.57 | 0 | 0 | 95
20 | MALDAH |  | Malda Division | Augmentation of Bhaluka Fatepur Piped water supply scheme | SM/10137 | Augmentation | Erection of Property board related to Jal Jeevan Mission works of Bhaluka Fatepur, Kandaran Zone-I & II, Chhattrak PWSS under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000963/2024-2025 | 652/MD | 19/02/2025 | 26/02/2025 | M/S SABANA CONSTRUCTION | 0.9 | 0 | 0 | 100
Total | [13 empty] | 899.62 | 336.97 | 37.46