## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Augmentation of Bamongram piped water supply scheme. | SM/10138 | Augmentation | Acceptance cum formal work order for Excess laying of HDPE (PE-80) pipe for distribution system for the Augmentation of BAMANGRAM & its adjoining mouzas piped water supply at Bamongola Dev. Block in the District Malda under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000407/2022-2023 | 2990/MD | 07/12/2022 | 21/01/2023 | BINA CONSTRUCTION | 22.62 | 22.62 | 100 | 0
2 | MALDAH |  | Malda Division | Augmentation of Bamongram piped water supply scheme. | SM/10138 | Augmentation | Acceptance cum formal work order for Route survey for distribution network design for augmentation of Bamangram Water Supply Scheme in Bamongola block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000145/2021-2022 | 1743/MD | 15/06/2021 | 29/06/2021 | HORIZEN | 2.86 | 2.45 | 85.72 | 1
3 | MALDAH |  | Malda Mechanical | Augmentation of Bamongram piped water supply scheme. | SM/10138 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation for T/W no.- I of Bamangram Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008160) | Assistant Engineer - II |  | ORD/001096/2022-2023 | 413/MLMD | 14/03/2023 | 12/07/2023 | M/S. SOMA ENTERPRISE | 7.98 | 6.95 | 87.06 | 1
4 | MALDAH |  | Malda Mechanical | Augmentation of Bamongram piped water supply scheme. | SM/10138 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation for T/W no.- II of Bamangram Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008160) | Assistant Engineer - II |  | ORD/001097/2022-2023 | 414/MLMD | 14/03/2023 | 12/07/2023 | M/S. SOMA ENTERPRISE | 7.72 | 6.68 | 86.63 | 1
5 | MALDAH |  | Malda Mechanical | Augmentation of Bamongram piped water supply scheme. | SM/10138 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. of Bamongram Distribution Zone, Sujapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000131/2023-2024 | 3004335962 | 19/06/2023 | 18/06/2024 | W.B.S.E.D.C.LTD | 1.3 | 1.3 | 100 | 100
6 | MALDAH |  | Malda Mechanical | Augmentation of Bamongram piped water supply scheme. | SM/10138 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Augmentation of Bamangram Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008160) | Assistant Engineer - II | Junior Engineer-03 | ORD/000251/2023-2024 | 2224/MLMD | 18/07/2023 | 15/11/2023 | SUBHAS CHANDRA KESHORI | 10.85 | 0 | 0 | 0
7 | MALDAH |  | Malda Mechanical | Augmentation of Bamongram piped water supply scheme. | SM/10138 | Augmentation | Supply, installation, and commissioning of electro-mechanical components at T/W no. II of Augmentation of Bamongram Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008160) |  |  | ORD/001798/2023-2024 | 3685/MLMD | 29/11/2023 | 27/05/2024 | MOON LIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 7.73 | 0 | 0 | 0
8 | MALDAH |  | Malda Division | Augmentation of Bamongram piped water supply scheme. | SM/10138 | Augmentation | Acceptance cum formal work order for Sinking of 300mm. Dia. x 200mm. Big dia. Tube Well 125 Mtr. deep by Direct Rotary method using PVC pipe & Gravel Filter including supply of Materials at Bamangram Piped Water Supply Scheme of Bamangola Dev. Block under Malda Division, P.H.E. Dte. in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000048/2022-2023 | 1397/MD | 14/06/2022 | 05/07/2022 | SNEHASISH GHOSH | 9.71 | 9.71 | 100 | 100
9 | MALDAH |  | Malda Division | Augmentation of Bamongram piped water supply scheme. | SM/10138 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000002/2022-2023 | 1104/MD | 17/05/2022 | 17/05/2022 | Resource Division | 77.51 | 0 | 0 | 0
10 | MALDAH |  | Malda Division | Augmentation of Bamongram piped water supply scheme. | SM/10138 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000039/2022-2023 | 1248/MD | 22/03/2023 | 22/03/2023 | Resource Division | 79.81 | 0 | 0 | 0
11 | MALDAH |  | Malda Division | Augmentation of Bamongram piped water supply scheme. | SM/10138 | Augmentation | Placement of fund against the work for Road restoration work for laying of pipe line for Bamongala Habibpur Road (Portion from 7.00 kmp to 7.50 kmp) for Bamongram Piped Water Supply Scheme under Malda Division, PHE Dte. |  |  | BILL/00531/2022-2023 | BP-2022-23-210 | 16/03/2023 | 16/03/2023 | EXECUTIVE ENGINEER, MALDA HIGHWAY DIVISION, P.W. (ROADS) DIRECTORATE. | 12.47 | 0 | 0 | 0
12 | MALDAH |  | Malda Division | Augmentation of Bamongram piped water supply scheme. | SM/10138 | Augmentation | Soil Investigation and design of substructure for ................ at Bamangola Dev. Block in Malda District. |  |  | BILL/00280/2022-2023 |  | 31/01/2023 | 31/01/2023 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR. | 2.95 | 0 | 0 | 0
13 | MALDAH |  | Malda Division | Augmentation of Bamongram piped water supply scheme. | SM/10138 | Augmentation | Soil Investigation and design of substructure for Over Head Reservoirs for Bamangram Piped Water Supply Scheme at Bamaongola Dev. Block in Malda district. |  |  | BILL/00463/2022-2023 | BP-2022-23-188 | 02/03/2023 | 02/03/2023 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR. | 2.95 | 0 | 0 | 0
14 | MALDAH |  | Malda Division | Augmentation of Bamongram piped water supply scheme. | SM/10138 | Augmentation | Formal work order for the work of Augmentation of BAMANGRAM Piped water supply scheme for the work of Geotechnical Study, construction of 500 Cum RCC OHR, Laying Distribution of pipe line and providing Functional Household Tap connection (FHTC) within Bamongola Dev. Block under Malda Division PH Engg.Dte. In the District of Malda | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000007/2022-2023 | 1132/MD | 20/05/2022 | 20/05/2023 | M/S S. DAS & ENTERPRISE | 571.92 | 507.57 | 88.75 | 90
15 | MALDAH |  | Malda Division | Augmentation of Bamongram piped water supply scheme. | SM/10138 | Augmentation | Construction of Boundary Wall at 4th Tube Well Site of Bamongram Water Supply Scheme under Bamongola Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000310/2024-2025 | 3950/MD | 07/08/2024 | 21/09/2024 | SWASTIK UDYOG | 8.01 | 0 | 0 | 0
16 | MALDAH |  | Malda Mechanical | Augmentation of Bamongram piped water supply scheme. | SM/10138 | Augmentation | Supply, installation, and commissioning of electro-mechanical components at T/W no. I of Augmentation of Bamongram Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008160) | Assistant Engineer - II | Junior Engineer-03 | ORD/001797/2023-2024 | 3684/MLMD | 29/11/2023 | 27/05/2024 | BANIK BROTHERS | 8.07 | 1.05 | 12.98 | 30
17 | MALDAH |  | Malda Division | Augmentation of Bamongram piped water supply scheme. | SM/10138 | Augmentation | Laying of Rising Main including Specials and Valves for Bamangram Piped Water Supply Scheme at Bamongola Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Amit Biswas, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000958/2023-2024 | 706/MD | 09/02/2024 | 25/03/2024 | M/S GHOSH CONSTRUCTION | 8.85 | 5.9 | 66.65 | 100
18 | MALDAH |  | Malda Division | Augmentation of Bamongram piped water supply scheme. | SM/10138 | Augmentation | Augmentation work of Pump Houses and Boundary Walls with New Construction of Boundary wall at Head work site of BAMANGRAM Water Supply Scheme at Bamangola Dev. Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Debasis Pal, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000009/2025-2026 | 2412/MD | 27/05/2025 | 07/01/2026 | M/S BHARATI CONSTRUCTION | 33.45 | 0 | 0 | 0
19 | MALDAH |  | Malda Division | Augmentation of Bamongram piped water supply scheme. | SM/10138 | Augmentation | Augmentation of Head work site Pump House of Bamangram Water Supply Scheme at Bamangola Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Debasis Pal, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000777/2024-2025 | 294/MD | 29/01/2025 | 30/03/2025 | M/S EHAN ENTERPRISE | 4.36 | 0 | 0 | 0
20 | MALDAH |  | Malda Division | Augmentation of Bamongram piped water supply scheme. | SM/10138 | Augmentation | Laying of dedicated /Parallel pipe line for better functionality and providing balance FHTC of BAMANGRAM Water Supply Scheme at Bamangola Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Debasis Pal, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000195/2025-2026 | 3629/MD | 24/07/2025 | 22/09/2025 | M/S MOON LIGHT CONSTRUCTION & CO. | 87.27 | 0 | 0 | 0
21 | MALDAH |  | Malda Division | Augmentation of Bamongram piped water supply scheme. | SM/10138 | Augmentation | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with 2nd Tube Well Site of Bamangram Piped Water Supply Scheme at Bamangola Dev. Block of Malda District under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000223/2023-2024 | 2673/MD | 13/07/2023 | 27/08/2023 | DEB CONSTRUCTION | 4.17 | 0 | 0 | 100
22 | MALDAH |  | Malda Mechanical | Augmentation of Bamongram piped water supply scheme. | SM/10138 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. IV of Augmentation of Bamangram Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008160) | Assistant Engineer - II | Junior Engineer-03 | ORD/000252/2023-2024 | 2225/MLMD | 18/07/2023 | 01/03/2025 | SUBHAS CHANDRA KESHORI | 12.49 | 12.27 | 98.28 | 100
23 | MALDAH |  | Malda Division | Augmentation of Bamongram piped water supply scheme. | SM/10138 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000031/2025-2026 | 2830/MD | 11/06/2025 | 11/06/2025 | Resource Division | 18.75 | 0 | 0 | 0
Total | [13 empty] | 1003.79 | 576.5 | 57.43