## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Mechanical | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME | SM/10181 | Augmentation | Hiring of Inspection vehicle (Diesel driven) for official use of AE-II for the office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - II |  | ORD/000781/2021-2022 | 1490/MLMD | 24/08/2021 | 30/08/2021 | SUBRATA SAHA | 0.86 | 0 | 0 | 1
2 | MALDAH |  | Malda Mechanical | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME | SM/10181 | Augmentation | Modification & upgradation of electro-mechanical installation work at Pump House no.- I, Zone- I of Araidanga water supply scheme in the district of Malda under Malda Mechanical; Division, PHE Dte. | Assistant Engineer - II |  | ORD/001125/2021-2022 | 306 /MLMD | 22/02/2022 | 24/03/2022 | M/S MANABESH ROY | 7.87 | 7 | 89.01 | 1
3 | MALDAH |  | Malda Mechanical | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME | SM/10181 | Augmentation | Modification & upgradation of electro-mechanical installation work at Pump House no.- I, Zone- II of Araidanga water supply scheme in the district of Malda under Malda Mechanical; Division, PHE Dte. | Assistant Engineer - II |  | ORD/001127/2021-2022 | 308 /MLMD. | 22/02/2022 | 24/03/2022 | DEVI ENTERPRISE... | 8.26 | 7.76 | 93.96 | 1
4 | MALDAH |  | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME | SM/10181 | Augmentation | Acceptance cum formal work order for Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at 4th Tube Well site of Araidanga Zone-I Water Supply Scheme under Malda Division, PHE Dte. In the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer |  | ORD/000027/2022-2023 | 1306/MD | 01/06/2022 | 01/07/2022 | J. M. CONSTRUCTION | 4.76 | 0 | 0 | 0
5 | MALDAH |  | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME | SM/10181 | Augmentation | Acceptance cum formal work order for Sinking of 01 (One) No. 250mm. Dia. x 150mm. Big dia. Tube Well 120 Mtr. deep by Direct Rotary method using UPVC pipe & Strainer in connection with Augmentation of Araidanga (Zone-I)Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer |  | ORD/000047/2022-2023 | 1396/MD | 14/06/2022 | 05/07/2022 | SNEHASISH GHOSH | 6.91 | 0 | 0 | 0
6 | MALDAH |  | Malda Mechanical | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME | SM/10181 | Augmentation | Claim for purchase of fuel for hiring of inspection vehicle (diesel driven for official) Use month of November, 2021 to September,2022, of issuance of Fuel & Lubricant to Vehicles bearing nos i) W.B-65-C 8851 ii) W.B-65-C 4392, iii) W.B-65-D 5401 for the office of the Executive Engineer,Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - II |  | ORD/001419/2021-2022 | 1808/MLMD | 26/10/2021 | 25/11/2021 | SHAKTI FILLING STATION | 0.62 | 0 | 0 | 1
7 | MALDAH |  | Malda Mechanical | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME | SM/10181 | Augmentation | Modification & upgradation of electro-mechanical installation work at Pump House no.- II, Zone- I of Araidanga water supply scheme in the district of Malda under Malda Mechanical; Division, PHE Dte. | Assistant Engineer - II |  | ORD/001126/2021-2022 | 307 /MLMD | 22/02/2022 | 24/03/2022 | ANIMA ENTERPRISE | 7.91 | 7.41 | 93.68 | 1
8 | MALDAH |  | Malda Mechanical | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME | SM/10181 | Augmentation | Supply and delivery of Calcium hypochlorite tablets at Araidanga & adjacent water supply schemes in the district of Malda under Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - II |  | ORD/000891/2021-2022 | 1667/MLMD | 22/09/2021 | 04/10/2021 | DEY ENTERPRISE.. | 0.89 | 0.89 | 100 | 1
9 | MALDAH |  | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME | SM/10181 | Augmentation | Placement of fund against the work for road restoration work for laying of pipe line for Aridanga Piped Water Supply Scheme under Malda Division, PHE Dte. |  |  | VCH/001010/2022-2023 | BP-2022-23-98 | 23/11/2022 | 23/11/2022 | EXECUTIVE ENGINEER, PUBLIC WORKS (ROADS) DIRECTORATE. | 4.67 | 0 | 0 | 0
10 | MALDAH |  | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME | SM/10181 | Augmentation | Formal work order for the work of Laying of Distribution pipe line in connection with Augmentation of ARAIDANGA (Zone-II) Pipe Water Supply Scheme at Ratua-II Block in the District of Malda under Malda Division P.H.E. Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer |  | ORD/000133/2022-2023 | 1789/MD | 01/08/2022 | 30/09/2022 | SUBHAS CHANDRA KESHARI | 163.59 | 137.51 | 84.06 | 1
11 | MALDAH |  | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME | SM/10181 | Augmentation | Acceptance cum formal work order for Laying of Distribution pipe line in connection with Augmentation of Araidanga Zone-I ( node from J-69 to J-172, J-73 to 240, J-81 to 331, J-172 to J-73, 240 to J-191, 331 to J-69) Pipe Water Supply Scheme at Ratua-II Block in the District of Malda under Malda Division P.H.E. Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer |  | ORD/000144/2022-2023 | 1932/MD | 23/08/2022 | 07/09/2022 | SUBRATA SAHA | 6.17 | 6.17 | 100 | 1
12 | MALDAH |  | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME | SM/10181 | Augmentation | Continuation work order for the work of Hiring of 1 no diesel vehicle in good condition (traffic worthily) having licence contract carriage permit from Revisional Transport authority for office of the SE/NBC-II under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer |  | ORD/000590/2022-2023 | 1248/NBC-II | 14/11/2022 | 13/05/2023 | TARUN KUMAR BHATTACHARYA | 3.79 | 2.59 | 68.4 | 78
13 | MALDAH |  | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME | SM/10181 | Augmentation | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Augmentation of ARIDANGA ZONE-I Piped Water Supply Scheme at Ratua-II Block under Malda Division, PHE Dte. In the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer |  | ORD/000793/2022-2023 | 1477/MD | 30/03/2023 | 29/04/2023 | CHARU CONSTRUCTION | 11.09 | 10.18 | 91.79 | 0
14 | MALDAH |  | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME | SM/10181 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000013/2022-2023 | 1872/MD | 16/08/2022 | 16/08/2022 | Resource Division | 88.26 | 0 | 0 | 0
15 | MALDAH |  | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME | SM/10181 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000027/2023-2024 | 1606/MD | 11/04/2023 | 11/04/2023 | Resource Division | 31.54 | 0 | 0 | 0
16 | MALDAH |  | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME | SM/10181 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000046/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 124.23 | 0 | 0 | 0
17 | MALDAH |  | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME | SM/10181 | Augmentation | Soil Investigation and design of substructure for Over Head Reservoirs for ARIDANGA ZONE-II Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte. In the district of Malda. |  |  | BILL/00490/2022-2023 | BP-2022-23-199 | 09/03/2023 | 09/03/2023 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR. | 2.95 | 0 | 0 | 0
18 | MALDAH |  | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME | SM/10181 | Augmentation | Soil Investigation and design of substructure for Over Head Reservoirs for ARIDANGA ZONE-I Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte. In the district of Malda. |  |  | BILL/00488/2022-2023 | BP-2022-23-197 | 09/03/2023 | 09/03/2023 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR. | 2.95 | 0 | 0 | 0
19 | MALDAH |  | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME | SM/10181 | Augmentation | Formal work order for the work of Laying of Distribution pipe line in connection with Augmentation of Araidanga (Zone-I) Pipe Water Supply Scheme at Ratua-II Block in the District of Malda under Malda Division P.H.E. Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000131/2022-2023 | 1784/MD | 01/08/2022 | 30/09/2022 | USHA ENTERPRISE | 282.55 | 280.52 | 99.28 | 100
20 | MALDAH |  | Malda Mechanical | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME | SM/10181 | Augmentation | Supply, delivery, installation, commissioning and trial operation of electro-mechanical components of Augmentation of Araidanga Water Supply Scheme (Zone-I) TW no IV and external illumination works at Head Works Site(Zone-I&II) in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008180) | Assistant Engineer - II | Junior Engineer-05 | ORD/000238/2023-2024 | 2255/MLMD | 18/07/2023 | 15/11/2023 | DAS CONSTRUCTION | 19.75 | 10.22 | 51.73 | 52
21 | MALDAH |  | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME | SM/10181 | Augmentation | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Augmentation of ARIDANGA ZONE-II Piped Water Supply Scheme at Ratua-II Block under Malda Division, PHE Dte. In the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000792/2022-2023 | 1476/MD | 30/03/2023 | 29/04/2023 | UTTAM KUMAR GHOSH | 11.04 | 10.61 | 96.17 | 75
22 | MALDAH |  | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME | SM/10181 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of NIJGANPARANPUR under Araidanga Zone-II Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000723/2023-2024 | 4772/MD | 05/12/2023 | 19/01/2024 | J. M. CONSTRUCTION | 12.15 | 12.06 | 99.22 | 70
23 | MALDAH |  | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME | SM/10181 | Augmentation | Additional Laying Distribution of UPVC Pipeline of Augmentation of ARAIDANGA ZONE-I Piped Water Supply Scheme at Ratua-I Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000745/2023-2024 | 5248/MD | 22/12/2023 | 05/02/2024 | M/S JHA CONSTRUCTION | 31.99 | 31.91 | 99.75 | 80
24 | MALDAH |  | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME | SM/10181 | Augmentation | Additional Laying Distribution of UPVC Pipeline of Augmentation of ARAIDANGA ZONE-II Piped Water Supply Scheme at Ratua-II Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000746/2023-2024 | 5250/MD | 22/12/2023 | 05/02/2024 | M/S KUNDU CONSTRUCTION | 25.79 | 23.62 | 91.57 | 80
25 | MALDAH |  | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME | SM/10181 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of ARAIDANGA ZONE-I Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000747/2023-2024 | 5249/MD | 22/12/2023 | 05/02/2024 | CHARU CONSTRUCTION | 20.19 | 37.23 | 184.44 | 75
26 | MALDAH |  | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME | SM/10181 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Village Uportola, Namotola, Radhanagar, Chunakhali and Paranpur under Aridanga Zone-II Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000880/2023-2024 | 155/MD | 08/01/2024 | 22/02/2024 | GOALPARA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 12.15 | 8.94 | 73.53 | 70
27 | MALDAH |  | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME | SM/10181 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000108/2023-2024 | 38/MD | 04/01/2024 | 04/01/2024 | Resource Division | 1.85 | 0 | 0 | 0
28 | MALDAH |  | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME | SM/10181 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000180/2023-2024 | 778/MD | 20/02/2024 | 20/02/2024 | Resource Division | 1.23 | 0 | 0 | 0
29 | MALDAH |  | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME | SM/10181 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Araidanga Zone-I Water Supply Scheme under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Prosanta Mandal, Assistant Engineer | Mithu Chowdhury, Junior Engineer,Sudip Kumar Mahata, Junior Engineer | ORD/000168/2025-2026 | 5795/MD | 13/11/2025 | 12/01/2026 | M/S JHA CONSTRUCTION | 110.7 | 0 | 0 | 0
30 | MALDAH |  | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME | SM/10181 | Augmentation | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Car-2) (Period from 01/02/2025 to 31/07/2025). | Mr. Prosanta Mandal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/001037/2024-2025 | 377/MD | 31/01/2025 | 31/07/2025 | SUBRATA SAHA | 0.86 | 0 | 0 | 0
31 | MALDAH |  | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME | SM/10181 | Augmentation | Formal work order for the work of Construction of 400 M³ Capacity OHR with FHTC of ARIDANGA ZON-II Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte. in the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000014/2023-2024 | 1649/MD | 13/04/2023 | 31/12/2024 | UTTAM KUMAR GHOSH | 173.92 | 112.75 | 64.83 | 93
32 | MALDAH |  | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME | SM/10181 | Augmentation | Formal work order for the work of Construction of 900 M³ Capacity OHR with FHTC of Aridanga Zone-I Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte. in the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000005/2023-2024 | 1572/MD | 10/04/2023 | 09/04/2024 | USHA ENTERPRISE | 338.37 | 180.21 | 53.26 | 92
33 | MALDAH |  | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME | SM/10181 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000014/2025-2026 | 2805/MD | 11/06/2025 | 11/06/2025 | Resource Division | 11.73 | 0 | 0 | 0
34 | MALDAH |  | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME | SM/10181 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000087/2025-2026 | 5554/MD | 29/10/2025 | 29/10/2025 | Resource Division | 11.73 | 0 | 0 | 0
35 | MALDAH |  | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME | SM/10181 | Augmentation | Construction of Pump House (5.40 mtr.X 3.60 mtr) at Head Work Site of Augmentation of Aridanga Zone-I Piped Water Supply Scheme at Ratua-II Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000139/2024-2025 | 2890/MD | 07/06/2024 | 22/07/2024 | A.K. AGENCY | 6.57 | 0 | 0 | 90
36 | MALDAH |  | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME | SM/10181 | Augmentation | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Aridanga Zone-II Water Supply Scheme under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Prosanta Mandal, Assistant Engineer | Mithu Chowdhury, Junior Engineer | ORD/000083/2025-2026 | 2281/MD | 21/05/2025 | 18/09/2025 | UNITED FRIENDS UNEMPLOYED ENGG CO-OPE SOCEITY LTD | 19.52 | 0 | 0 | 0
Total | [13 empty] | 1569.38 | 887.58 | 56.56