## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | INSTALLATION OF 100 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES OF GP MADNABATI,GOBINDAPUR & MAHESHPUR AND CHANDPUR IN BAMONGOLA DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE | SM/10215 | Anganwadi | Acceptance cum formal work order for Supplying G.I. pipe strainer for installation of CWPP at AWC of G.P.- Madnabati, Gobindapur & Maheshpur and Chandpur in Bamangola Dev. Block at Mangalbari Stack Yard under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000058/2022-2023 | 1502/MD | 28/06/2022 | 13/07/2022 | SAUDAGAR (INDIA) | 18.01 | 0 | 0 | 100
2 | MALDAH |  | Malda Division | INSTALLATION OF 100 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES OF GP MADNABATI,GOBINDAPUR & MAHESHPUR AND CHANDPUR IN BAMONGOLA DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE | SM/10215 | Anganwadi | Material Requisition To Resource Division |  |  | RTOR000018/2021-2022 | 523/MD | 03/03/2022 | 03/03/2022 | Resource Division | 20.91 | 0 | 0 | 0
3 | MALDAH |  | Malda Division | INSTALLATION OF 100 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES OF GP MADNABATI,GOBINDAPUR & MAHESHPUR AND CHANDPUR IN BAMONGOLA DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE | SM/10215 | Anganwadi | Material Requisition To Resource Division |  |  | RTOR000142/2023-2024 | 118/MD | 05/01/2024 | 05/01/2024 | Resource Division | 16.32 | 0 | 0 | 0
4 | MALDAH |  | Malda Division | INSTALLATION OF 100 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES OF GP MADNABATI,GOBINDAPUR & MAHESHPUR AND CHANDPUR IN BAMONGOLA DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE | SM/10215 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) at different Anganwadi Centres (AWCs) of G.P.- Madnabati, Gobindapur & Maheshpur and Chandpur in Bamangola Dev. Block, Malda under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000009/2022-2023 | 1134/MD | 20/05/2022 | 17/09/2022 | M/S GUHA & ROY ENTERPRISE | 572.3 | 0 | 0 | 98
Total | [13 empty] | 627.55 | 0 | 0