## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | INSTALLATION OF 97 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT ANGANWADI CENTRES(AWCs) OF RATUA -II DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. | SM/10216 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) at different Anganwadi Centres (AWCs) of Ratua-II Dev. Block, Malda under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Sudip Kumar Mahata, Junior Engineer | ORD/000043/2022-2023 | 1381/MD | 13/06/2022 | 11/10/2022 | M/S RUBIET HOSSAIN | 688.25 | 652.59 | 94.82 | 100
2 | MALDAH |  | Malda Division | INSTALLATION OF 97 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT ANGANWADI CENTRES(AWCs) OF RATUA -II DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. | SM/10216 | Anganwadi | Acceptance cum formal work order for Supplying G.I. pipe strainer for installation of CWPP at AWC of Ratua-II Dev. Block at Chanchal Stack Yard under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Sudip Kumar Mahata, Junior Engineer | ORD/000053/2022-2023 | 1437/MD | 20/06/2022 | 05/07/2022 | M/S RUBIET HOSSAIN | 17.37 | 17.01 | 97.94 | 100
3 | MALDAH |  | Malda Division | INSTALLATION OF 97 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT ANGANWADI CENTRES(AWCs) OF RATUA -II DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. | SM/10216 | Anganwadi | Material Requisition To Resource Division |  |  | RTOR000017/2021-2022 | 522/MD | 03/03/2022 | 03/03/2022 | Resource Division | 134.01 | 0 | 0 | 0
Total | [13 empty] | 839.63 | 669.6 | 79.75