## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | INSTALLATION OF 18 nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT SCHOOLS OF OLD MALDA DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. | SM/10241 | School | Acceptance cum formal work order for Installation of Stand-Alone Community Purification Plant (CWPP) at different Schools of Old Malda Dev. Block, Malda under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Bikash Balo, Junior Engineer,Ramen Karmakar, Junior Engineer | ORD/000001/2022-2023 | 830/MD | 06/04/2022 | 05/07/2022 | NEOGI ENTERPRISE | 88.91 | 83.42 | 93.82 | 100
2 | MALDAH |  | Malda Division | INSTALLATION OF 18 nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT SCHOOLS OF OLD MALDA DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. | SM/10241 | School | Material Requisition To Resource Division |  |  | RTOR000013/2021-2022 | 530/MD | 03/03/2022 | 03/03/2022 | Resource Division | 24.82 | 0 | 0 | 0
Total | [13 empty] | 113.72 | 83.42 | 73.35