## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | INSTALLATION OF 129 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT ANGANWADI CENTRES OF GP-BAMONGOLA,JAGDALA & PAKUAHAT IN BAMONGOLA DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. | SM/10242 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWCs at Bamangola GP of Bamangola Dev. Block under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000426/2022-2023 | 3197/MD | 27/12/2022 | 12/03/2023 | MODERN CONSTRUCTION | 174.38 | 172.23 | 98.77 | 100
2 | MALDAH |  | Malda Division | INSTALLATION OF 129 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT ANGANWADI CENTRES OF GP-BAMONGOLA,JAGDALA & PAKUAHAT IN BAMONGOLA DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. | SM/10242 | Anganwadi | Material Requisition To Resource Division |  |  | RTOR000019/2021-2022 | 524/MD | 03/03/2022 | 03/03/2022 | Resource Division | 79.15 | 0 | 0 | 0
3 | MALDAH |  | Malda Division | INSTALLATION OF 129 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT ANGANWADI CENTRES OF GP-BAMONGOLA,JAGDALA & PAKUAHAT IN BAMONGOLA DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. | SM/10242 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWCs at Jogdala GP of Bamangola Dev. Block under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000504/2022-2023 | 117/MD | 18/01/2023 | 03/04/2023 | MOTI RAHAMAN | 173.18 | 164.25 | 94.85 | 90
4 | MALDAH |  | Malda Division | INSTALLATION OF 129 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT ANGANWADI CENTRES OF GP-BAMONGOLA,JAGDALA & PAKUAHAT IN BAMONGOLA DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. | SM/10242 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWC's at Pakuahat GP of Bamongola Dev. Block under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000491/2022-2023 | 95/MD | 17/01/2023 | 02/04/2023 | J. S. CONSTRUCTION | 199.27 | 188.74 | 94.71 | 90
5 | MALDAH |  | Malda Division | INSTALLATION OF 129 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT ANGANWADI CENTRES OF GP-BAMONGOLA,JAGDALA & PAKUAHAT IN BAMONGOLA DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. | SM/10242 | Anganwadi | Installation of Solar Powered Standalone Community Water Purification Plant (CWPP) for AWC's at different places of Bamongola Dev. Block under Malda Division, PHE Dte. (Quantity: 14 Nos.) | Mr. Arnab Giri, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Mukaddar Parvage, Junior Engineer,Ziaur Rahaman, Junior Engineer | ORD/000185/2025-2026 | 2953/MD | 19/06/2025 | 16/11/2025 | USHA ENTERPRISE | 95.65 | 0 | 0 | 0
Total | [13 empty] | 721.63 | 525.23 | 72.78