## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | INSTALLATION OF 75 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT ANGANWADI CENTRES(AWCs) OF HARISHCHANDRAPUR-II DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. | SM/10243 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWCs at Sultannagar, Bhaluka & Doulatnagar GP of Harishchandrapur-II Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000427/2022-2023 | 3198/MD | 27/12/2022 | 12/03/2023 | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 161.94 | 0 | 0 | 100
2 | MALDAH |  | Malda Division | INSTALLATION OF 75 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT ANGANWADI CENTRES(AWCs) OF HARISHCHANDRAPUR-II DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. | SM/10243 | Anganwadi | Material Requisition To Resource Division |  |  | RTOR000012/2021-2022 | 519/MD | 03/03/2022 | 03/03/2022 | Resource Division | 49.36 | 0 | 0 | 0
3 | MALDAH |  | Malda Division | INSTALLATION OF 75 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT ANGANWADI CENTRES(AWCs) OF HARISHCHANDRAPUR-II DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. | SM/10243 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWCs at Islampur, Doulatpur & Sadlichak GP of Harishchandrapur-II Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation,Mr. Tilok Roy, Junior Engineer | ORD/000530/2022-2023 | 553/MD | 09/02/2023 | 25/04/2023 | SOUNAK ENTERPRISE | 112.11 | 0 | 0 | 70
4 | MALDAH |  | Malda Division | INSTALLATION OF 75 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT ANGANWADI CENTRES(AWCs) OF HARISHCHANDRAPUR-II DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. | SM/10243 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWC's at Malior-I & II and Masaldaha GP of Harishchandrapur-II Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Tilok Roy, Junior Engineer | ORD/000455/2022-2023 | 60/MD | 16/01/2023 | 01/04/2023 | M/S TRILOCHAN CONSTRUCTION CO | 112 | 0 | 0 | 96
Total | [13 empty] | 435.41 | 0 | 0