## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | INSTALLATION OF 118 nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP)AT ANGANWADI CENTRES(AWCs) OF GP-CHAKNAGAR,SALAIDANGA,SAHAJADPUR,GAZOLE-I,GAZOLE-II & BAHIRGACHHI -II IN GAZOLE DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE | SM/10244 | Anganwadi | Acceptance cum formal work order for Supplying G.I. pipe strainer for installation of CWPP at AWC of G.P.- Chaknagar, Salaidanga, Sahajadpur, Gazole-I, Gazole-II & Bahirgachhi-II in Gazole Dev. Block at Mangalbari Stack Yard under Malda Division, PHE Dte.(Part-II) | Mr. Arnab Giri, Assistant Engineer | Biswajit Gosh, Junior Engineer | ORD/000051/2022-2023 | 1435/MD | 20/06/2022 | 05/07/2022 | SAUDAGAR (INDIA) | 20.75 | 20.74 | 99.95 | 0
2 | MALDAH |  | Malda Division | INSTALLATION OF 118 nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP)AT ANGANWADI CENTRES(AWCs) OF GP-CHAKNAGAR,SALAIDANGA,SAHAJADPUR,GAZOLE-I,GAZOLE-II & BAHIRGACHHI -II IN GAZOLE DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE | SM/10244 | Anganwadi | Material Requisition To Resource Division |  |  | RTOR000008/2021-2022 | 528/MD | 03/03/2022 | 03/03/2022 | Resource Division | 72.38 | 0 | 0 | 0
3 | MALDAH |  | Malda Division | INSTALLATION OF 118 nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP)AT ANGANWADI CENTRES(AWCs) OF GP-CHAKNAGAR,SALAIDANGA,SAHAJADPUR,GAZOLE-I,GAZOLE-II & BAHIRGACHHI -II IN GAZOLE DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE | SM/10244 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) at different Anganwadi Centres (AWCs) of G.P.- Chaknagar, Salaidanga, Sahajadpur, Gazole-I, Gazole-II & Bahirgachhi-II in Gazole Dev. Block, Malda under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000010/2022-2023 | 1135/MD | 20/05/2022 | 17/09/2022 | M/S S. DAS & ENTERPRISE | 675.32 | 629.98 | 93.29 | 80
Total | [13 empty] | 768.45 | 650.71 | 84.68