## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | INSTALLATION OF 90 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT ANGANWADI CENTRES(AWCs) OF GP-MAHANANDATOLA,BELAIMARI,BHADO,SAMSI,CHANDMONI-I& CHANDMONI-II IN RATUA-I DEV BLOCK,MALDA UNDER MALDA DIVISION,PHE DTE. | SM/10245 | Anganwadi | Acceptance cum formal work order for Supplying G.I. pipe strainer for installation of CWPP at AWC of G.P.- Mahananda Tola, Belaimari, Bhado, Samsi, Chandmoni-I & Chandmoni-II in Ratua-I Dev. Block at Chanchal Stack Yard under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Junior Engineer, | ORD/000052/2022-2023 | 1436/MD | 20/06/2022 | 05/07/2022 | M/S GOUTAM CHAKRABORTY | 16.12 | 15.31 | 95 | 95
2 | MALDAH |  | Malda Division | INSTALLATION OF 90 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT ANGANWADI CENTRES(AWCs) OF GP-MAHANANDATOLA,BELAIMARI,BHADO,SAMSI,CHANDMONI-I& CHANDMONI-II IN RATUA-I DEV BLOCK,MALDA UNDER MALDA DIVISION,PHE DTE. | SM/10245 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) at different Anganwadi Centres (AWCs) of G.P.- Mahananda Tola, Belaimari, Bhado, Samsi, Chandmoni-I & Chandmoni-II in Ratua-I Dev. Block, Malda under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Tapan Haldar, Junior Engineer | ORD/000008/2022-2023 | 1133/MD | 20/05/2022 | 17/09/2022 | M/S GOUTAM CHAKRABORTY | 634.77 | 572.78 | 90.23 | 99
3 | MALDAH |  | Malda Division | INSTALLATION OF 90 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT ANGANWADI CENTRES(AWCs) OF GP-MAHANANDATOLA,BELAIMARI,BHADO,SAMSI,CHANDMONI-I& CHANDMONI-II IN RATUA-I DEV BLOCK,MALDA UNDER MALDA DIVISION,PHE DTE. | SM/10245 | Anganwadi | Material Requisition To Resource Division |  |  | RTOR000015/2021-2022 | 520/MD | 03/03/2022 | 03/03/2022 | Resource Division | 124.28 | 0 | 0 | 0
Total | [13 empty] | 775.17 | 588.1 | 75.87