## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | INSTALLATION OF 121 Nos. STANDALONE COMMUNITY PURIFICATION PLANTS(CWPP) AT ANGANWADI CENTRES(AWCs) OF GP-MANGALPURA,AKTOIL,HABIBPUR,BAIDYAPUR & JAJOIL IN HABIBPUR DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. | SM/10246 | Anganwadi | Material Requisition To Resource Division |  |  | RTOR000009/2021-2022 | 529/MD | 03/03/2022 | 03/03/2022 | Resource Division | 79.67 | 0 | 0 | 0
2 | MALDAH |  | Malda Division | INSTALLATION OF 121 Nos. STANDALONE COMMUNITY PURIFICATION PLANTS(CWPP) AT ANGANWADI CENTRES(AWCs) OF GP-MANGALPURA,AKTOIL,HABIBPUR,BAIDYAPUR & JAJOIL IN HABIBPUR DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. | SM/10246 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWCs at Aktoil GP of Habibpur Dev. Block under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000520/2022-2023 | 813/MD | 20/02/2023 | 06/05/2023 | NEOGI ENTERPRISE | 137.07 | 116.11 | 84.71 | 70
3 | MALDAH |  | Malda Division | INSTALLATION OF 121 Nos. STANDALONE COMMUNITY PURIFICATION PLANTS(CWPP) AT ANGANWADI CENTRES(AWCs) OF GP-MANGALPURA,AKTOIL,HABIBPUR,BAIDYAPUR & JAJOIL IN HABIBPUR DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. | SM/10246 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWCs at Mangalpura & Jajoil GP of Habibpur Dev. Block under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000529/2022-2023 | 554/MD | 09/02/2023 | 25/04/2023 | GBM ASSOCIATES | 112.04 | 100.74 | 89.92 | 80
4 | MALDAH |  | Malda Division | INSTALLATION OF 121 Nos. STANDALONE COMMUNITY PURIFICATION PLANTS(CWPP) AT ANGANWADI CENTRES(AWCs) OF GP-MANGALPURA,AKTOIL,HABIBPUR,BAIDYAPUR & JAJOIL IN HABIBPUR DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. | SM/10246 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWCs at Baidyapur GP of Habibpur Dev. Block under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000528/2022-2023 | 555/MD | 09/02/2023 | 25/04/2023 | MILLENNIUM ENTERPRISR | 136.96 | 127.56 | 93.14 | 100
5 | MALDAH |  | Malda Division | INSTALLATION OF 121 Nos. STANDALONE COMMUNITY PURIFICATION PLANTS(CWPP) AT ANGANWADI CENTRES(AWCs) OF GP-MANGALPURA,AKTOIL,HABIBPUR,BAIDYAPUR & JAJOIL IN HABIBPUR DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. | SM/10246 | Anganwadi | Material Requisition To Resource Division |  |  | RTOR000143/2023-2024 | 121/MD | 05/01/2024 | 05/01/2024 | Resource Division | 6.8 | 0 | 0 | 0
6 | MALDAH |  | Malda Division | INSTALLATION OF 121 Nos. STANDALONE COMMUNITY PURIFICATION PLANTS(CWPP) AT ANGANWADI CENTRES(AWCs) OF GP-MANGALPURA,AKTOIL,HABIBPUR,BAIDYAPUR & JAJOIL IN HABIBPUR DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. | SM/10246 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWCs at Habibpur GP of Habibpur Dev. Block under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000517/2022-2023 | 542/MD | 08/02/2023 | 01/05/2025 | NEOGI ENTERPRISE | 137.06 | 0 | 0 | 40
Total | [13 empty] | 609.59 | 344.42 | 56.5