## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | INSTALLATION OF 96 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES(AWCs) OF OLD MALDA DEV BLOCK,MALDA UNDER MALDA DIVISION,PHE DTE | SM/10247 | Anganwadi | Acceptance cum formal work order for Supplying G.I. pipe strainer for installation of CWPP at AWC of Old Malda Dev. Block at Mangalbari Stack Yard under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ramen Karmakar, Junior Engineer | ORD/000049/2022-2023 | 1433/MD | 20/06/2022 | 05/07/2022 | M/S S. S. ENTERPRISE | 17.19 | 10.12 | 58.85 | 0
2 | MALDAH |  | Malda Division | INSTALLATION OF 96 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES(AWCs) OF OLD MALDA DEV BLOCK,MALDA UNDER MALDA DIVISION,PHE DTE | SM/10247 | Anganwadi | Material Requisition To Resource Division |  |  | RTOR000016/2021-2022 | 521/MD | 03/03/2022 | 03/03/2022 | Resource Division | 4.49 | 0 | 0 | 0
3 | MALDAH |  | Malda Division | INSTALLATION OF 96 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES(AWCs) OF OLD MALDA DEV BLOCK,MALDA UNDER MALDA DIVISION,PHE DTE | SM/10247 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) at different Anganwadi Centres (AWCs) of Old Malda Dev. Block, Malda under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000059/2022-2023 | 1512/MD | 29/06/2022 | 27/10/2022 | M/S S. S. ENTERPRISE | 549.41 | 415.74 | 75.67 | 94
Total | [13 empty] | 571.09 | 425.86 | 74.57