## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at Head Work site of UTTAR HARISHCHANDRAPUR ZONE-II & its adjoining mouza Water Supply Scheme under Malda Division,PHE Dte. In the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000054/2022-2023 | 1486/MD | 23/06/2022 | 22/08/2022 | S. N. CONSTRUCTION | 6.18 | 0 | 0 | 0
2 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Laying Emergent repairing of distribution pipe line & laying of UPVC pipe line of UTTAR HARISHCHANDRAPUR water supply scheme under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000783/2019-2020 | 856/MD | 20/03/2020 | 20/03/2020 | PARIJAT RAY | 4.57 | 0 | 0 | 1
3 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000006/2022-2023 | 1206/MD | 24/05/2022 | 24/05/2022 | Resource Division | 53.31 | 0 | 0 | 0
4 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Soil Investigation and design of substructure for Over Head Reservoirs for UTTAR HARISHCHANDRAPUR ZONE-I Piped Water Supply Scheme at Harishchandapur-I Dev. Block under Malda Division, PHE Dte. In the district of Malda. |  |  | BILL/00487/2022-2023 | BP-2022-23-196 | 09/03/2023 | 09/03/2023 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR. | 2.95 | 0 | 0 | 0
5 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Bill for reimbursement of cost of Diesel and Mobile in respect of hired Vehicle Car No. WB65A/4911 for the month of May & June 2023. |  |  | BILL/00370/2023-2024 |  | 04/09/2023 | 04/09/2023 | USHA ENTERPRISE | 0.41 | 0 | 0 | 0
6 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Placement of fund against the work for road restoration work for laying of pipe line for NH-81 to Harishchandarapur Railway Station Road under Malda Division, PHE Dte. In the district of Malda. |  |  | BILL/00495/2022-2023 | BP-2022-23-213 | 17/03/2023 | 17/03/2023 | EXECUTIVE ENGINEER, MALDA HIGHWAY DIVISION, P.W. (ROADS) DIRECTORATE. | 1.4 | 0 | 0 | 0
7 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Formal work order for the work of Construction of 400 M3 Capacity OHR with Soil Investigation and FHTC of UTTAR HARISHCHANDRAPUR ZONE-II Piped Water Supply Scheme at Harishchandrapur-I and II Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000227/2023-2024 | 2682/MD | 13/07/2023 | 27/03/2026 | KANAN CONSTRUCTION ENTERPRISE | 229.11 | 0 | 0 | 65
8 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to tubewell No 3 at Uttar Harishchandrapur Zone-I PWSS under Harischandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000903/2023-2024 | 276/MD | 11/01/2024 | 25/02/2024 | M/S DUTTA ENTERPRISE | 4.18 | 0 | 0 | 0
9 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Construction of Boundary Wall at Head Work site of Uttar Harishchandrapur Zone-II Water Supply Scheme under Harischandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000211/2024-2025 | 3032/MD | 13/06/2024 | 13/11/2024 | M/S. B. PAUL & COMPANY | 25.13 | 0 | 0 | 82
10 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Acceptance cum formal work order for Sinking of 01 (One) Nos. 300mm. Dia. x 200mm. Big dia. Tube Well 150 Mtr. deep by Direct Rotary method using UPVC pipe & Strainer in connection with Augmentation of Uttar Harishchandrapur (Zone-I) Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda . | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000044/2022-2023 | 1393/MD | 14/06/2022 | 05/07/2022 | M/S DEBASISH GHOSH | 10.83 | 0 | 0 | 96
11 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Acceptance cum formal work order for Sinking of 01 (One) Nos. 300mm. Dia. x 200mm. Big dia. Tube Well 150 Mtr. deep by Direct Rotary method using UPVC pipe & Strainer in connection with Augmentation of Uttar Harishchandrapur (Zone-II) Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda . | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000045/2022-2023 | 1394/MD | 14/06/2022 | 05/07/2022 | SNEHASISH GHOSH | 10.82 | 0 | 0 | 95
12 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Construction of 5.40 mtr.X 3.60 mtr Switch Room cum chlorine room at UTTAR HARISHCHANDRAPUR ZONE-II Piped Water Supply Scheme at Head Work Site under Harishchandrapur-II Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000140/2024-2025 | 2891/MD | 07/06/2024 | 22/07/2024 | KANAN CONSTRUCTION ENTERPRISE | 6.6 | 0 | 0 | 100
13 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000105/2023-2024 | 35/MD | 04/01/2024 | 04/01/2024 | Resource Division | 17.33 | 0 | 0 | 0
14 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000127/2023-2024 | 97/MD | 05/01/2024 | 05/01/2024 | Resource Division | 11.4 | 0 | 0 | 0
15 | MALDAH |  | Malda Mechanical | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Quatation for new service connection at Uttar Harishchandrapur w/s sch. Zone I T/W no IV UNDER MLMD. Dist Malda. (Harishchandrapur C. C. C) |  |  | BILL/03507/2023-2024 | BP-2023-24-527 | 15/02/2024 | 15/02/2024 | W.B.S.E.D.C.LTD | 8.02 | 0 | 0 | 0
16 | MALDAH |  | Malda Mechanical | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | New service connection at UTTAR HARISHCHANDRAPUR PWSS Zone II T/W NO I Under EE/MLMD PHE DTE DIST. Malda.( Harishchandrapur c c c) |  |  | BILL/03759/2023-2024 | BP-2023-24-730 | 28/03/2024 | 28/03/2024 | W.B.S.E.D.C.LTD | 4.42 | 0 | 0 | 0
17 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Formal work order for the work of Laying of Distribution pipe line in connection with Augmentation of Uttar Harishchandrapur Zone-II Water Supply Scheme under Malda Division PHE. Dte in The District of Malda. (2nd Call) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000509/2022-2023 | 377/MD | 31/01/2023 | 30/11/2025 | KUNDU CONSTRUCTION | 227.6 | 0 | 0 | 41
18 | MALDAH |  | Malda Mechanical | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Augmentation of Uttar Harishandropur (Zone- II) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008163) | Assistant Engineer - II | Junior Engineer-05 | ORD/000237/2023-2024 | 2254/MLMD | 18/07/2023 | 26/11/2025 | DAS ENTERPRISE. | 21.45 | 0 | 0 | 45
19 | MALDAH |  | Malda Mechanical | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , II, III & IV and making compound lighting arrangement at T/W no. I of Augmentation of Uttar Harishandropur (Zone- I) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008163) | Assistant Engineer - II | Junior Engineer-05 | ORD/000236/2023-2024 | 2253/MLMD | 18/07/2023 | 29/04/2026 | M/S P.P. ELECTRICALS | 50.68 | 0 | 0 | 82
20 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Formal work order for the work of Construction of 900 M3 Capacity OHR with FHTC (Mouza- Uttar Harishchandrapur 50% area covered) of Uttar Harishchandrapur Zone-I Piped Water Supply Scheme at Harishchandrapur-I & II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000476/2023-2024 | 3615/MD | 21/09/2023 | 01/01/2025 | MAHAMAYA BURIMA ENTERPRISE | 340.61 | 0 | 0 | 65
21 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Laying of Additional Pipeline HDPE in connection with Jal Jeevan Mission (JJM) at Uttar Harishchandrapur Zone-II Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000624/2024-2025 | 5831/MD | 22/11/2024 | 05/10/2025 | KUNDU CONSTRUCTION | 95.04 | 0 | 0 | 0
22 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Construction of Boundary Wall at 3rd Tube well site of Uttar Harishchandrapur Zone-I Water Supply Scheme under Harischandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000210/2024-2025 | 3031/MD | 13/06/2024 | 01/04/2026 | M/S GHOSH CONSTRUCTION | 10.19 | 0 | 0 | 0
23 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Construction of Boundary Wall at Head Work site of Uttar Harishchandrapur Zone-I Water Supply Scheme under Harischandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000489/2024-2025 | 5002/MD | 27/09/2024 | 24/06/2025 | SAJEDUR RAHAMAN | 34.41 | 0 | 0 | 80
24 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Road restoration work related to laying of Pipeleine at Uttar Harishchandrapur Zone-I Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. (2nd Call) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000159/2025-2026 | 2881/MD | 17/06/2025 | 01/08/2025 | PRADIP KUMAR DAS | 56.21 | 0 | 0 | 0
25 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room at Pump House No. 4 of Uttar Harishchandrapur Zone-I PWSS under Harishchandrapur-I Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000107/2025-2026 | 2278/MD | 21/05/2025 | 05/07/2025 | MASUMA ENTERPRISE | 4.28 | 0 | 0 | 100
26 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Formal work order for the work of Laying of Distribution pipe line in connection with Augmentation of Uttar Harishchandrapur Zone-I Water Supply Scheme under Malda Division PHE. Dte in The District of Malda. (2ND Call) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000134/2022-2023 | 1791/MD | 01/08/2022 | 01/06/2025 | PRADIP KUMAR DAS | 369.64 | 0 | 0 | 100
Total | [13 empty] | 1606.76 | 0 | 0