## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at Head Work site of UTTAR HARISHCHANDRAPUR ZONE-II & its adjoining mouza Water Supply Scheme under Malda Division,PHE Dte. In the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000054/2022-2023 | 1486/MD | 23/06/2022 | 22/08/2022 | S. N. CONSTRUCTION | 6.18 | 0 | 0 | 0
2 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Laying Emergent repairing of distribution pipe line & laying of UPVC pipe line of UTTAR HARISHCHANDRAPUR water supply scheme under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000783/2019-2020 | 856/MD | 20/03/2020 | 20/03/2020 | PARIJAT RAY | 4.57 | 0 | 0 | 1
3 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000006/2022-2023 | 1206/MD | 24/05/2022 | 24/05/2022 | Resource Division | 53.31 | 0 | 0 | 0
4 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Soil Investigation and design of substructure for Over Head Reservoirs for UTTAR HARISHCHANDRAPUR ZONE-I Piped Water Supply Scheme at Harishchandapur-I Dev. Block under Malda Division, PHE Dte. In the district of Malda. |  |  | BILL/00487/2022-2023 | BP-2022-23-196 | 09/03/2023 | 09/03/2023 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR. | 2.95 | 0 | 0 | 0
5 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Bill for reimbursement of cost of Diesel and Mobile in respect of hired Vehicle Car No. WB65A/4911 for the month of May & June 2023. |  |  | BILL/00370/2023-2024 |  | 04/09/2023 | 04/09/2023 | USHA ENTERPRISE | 0.41 | 0 | 0 | 0
6 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Placement of fund against the work for road restoration work for laying of pipe line for NH-81 to Harishchandarapur Railway Station Road under Malda Division, PHE Dte. In the district of Malda. |  |  | BILL/00495/2022-2023 | BP-2022-23-213 | 17/03/2023 | 17/03/2023 | EXECUTIVE ENGINEER, MALDA HIGHWAY DIVISION, P.W. (ROADS) DIRECTORATE. | 1.4 | 0 | 0 | 0
7 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Formal work order for the work of Construction of 400 M3 Capacity OHR with Soil Investigation and FHTC of UTTAR HARISHCHANDRAPUR ZONE-II Piped Water Supply Scheme at Harishchandrapur-I and II Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000227/2023-2024 | 2682/MD | 13/07/2023 | 28/09/2025 | KANAN CONSTRUCTION ENTERPRISE | 229.11 | 84.59 | 36.92 | 65
8 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to tubewell No 3 at Uttar Harishchandrapur Zone-I PWSS under Harischandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000903/2023-2024 | 276/MD | 11/01/2024 | 25/02/2024 | M/S DUTTA ENTERPRISE | 4.18 | 0 | 0 | 0
9 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Construction of Boundary Wall at Head Work site of Uttar Harishchandrapur Zone-II Water Supply Scheme under Harischandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000211/2024-2025 | 3032/MD | 13/06/2024 | 13/07/2024 | M/S. B. PAUL & COMPANY | 25.13 | 14.45 | 57.48 | 82
10 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Jack Pushing of M.S. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at NODE POINT 80 TO 82,82 TO 83 (DISTRIBUTION SYSTEM) at Uttar Harishchandrapur Zone -II and its adjoining Mouzas Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000477/2024-2025 | 4991/MD | 27/09/2024 | 11/11/2024 | M/S TRILOCHAN CONSTRUCTION CO | 23.29 | 0 | 0 | 0
11 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Acceptance cum formal work order for Sinking of 01 (One) Nos. 300mm. Dia. x 200mm. Big dia. Tube Well 150 Mtr. deep by Direct Rotary method using UPVC pipe & Strainer in connection with Augmentation of Uttar Harishchandrapur (Zone-I) Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda . | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000044/2022-2023 | 1393/MD | 14/06/2022 | 05/07/2022 | M/S DEBASISH GHOSH | 10.83 | 0 | 0 | 96
12 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Acceptance cum formal work order for Sinking of 01 (One) Nos. 300mm. Dia. x 200mm. Big dia. Tube Well 150 Mtr. deep by Direct Rotary method using UPVC pipe & Strainer in connection with Augmentation of Uttar Harishchandrapur (Zone-II) Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda . | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000045/2022-2023 | 1394/MD | 14/06/2022 | 05/07/2022 | SNEHASISH GHOSH | 10.82 | 10.71 | 98.95 | 95
13 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Construction of 5.40 mtr.X 3.60 mtr Switch Room cum chlorine room at UTTAR HARISHCHANDRAPUR ZONE-II Piped Water Supply Scheme at Head Work Site under Harishchandrapur-II Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000140/2024-2025 | 2891/MD | 07/06/2024 | 22/07/2024 | KANAN CONSTRUCTION ENTERPRISE | 6.6 | 5.79 | 87.82 | 100
14 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000105/2023-2024 | 35/MD | 04/01/2024 | 04/01/2024 | Resource Division | 17.33 | 0 | 0 | 0
15 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000127/2023-2024 | 97/MD | 05/01/2024 | 05/01/2024 | Resource Division | 11.4 | 0 | 0 | 0
16 | MALDAH |  | Malda Mechanical | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Quatation for new service connection at Uttar Harishchandrapur w/s sch. Zone I T/W no IV UNDER MLMD. Dist Malda. (Harishchandrapur C. C. C) |  |  | BILL/03507/2023-2024 | BP-2023-24-527 | 15/02/2024 | 15/02/2024 | W.B.S.E.D.C.LTD | 8.02 | 0 | 0 | 0
17 | MALDAH |  | Malda Mechanical | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | New service connection at UTTAR HARISHCHANDRAPUR PWSS Zone II T/W NO I Under EE/MLMD PHE DTE DIST. Malda.( Harishchandrapur c c c) |  |  | BILL/03759/2023-2024 | BP-2023-24-730 | 28/03/2024 | 28/03/2024 | W.B.S.E.D.C.LTD | 4.42 | 0 | 0 | 0
18 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Formal work order for the work of Laying of Distribution pipe line in connection with Augmentation of Uttar Harishchandrapur Zone-I Water Supply Scheme under Malda Division PHE. Dte in The District of Malda. (2ND Call) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000134/2022-2023 | 1791/MD | 01/08/2022 | 01/06/2025 | PRADIP KUMAR DAS | 369.64 | 327.83 | 88.69 | 100
19 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Formal work order for the work of Laying of Distribution pipe line in connection with Augmentation of Uttar Harishchandrapur Zone-II Water Supply Scheme under Malda Division PHE. Dte in The District of Malda. (2nd Call) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000509/2022-2023 | 377/MD | 31/01/2023 | 01/10/2025 | KUNDU CONSTRUCTION | 227.6 | 126.66 | 55.65 | 41
20 | MALDAH |  | Malda Mechanical | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Augmentation of Uttar Harishandropur (Zone- II) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008163) | Assistant Engineer - II | Junior Engineer-05 | ORD/000237/2023-2024 | 2254/MLMD | 18/07/2023 | 26/11/2025 | DAS ENTERPRISE. | 21.45 | 0 | 0 | 45
21 | MALDAH |  | Malda Mechanical | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , II, III & IV and making compound lighting arrangement at T/W no. I of Augmentation of Uttar Harishandropur (Zone- I) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008163) | Assistant Engineer - II | Junior Engineer-05 | ORD/000236/2023-2024 | 2253/MLMD | 18/07/2023 | 29/04/2026 | M/S P.P. ELECTRICALS | 50.68 | 39.6 | 78.14 | 82
22 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Formal work order for the work of Construction of 900 M3 Capacity OHR with FHTC (Mouza- Uttar Harishchandrapur 50% area covered) of Uttar Harishchandrapur Zone-I Piped Water Supply Scheme at Harishchandrapur-I & II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000476/2023-2024 | 3615/MD | 21/09/2023 | 01/01/2025 | MAHAMAYA BURIMA ENTERPRISE | 340.61 | 68.01 | 19.97 | 65
23 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Formal work order for the work of Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Uttar Harishchandrapur Zone-I Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000775/2024-2025 | 269/MD | 28/01/2025 | 01/01/2026 | FUTURE | 126.38 | 0 | 0 | 50
24 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Laying of Additional Pipeline HDPE in connection with Jal Jeevan Mission (JJM) at Uttar Harishchandrapur Zone-II Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000624/2024-2025 | 5831/MD | 22/11/2024 | 05/10/2025 | KUNDU CONSTRUCTION | 95.04 | 0 | 0 | 0
25 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Construction of Boundary Wall at 3rd Tube well site of Uttar Harishchandrapur Zone-I Water Supply Scheme under Harischandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000210/2024-2025 | 3031/MD | 13/06/2024 | 01/11/2025 | M/S GHOSH CONSTRUCTION | 10.19 | 0 | 0 | 0
26 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Construction of Boundary Wall at Head Work site of Uttar Harishchandrapur Zone-I Water Supply Scheme under Harischandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000489/2024-2025 | 5002/MD | 27/09/2024 | 24/06/2025 | SAJEDUR RAHAMAN | 34.41 | 0 | 0 | 80
27 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Road restoration work related to laying of Pipeleine at Uttar Harishchandrapur Zone-I Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. (2nd Call) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000159/2025-2026 | 2881/MD | 17/06/2025 | 01/08/2025 | PRADIP KUMAR DAS | 56.21 | 0 | 0 | 0
28 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room at Pump House No. 4 of Uttar Harishchandrapur Zone-I PWSS under Harishchandrapur-I Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000107/2025-2026 | 2278/MD | 21/05/2025 | 05/07/2025 | MASUMA ENTERPRISE | 4.28 | 0 | 0 | 100
29 | MALDAH |  | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Uttar Harishchandrapur Zone-II Water Supply Scheme under Harishchandrtapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Tilok Roy, Junior Engineer | ORD/000790/2024-2025 | 355/MD | 30/01/2025 | 16/03/2025 | AHONA ENTERPRISE | 40.23 | 0 | 0 | 0
Total | [13 empty] | 1796.65 | 677.64 | 37.72