## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | INSTALLATION OF 105 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES(AWCs) OF GP -BAHIRGACHHI-I,PANDUA,MAJHRA,RANIGANJ-I & RANIGANJ-II IN GAZOLE DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. | SM/10303 | Anganwadi | Acceptance cum formal work order for Supplying G.I. pipe strainer for installation of CWPP at AWC of G.P.- Bahirgachhi-I, Pandua, Majhra, Raniganj-I & Raniganj-II in Gazole Dev. Block at Mangalbari Stack Yard under Malda Division, PHE Dte.(Part-I) | Mr. Arnab Giri, Assistant Engineer | Biswajit Gosh, Junior Engineer | ORD/000050/2022-2023 | 1434/MD | 20/06/2022 | 05/07/2022 | M/S TAPAS KUMAR CHAKRABORTY | 18.82 | 18.82 | 100 | 100
2 | MALDAH |  | Malda Division | INSTALLATION OF 105 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES(AWCs) OF GP -BAHIRGACHHI-I,PANDUA,MAJHRA,RANIGANJ-I & RANIGANJ-II IN GAZOLE DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. | SM/10303 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) at different Anganwadi Centres (AWCs) of G.P.- Bahirgachhi-I, Pandua, Majhra, Raniganj-I & Raniganj-II in Gazole Dev. Block, Malda under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Biswajit Gosh, Junior Engineer | ORD/000012/2022-2023 | 1139/MD | 20/05/2022 | 17/09/2022 | M/S TAPAS KUMAR CHAKRABORTY | 600.86 | 262.6 | 43.7 | 83
3 | MALDAH |  | Malda Division | INSTALLATION OF 105 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES(AWCs) OF GP -BAHIRGACHHI-I,PANDUA,MAJHRA,RANIGANJ-I & RANIGANJ-II IN GAZOLE DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. | SM/10303 | Anganwadi | Material Requisition To Resource Division |  |  | RTOR000007/2021-2022 | 518/MD | 03/03/2022 |  | Resource Division | 106.49 | 0 | 0 | 0
4 | MALDAH |  | Malda Division | INSTALLATION OF 105 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES(AWCs) OF GP -BAHIRGACHHI-I,PANDUA,MAJHRA,RANIGANJ-I & RANIGANJ-II IN GAZOLE DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. | SM/10303 | Anganwadi | Material Requisition To Resource Division |  |  | RTOR000139/2023-2024 | 117/MD | 05/01/2024 |  | Resource Division | 7.74 | 0 | 0 | 0
Total | [13 empty] | 733.9 | 281.41 | 38.34