## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | INSTALLATION OF 89 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES(AWCs) OF HARISHCHANDRAPUR-I DEV BLOCK MALDA UNDER MALDA DIVISION,PHE DTE | SM/10304 | Anganwadi | Acceptance cum formal work order for Installation of Stand-Alone Community Purification Plant (CWPP) for AWC's at Boroi Mahendrapur GP of Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. (QTY:- 6 Nos.) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000393/2022-2023 | 2721/MD | 17/11/2022 | 16/01/2023 | M/S S. S. ENTERPRISE | 41.18 | 33.75 | 81.96 | 47
2 | MALDAH |  | Malda Division | INSTALLATION OF 89 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES(AWCs) OF HARISHCHANDRAPUR-I DEV BLOCK MALDA UNDER MALDA DIVISION,PHE DTE | SM/10304 | Anganwadi | Acceptance cum formal work order for Installation of Stand-Alone Community Purification Plant (CWPP) for AWC's at Kushida and Rashidabad GP of Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. (QTY:-12 Nos.) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000394/2022-2023 | 2722/MD | 17/11/2022 | 16/01/2023 | ASIT PRAMANIK | 82.34 | 0 | 0 | 100
3 | MALDAH |  | Malda Division | INSTALLATION OF 89 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES(AWCs) OF HARISHCHANDRAPUR-I DEV BLOCK MALDA UNDER MALDA DIVISION,PHE DTE | SM/10304 | Anganwadi | Acceptance cum formal work order for Installation of Stand-Alone Community Purification Plant (CWPP) for AWC's at Harishchandrapur GP of Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. (QTY:-14 Nos.) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000389/2022-2023 | 2717/MD | 17/11/2022 | 16/01/2023 | M/S DAS CONSTRUCTION | 96.05 | 84.85 | 88.34 | 49
4 | MALDAH |  | Malda Division | INSTALLATION OF 89 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES(AWCs) OF HARISHCHANDRAPUR-I DEV BLOCK MALDA UNDER MALDA DIVISION,PHE DTE | SM/10304 | Anganwadi | Material Requisition To Resource Division |  |  | RTOR000014/2021-2022 | 527/MD | 03/03/2022 | 03/03/2022 | Resource Division | 58.62 | 0 | 0 | 0
5 | MALDAH |  | Malda Division | INSTALLATION OF 89 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES(AWCs) OF HARISHCHANDRAPUR-I DEV BLOCK MALDA UNDER MALDA DIVISION,PHE DTE | SM/10304 | Anganwadi | Acceptance cum formal work order for Installation of Stand-Alone Community Purification Plant (CWPP) for AWC's at Boroi Mahendrapur GP of Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. (QTY:- 7 Nos.) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation,Mr. Tilok Roy, Junior Engineer | ORD/000392/2022-2023 | 2720/MD | 17/11/2022 | 16/01/2023 | ZEOLITE FRESH INDIA | 48.09 | 0 | 0 | 50
6 | MALDAH |  | Malda Division | INSTALLATION OF 89 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES(AWCs) OF HARISHCHANDRAPUR-I DEV BLOCK MALDA UNDER MALDA DIVISION,PHE DTE | SM/10304 | Anganwadi | Acceptance cum formal work order for Installation of Stand-Alone Community Purification Plant (CWPP) for AWC's at Bhingal GP of Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. (QTY:-9 Nos.) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000390/2022-2023 | 2718/MD | 17/11/2022 | 16/01/2023 | BANIK BROTHERS | 61.83 | 53.06 | 85.81 | 0
7 | MALDAH |  | Malda Division | INSTALLATION OF 89 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES(AWCs) OF HARISHCHANDRAPUR-I DEV BLOCK MALDA UNDER MALDA DIVISION,PHE DTE | SM/10304 | Anganwadi | Installation of Solar Powered Standalone Community Water Purification Plant (CWPP) for AWC's at different places of Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. (Quantity: 15 Nos.) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Susanta Pal, JE_Deputation | ORD/000043/2025-2026 | 1913/MD | 14/05/2025 | 11/10/2025 | SHREE BISHNU CONSTRUCTION | 96.81 | 0 | 0 | 0
8 | MALDAH |  | Malda Division | INSTALLATION OF 89 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES(AWCs) OF HARISHCHANDRAPUR-I DEV BLOCK MALDA UNDER MALDA DIVISION,PHE DTE | SM/10304 | Anganwadi | Acceptance cum formal work order for Installation of Stand-Alone Community Purification Plant (CWPP) for AWC's at Tulshihata GP of Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. (QTY:-10 Nos.) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Tilok Roy, Junior Engineer | ORD/000391/2022-2023 | 2719/MD | 17/11/2022 | 31/10/2023 | PACIFIC ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 68.5 | 55.72 | 81.35 | 100
Total | [13 empty] | 553.42 | 227.39 | 41.09