## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | INSTALLATION OF 128 Nos. STANDALONE COMMUNITY PURIFICATION PLANT (CWPP)AT ANGANWADI CENTRES(AWCs) OF GP-AIHO,BULBULCHANDI,KANTURKA,DHUMPUR,RISHIPUR& SRIRAMPUR IN HABIBPUR DEV BLOCK MALDA UNDER MALDA DIVISION,PHE DTE. | SM/10306 | Anganwadi | Acceptance cum formal work order for Supplying G.I. pipe strainer for installation of CWPP at AWC of G.P.- Aiho, Bulbulchandi, Kanturka, Dhumpur, Rishipur & Srirampur in Habibpur Dev. Block at Mangalbari Stack Yard under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Sumit Kumar Ganguly, Junior Engineer | ORD/000057/2022-2023 | 1501/MD | 28/06/2022 | 13/07/2022 | MERCURY ENGINEERING COMPANY | 23.05 | 23.05 | 100 | 0
2 | MALDAH |  | Malda Division | INSTALLATION OF 128 Nos. STANDALONE COMMUNITY PURIFICATION PLANT (CWPP)AT ANGANWADI CENTRES(AWCs) OF GP-AIHO,BULBULCHANDI,KANTURKA,DHUMPUR,RISHIPUR& SRIRAMPUR IN HABIBPUR DEV BLOCK MALDA UNDER MALDA DIVISION,PHE DTE. | SM/10306 | Anganwadi | Material Requisition To Resource Division |  |  | RTOR000010/2021-2022 | 526/MD | 03/03/2022 | 03/03/2022 | Resource Division | 84.31 | 0 | 0 | 0
3 | MALDAH |  | Malda Division | INSTALLATION OF 128 Nos. STANDALONE COMMUNITY PURIFICATION PLANT (CWPP)AT ANGANWADI CENTRES(AWCs) OF GP-AIHO,BULBULCHANDI,KANTURKA,DHUMPUR,RISHIPUR& SRIRAMPUR IN HABIBPUR DEV BLOCK MALDA UNDER MALDA DIVISION,PHE DTE. | SM/10306 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) at different Anganwadi Centres (AWCs) of G.P.- Aiho, Bulbulchandi, Kanturka, Dhumpur, Rishipur & Srirampur in Habibpur Dev. Block, Malda under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000011/2022-2023 | 1136/MD | 20/05/2022 | 17/09/2022 | M/S S. DAS & ENTERPRISE | 732.48 | 263.5 | 35.97 | 90
Total | [13 empty] | 839.84 | 286.56 | 34.12