## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | INSTALLATION OF 85 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES OF GP-ALAL,KARKACH,DEOTALA& BABUPUR IN GAZOLE DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. | SM/10307 | Anganwadi | Material Requisition To Resource Division |  |  | RTOR000020/2021-2022 | 525/MD | 03/03/2022 | 03/03/2022 | Resource Division | 44.95 | 0 | 0 | 0
2 | MALDAH |  | Malda Division | INSTALLATION OF 85 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES OF GP-ALAL,KARKACH,DEOTALA& BABUPUR IN GAZOLE DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. | SM/10307 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWC's at Karkach GP of Gazole Dev. Block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Biswajit Gosh, Junior Engineer | ORD/000454/2022-2023 | 116/MD | 18/01/2023 | 03/04/2023 | MERCURY ENGINEERING COMPANY | 218.07 | 0 | 0 | 100
3 | MALDAH |  | Malda Division | INSTALLATION OF 85 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES OF GP-ALAL,KARKACH,DEOTALA& BABUPUR IN GAZOLE DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. | SM/10307 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWC's at Alal, Deotola & Babupur GP of Gazole Dev. Block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000461/2022-2023 | 61/MD | 16/01/2023 | 01/04/2023 | PRADIP KUMAR DAS | 218.07 | 0 | 0 | 100
4 | MALDAH |  | Malda Division | INSTALLATION OF 85 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES OF GP-ALAL,KARKACH,DEOTALA& BABUPUR IN GAZOLE DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. | SM/10307 | Anganwadi | Installation of Solar Powered Standalone Community Water Purification Plant (CWPP) for AWC's at different places of Gazole Dev. Block under Malda Division, PHE Dte. (Quantity: 14 Nos.) | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000044/2025-2026 | 2408/MD | 27/05/2025 | 24/10/2025 | BANIK BROTHERS | 90.71 | 0 | 0 | 0
Total | [13 empty] | 571.8 | 0 | 0