## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Augmentation of Mirzapur Piped Water Supply Scheme | SM/10317 | Augmentation | Acceptance cum formal work order for Route survey for distribution network design for augmentation of Mirzapur Water Supply Scheme in Bamongola block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000146/2021-2022 | 1744/MD | 15/06/2021 | 29/06/2021 | HORIZEN | 2.86 | 2.28 | 79.82 | 1
2 | MALDAH |  | Malda Division | Augmentation of Mirzapur Piped Water Supply Scheme | SM/10317 | Augmentation | Acceptance cum formal work order for Design, Preparation & Submission of DPR as per existing route survey data for Augmentation of Mirzapur Piped Water Supply Scheme under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000534/2021-2022 | 2687/MD | 09/09/2021 | 16/09/2021 | HORIZEN | 1.25 | 1.25 | 100 | 1
3 | MALDAH |  | Malda Mechanical | Augmentation of Mirzapur Piped Water Supply Scheme | SM/10317 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of MIRZAPUR Water Supply Scheme T/W no. II in the District of Malda under Malda Mechanical Division, PHE Dte. | Assistant Engineer - II |  | ORD/000964/2022-2023 | 2950/MLMD | 28/12/2022 | 26/02/2023 | MERCURY ENGINEERING COMPANY. | 11.06 | 9.79 | 88.51 | 1
4 | MALDAH |  | Malda Mechanical | Augmentation of Mirzapur Piped Water Supply Scheme | SM/10317 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of MIRZAPUR Water Supply Scheme T/W no. I in the District of Malda under Malda Mechanical Division, PHE Dte. | Assistant Engineer - II |  | ORD/000963/2022-2023 | 2949/MLMD | 28/12/2022 | 26/02/2023 | DEY ENTERPRISE.. | 11.13 | 9.86 | 88.55 | 1
5 | MALDAH |  | Malda Mechanical | Augmentation of Mirzapur Piped Water Supply Scheme | SM/10317 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of Mirzapur, Bamongola C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000104/2023-2024 | 3004228429 | 26/04/2023 | 25/07/2023 | W.B.S.E.D.C.LTD | 6.85 | 6.85 | 100 | 0
6 | MALDAH |  | Malda Mechanical | Augmentation of Mirzapur Piped Water Supply Scheme | SM/10317 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. IV of Mirzapur, Bamongola C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000103/2023-2024 | 3004228411 | 26/04/2023 | 25/07/2023 | W.B.S.E.D.C.LTD | 4.57 | 4.57 | 100 | 0
7 | MALDAH |  | Malda Division | Augmentation of Mirzapur Piped Water Supply Scheme | SM/10317 | Augmentation | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to tubewell No 3 at Mirzapur PWSS of Bamongola Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000461/2023-2024 | 3394/MD | 31/08/2023 | 15/10/2023 | DIPU DUTTA | 4.16 | 0 | 0 | 0
8 | MALDAH |  | Malda Division | Augmentation of Mirzapur Piped Water Supply Scheme | SM/10317 | Augmentation | Acceptance cum formal work order for Sinking of 300mm. Dia. x 200 mm. dia. and 140 Mtr. Deep Big dia Tube well (1 No) at Mirzapur Water Supply Scheme under Bamangola Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000017/2023-2024 | 1674/MD | 18/04/2023 | 18/05/2023 | A. L. ENGINEERING SOLUTION | 12.77 | 0 | 0 | 100
9 | MALDAH |  | Malda Mechanical | Augmentation of Mirzapur Piped Water Supply Scheme | SM/10317 | Augmentation | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-II for the office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - II | Junior Engineer-04 | ORD/000086/2023-2024 | 699/MLMD | 10/04/2023 | 10/06/2023 | SUBRATA SAHA | 0.29 | 0 | 0 | 100
10 | MALDAH |  | Malda Mechanical | Augmentation of Mirzapur Piped Water Supply Scheme | SM/10317 | Augmentation | Claim for purchase of fuel for hiring of inspection for different site visit use for Assistant Engineer-II ,Under Mechanical Division, P.H.E. Dte. | Assistant Engineer - II | Junior Engineer-04 | ORD/001362/2022-2023 | 270/MLMD. | 24/02/2023 | 24/04/2023 | SUBRATA SAHA | 0.44 | 0.44 | 100 | 100
11 | MALDAH |  | Malda Mechanical | Augmentation of Mirzapur Piped Water Supply Scheme | SM/10317 | Augmentation | Claim for purchase of fuel for hiring of inspection for different site visit use for Assistant Engineer-II ,Under Mechanical Division, P.H.E. Dte. |  | Junior Engineer-06 | ORD/000726/2023-2024 | 699/MLMD. | 10/04/2023 | 17/04/2023 | SUBRATA SAHA | 0.46 | 0 | 0 | 100
12 | MALDAH |  | Malda Mechanical | Augmentation of Mirzapur Piped Water Supply Scheme | SM/10317 | Augmentation | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-II for the office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - II | Junior Engineer-04 | ORD/001147/2022-2023 | 270/MLMD | 24/02/2023 | 24/04/2023 | SUBRATA SAHA | 0.29 | 0.29 | 100 | 100
13 | MALDAH |  | Malda Division | Augmentation of Mirzapur Piped Water Supply Scheme | SM/10317 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000014/2022-2023 | 1873/MD | 16/08/2022 | 16/08/2022 | Resource Division | 132.02 | 0 | 0 | 0
14 | MALDAH |  | Malda Division | Augmentation of Mirzapur Piped Water Supply Scheme | SM/10317 | Augmentation | Placement of fund against the work for Road restoration work for laying of pipe line for Bamongala Habibpur Road (Portion from 7.00 kmp to 7.50 kmp) for Mirzapur Piped Water Supply Scheme under Malda Division, PHE Dte. |  |  | BILL/00530/2022-2023 | BP-2022-23-211 | 16/03/2023 | 16/03/2023 | EXECUTIVE ENGINEER, MALDA HIGHWAY DIVISION, P.W. (ROADS) DIRECTORATE. | 3.11 | 0 | 0 | 0
15 | MALDAH |  | Malda Division | Augmentation of Mirzapur Piped Water Supply Scheme | SM/10317 | Augmentation | Formal work order for the work of Construction of 600 M3 Capacity OHR with FHTC (Mouza- Jaitan, Mirzapur, Mukuli and Salalpur) of Mirzapur Piped Water Supply Scheme at Bamangola Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000312/2023-2024 | 2917/MD | 31/07/2023 | 29/05/2025 | MATIUR RAHAMAN | 281.67 | 0 | 0 | 89
16 | MALDAH |  | Malda Division | Augmentation of Mirzapur Piped Water Supply Scheme | SM/10317 | Augmentation | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 120 m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at Head Work Site of Mirzapur Water Supply Scheme of Bamangola Block under Malda Division P.H.E Dte in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000601/2024-2025 | 5740/MD | 20/11/2024 | 20/03/2025 | DEBAPRIYA SAHA | 45.31 | 0 | 0 | 0
17 | MALDAH |  | Malda Division | Augmentation of Mirzapur Piped Water Supply Scheme | SM/10317 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) and Laying of 90 mm dia (OD) uPVC Pipeline under command area of MIRZAPUR Water Supply Scheme at Bamangola Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000224/2024-2025 | 3026/MD | 13/06/2024 | 01/03/2025 | M/S KUNDU CONSTRUCTION | 89.01 | 0 | 0 | 90
18 | MALDAH |  | Malda Division | Augmentation of Mirzapur Piped Water Supply Scheme | SM/10317 | Augmentation | Construction of Boundary Wall at 4th Tubewell Site of Mirzapur Water Supply Scheme under Bamongola Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000309/2024-2025 | 3949/MD | 07/08/2024 | 21/09/2024 | HIRAK ROY CHOUDHURY | 7.45 | 0 | 0 | 0
19 | MALDAH |  | Malda Division | Augmentation of Mirzapur Piped Water Supply Scheme | SM/10317 | Augmentation | Formal work order for the work of Laying Distribution pipe line for MIRZAPUR & its adjoining mouzas piped water supply at Bamongola Block in the District Malda under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000130/2022-2023 | 1747/MD | 27/07/2022 | 25/09/2022 | UTTAM KUMAR DUTTA | 163.77 | 157.81 | 96.36 | 100
20 | MALDAH |  | Malda Division | Augmentation of Mirzapur Piped Water Supply Scheme | SM/10317 | Augmentation | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to tubewell No 4 at Mirzapur PWSS of Bamongola Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000462/2023-2024 | 3395/MD | 31/08/2023 | 15/10/2023 | SARANGA SARKAR | 4.17 | 0 | 0 | 100
21 | MALDAH |  | Malda Division | Augmentation of Mirzapur Piped Water Supply Scheme | SM/10317 | Augmentation | Dismentling of Concrete road and Construction the same at different places of road connecting to LDS of Augmentation of MIRZAPUR Water Supply Scheme at Bamangola Dev. Block under Malda Division, P.H.E.Dte. In the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000152/2024-2025 | 2921/MD | 10/06/2024 | 10/07/2024 | UTTAM KUMAR DUTTA | 12.53 | 0 | 0 | 100
22 | MALDAH |  | Malda Mechanical | Augmentation of Mirzapur Piped Water Supply Scheme | SM/10317 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of augmentation of MIRZAPUR Water Supply Scheme T/W no. III in the District of Malda under Malda Mechanical Division, PHE Dte. | Assistant Engineer - II | Junior Engineer-03 | ORD/000965/2022-2023 | 2951/MLMD | 28/12/2022 | 12/12/2025 | M/S D.G.B. ENTERPRISE. | 11.25 | 8.37 | 74.38 | 1
23 | MALDAH |  | Malda Division | Augmentation of Mirzapur Piped Water Supply Scheme | SM/10317 | Augmentation | Laying of Rising Main including Specials and Valves for Mirzapur Piped Water Supply Scheme at Bamongola Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Debasis Pal, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000139/2025-2026 | 2617/MD | 02/06/2025 | 17/07/2025 | ANJIMA CONSTRUCTION CO. | 13.72 | 0 | 0 | 0
24 | MALDAH |  | Malda Division | Augmentation of Mirzapur Piped Water Supply Scheme | SM/10317 | Augmentation | Augmentation work of Pump Houses and Boundary Walls with New Construction of Boundary wall and Pump House (5.40x3.60 m) at Head work site of MIRZAPUR Water Supply Scheme at Bamangola Dev. Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Mukaddar Parvage, Junior Engineer | ORD/000003/2025-2026 | 2413/MD | 27/05/2025 | 10/08/2025 | MATIUR RAHAMAN | 38.45 | 0 | 0 | 0
25 | MALDAH |  | Malda Division | Augmentation of Mirzapur Piped Water Supply Scheme | SM/10317 | Augmentation | Sinking of Tubewell No 3 at Mirzapur Water Supply Scheme under Bamongola Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Debasis Pal, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000864/2024-2025 | 1220/MD | 26/03/2025 | 10/05/2025 | BABLU MANDAL | 12.17 | 0 | 0 | 0
26 | MALDAH |  | Malda Division | Augmentation of Mirzapur Piped Water Supply Scheme | SM/10317 | Augmentation | Sinking of Tubewell No 4 at Mirzapur Water Supply Scheme under Bamongola Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Debasis Pal, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000865/2024-2025 | 1221/MD | 26/03/2025 | 10/05/2025 | BABLU MANDAL | 12.04 | 0 | 0 | 0
27 | MALDAH |  | Malda Division | Augmentation of Mirzapur Piped Water Supply Scheme | SM/10317 | Augmentation | Emergent work for better functionally of existing FHTC connection on different diameter Pipeline for MIRZAPUR Piped Water Supply Scheme at Bamangola Dev. Block in the District Malda under Malda Division, PHE Dte. | Mr. Debasis Pal, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000194/2025-2026 | 3628/MD | 24/07/2025 | 22/09/2025 | SAJEDUR RAHAMAN | 8.76 | 0 | 0 | 0
28 | MALDAH |  | Malda Mechanical | Augmentation of Mirzapur Piped Water Supply Scheme | SM/10317 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of augmentation of MIRZAPUR Water Supply Scheme T/W no. IV in the District of Malda under Malda Mechanical Division, PHE Dte. | Assistant Engineer - II | Junior Engineer-03 | ORD/000966/2022-2023 | 2952/MLMD | 28/12/2022 | 18/03/2025 | DILIP MAHATO. | 11.25 | 8.89 | 79.03 | 78
Total | [13 empty] | 902.81 | 210.39 | 23.3