## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Installation of stand alone community purification plant (108 nos.) at Anganwadi centres(AWCs) of Chanchal-I dev block ,Malda under Malda Division,PHE Dte. | SM/10379 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWCs at Bhagabanpur-II & Mahanandapur GP of Chanchal-I Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer,Yusuf Sk, Junior Engineer | ORD/000586/2022-2023 | 827/MD | 21/02/2023 | 07/05/2023 | MILLENNIUM ENTERPRISR | 93.38 | 0 | 0 | 0
2 | MALDAH |  | Malda Division | Installation of stand alone community purification plant (108 nos.) at Anganwadi centres(AWCs) of Chanchal-I dev block ,Malda under Malda Division,PHE Dte. | SM/10379 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWC's at Alihanda & Mokdumpur GP of Chanchal-I Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer,Yusuf Sk, Junior Engineer | ORD/000456/2022-2023 | 601/MD | 10/02/2023 | 26/04/2023 | M/S TAPAS KUMAR CHAKRABORTY | 124.45 | 118.88 | 95.53 | 100
3 | MALDAH |  | Malda Division | Installation of stand alone community purification plant (108 nos.) at Anganwadi centres(AWCs) of Chanchal-I dev block ,Malda under Malda Division,PHE Dte. | SM/10379 | Anganwadi | Material Requisition To Resource Division |  |  | RTOR000023/2021-2022 | 718/MD | 25/03/2022 | 25/03/2022 | Resource Division | 65.14 | 0 | 0 | 0
4 | MALDAH |  | Malda Division | Installation of stand alone community purification plant (108 nos.) at Anganwadi centres(AWCs) of Chanchal-I dev block ,Malda under Malda Division,PHE Dte. | SM/10379 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWCs at Chanchal & Matiharpur GP of Chanchal-I Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000519/2022-2023 | 480/MD | 07/02/2023 | 23/04/2023 | DUTTA ENTERPRISE | 186.76 | 0 | 0 | 90
5 | MALDAH |  | Malda Division | Installation of stand alone community purification plant (108 nos.) at Anganwadi centres(AWCs) of Chanchal-I dev block ,Malda under Malda Division,PHE Dte. | SM/10379 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWC's at Kaligram & Khorba GP of Chanchal-I Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000492/2022-2023 | 93/MD | 17/01/2023 | 02/04/2023 | MAMATA USHA ENTERPRISE | 118.39 | 91.81 | 77.55 | 99
Total | [13 empty] | 588.13 | 210.69 | 35.82