## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Anganwadi(103 nos) Centres (AWCs) of Chanchal-II Dev. Block, Malda under Malda Division, PHE Dte. | SM/10380 | Anganwadi | Material Requisition To Resource Division |  |  | RTOR000022/2021-2022 | 717/MD | 25/03/2022 |  | Resource Division | 67.41 | 0 | 0 | 0
2 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Anganwadi(103 nos) Centres (AWCs) of Chanchal-II Dev. Block, Malda under Malda Division, PHE Dte. | SM/10380 | Anganwadi | Material Requisition To Resource Division |  |  | RTOR000174/2023-2024 | 424/MD | 19/01/2024 |  | Resource Division | 98.18 | 0 | 0 | 0
3 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Anganwadi(103 nos) Centres (AWCs) of Chanchal-II Dev. Block, Malda under Malda Division, PHE Dte. | SM/10380 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWCs at Bhakri & Kshempur GP of Chanchal-II Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000512/2022-2023 | 453/MD | 03/02/2023 | 19/04/2023 | MOTI RAHAMAN | 168.68 | 25.82 | 15.3 | 25
4 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Anganwadi(103 nos) Centres (AWCs) of Chanchal-II Dev. Block, Malda under Malda Division, PHE Dte. | SM/10380 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWCs at Jalalpur & Malatipur GP of Chanchal-II Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000918/2023-2024 | 371/MD | 16/01/2024 | 31/03/2024 | M/S S. DAS & ENTERPRISE | 191.7 | 48.09 | 25.08 | 50
5 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Anganwadi(103 nos) Centres (AWCs) of Chanchal-II Dev. Block, Malda under Malda Division, PHE Dte. | SM/10380 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWCs at Gour Handa and Dhangara Bishanpur GP of Chanchal-II Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000581/2022-2023 | 826/MD | 21/02/2023 | 07/05/2023 | M/S S. S. ENTERPRISE | 191.7 | 112.2 | 58.53 | 70
6 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Anganwadi(103 nos) Centres (AWCs) of Chanchal-II Dev. Block, Malda under Malda Division, PHE Dte. | SM/10380 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWCs at Chandrapara GP of Chanchal-II Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Junior Engineer,Mr. Sanjit Sarkar, Junior Engineer ,Mr. Tilok Roy, Junior Engineer | ORD/000531/2022-2023 | 552/MD | 09/02/2023 | 25/04/2023 | MILLENNIUM ENTERPRISR | 107.29 | 51.6 | 48.1 | 97
Total | [13 empty] | 824.94 | 237.71 | 28.81