## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(112 nos )of Harishchandrapur-II Dev. Block, Malda under Malda Division, PHE Dte. | SM/10381 | School | Material Requisition To Resource Division |  |  | RTOR000030/2021-2022 | 725/MD | 25/03/2022 | 25/03/2022 | Resource Division | 73.75 | 0 | 0 | 0
2 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(112 nos )of Harishchandrapur-II Dev. Block, Malda under Malda Division, PHE Dte. | SM/10381 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Malior-I & Malior-II GP of Harishchandrapur-II Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000457/2022-2023 | 37/MD | 16/01/2023 | 01/04/2023 | A. D. D. ASSOCIATES | 123.99 | 114.31 | 92.2 | 100
3 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(112 nos )of Harishchandrapur-II Dev. Block, Malda under Malda Division, PHE Dte. | SM/10381 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Sadlichak & Bhaluka GP of Harishchandrapur-II Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Tilok Roy, Junior Engineer | ORD/000495/2022-2023 | 91/MD | 17/01/2023 | 02/04/2023 | M/S TRILOCHAN CONSTRUCTION CO | 107.77 | 82.95 | 76.96 | 95
4 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(112 nos )of Harishchandrapur-II Dev. Block, Malda under Malda Division, PHE Dte. | SM/10381 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Doulatpur & Mashaldaha GP of Harishchandrapur-II Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000496/2022-2023 | 86/MD | 17/01/2023 | 02/04/2023 | M/S TRILOCHAN CONSTRUCTION CO | 107.82 | 100.91 | 93.6 | 97
5 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(112 nos )of Harishchandrapur-II Dev. Block, Malda under Malda Division, PHE Dte. | SM/10381 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Sultannagar GP of Harishchandrapur-II Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation,Mr. Tilok Roy, Junior Engineer | ORD/000424/2022-2023 | 3195/MD | 27/12/2022 | 01/01/2024 | MUNNA AGROTECH ENTERPRISE | 91.69 | 83.67 | 91.25 | 60
6 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(112 nos )of Harishchandrapur-II Dev. Block, Malda under Malda Division, PHE Dte. | SM/10381 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Islampur & Daulatnagar GP of Harishchandrapur-II Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000458/2022-2023 | 41/MD | 16/01/2023 | 01/08/2024 | MILLENNIUM ENTERPRISR | 140.16 | 110.46 | 78.81 | 100
Total | [13 empty] | 645.18 | 492.3 | 76.3