## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant (128 nos.) at Schools of Gazole Dev. Block, Malda under Malda Division, PHE Dte. | SM/10383 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Deotala & Alal GP of Gazole Dev. Block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000498/2022-2023 | 85/MD | 17/01/2023 | 18/03/2023 | M/S DAS CONSTRUCTION | 96.99 | 92.57 | 95.44 | 100
2 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant (128 nos.) at Schools of Gazole Dev. Block, Malda under Malda Division, PHE Dte. | SM/10383 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Gazole-I & Gazole-II GP of Gazole Dev. Block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Biswajit Gosh, Junior Engineer | ORD/000494/2022-2023 | 92/MD | 17/01/2023 | 02/04/2023 | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 113.26 | 106.75 | 94.25 | 59
3 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant (128 nos.) at Schools of Gazole Dev. Block, Malda under Malda Division, PHE Dte. | SM/10383 | School | Material Requisition To Resource Division |  |  | RTOR000028/2021-2022 | 723/MD | 25/03/2022 | 25/03/2022 | Resource Division | 84.32 | 0 | 0 | 0
4 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant (128 nos.) at Schools of Gazole Dev. Block, Malda under Malda Division, PHE Dte. | SM/10383 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Salaidanga GP of Gazole Dev. Block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000452/2022-2023 | 59/MD | 16/01/2023 | 01/04/2023 | M/S TRILOCHAN CONSTRUCTION CO | 107.8 | 93.04 | 86.31 | 100
5 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant (128 nos.) at Schools of Gazole Dev. Block, Malda under Malda Division, PHE Dte. | SM/10383 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Raniganj-I & II and Majhra GP of Gazole Dev. Block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000462/2022-2023 | 40/MD | 16/01/2023 | 01/04/2023 | A. D. D. ASSOCIATES | 123.99 | 118.61 | 95.66 | 90
6 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant (128 nos.) at Schools of Gazole Dev. Block, Malda under Malda Division, PHE Dte. | SM/10383 | School | Material Requisition To Resource Division |  |  | RTOR000140/2023-2024 | 120/MD | 05/01/2024 | 05/01/2024 | Resource Division | 8.16 | 0 | 0 | 0
7 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant (128 nos.) at Schools of Gazole Dev. Block, Malda under Malda Division, PHE Dte. | SM/10383 | School | Installation of Solar Powered Standalone Community Water Purification Plant (CWPP) for Schools at different places of Gazole Dev. Block under Malda Division, PHE Dte. (Quantity: 7 Nos.) | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000045/2025-2026 | 1914/MD | 14/05/2025 | 11/10/2025 | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 40.41 | 0 | 0 | 0
8 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant (128 nos.) at Schools of Gazole Dev. Block, Malda under Malda Division, PHE Dte. | SM/10383 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Chaknagar & Karkach GP of Gazole Dev. Block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000497/2022-2023 | 84/MD | 17/01/2023 | 02/09/2024 | M/S DAS CONSTRUCTION | 102.38 | 87.44 | 85.41 | 60
9 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant (128 nos.) at Schools of Gazole Dev. Block, Malda under Malda Division, PHE Dte. | SM/10383 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Pandua and Bahirgachhi-II GP of Gazole Dev. Block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer ,Biswajit Ghosh, Junior Engineer | ORD/000451/2022-2023 | 62/MD | 16/01/2023 | 31/12/2024 | MERCURY ENGINEERING COMPANY | 107.9 | 36.57 | 33.89 | 100
Total | [13 empty] | 785.21 | 534.97 | 68.13